## Overview
Residential development ¦ programme and controls
CE-R01-PC / logic-linked baseline / 6 towers / 288 apartments / Rev 01
PROGRAMME SUMMARY | BASELINE
Activities | 809
Logic links | 972
Duration, working days | 502
Practical completion | 2028-06-08
Target headroom, workdays | 122
Critical activities | 82
Direct budget, USD | 22616875.3938
Peak weekly average workforce | 213.6667
Weeks exceeding crew thresholds | 0
PLANNING BASIS
Six-day working calendar. No site actuals or approved contract baseline are represented.
CPM network is logic-linked. Weekly resource thresholds identify unlevelled overlaps.
MEP and authority interfaces require integration before project execution.
Same direct BOQ budget; detailed time loading is a separate baseline from the cashflow model.

## Controls
Residential development ¦ programme controls
CE-R01-PC / Rev 01 / six blocks / 288 apartments / 70,560 m2
Parameter | Input | Unit | Basis
Baseline start | 2026-11-02T00:00:00.000Z | date | Six working days/week; Sunday excluded
Workdays per week | 6 | days | Calendar table covers 900 working days
Target delivery | 624 | workdays | 24 months at nominal 26 workdays/month
Tower start offset | 12 | workdays | Separate crews allow staggered tower starts
Earthworks workforce capacity | 40 | people | Weekly average planning threshold
Formwork workforce capacity | 150 | people | Weekly average planning threshold
Rebar workforce capacity | 120 | people | Weekly average planning threshold
Concrete workforce capacity | 80 | people | Weekly average planning threshold
Masonry workforce capacity | 120 | people | Weekly average planning threshold
Finishes workforce capacity | 180 | people | Weekly average planning threshold
Envelope workforce capacity | 100 | people | Weekly average planning threshold
External workforce capacity | 50 | people | Weekly average planning threshold
Site workforce capacity | 40 | people | Weekly average planning threshold
Planning date | 2026-10-24T00:00:00.000Z | date | Forecast baseline issue; no actual progress recorded

## Activities
Logic-linked construction baseline
Finish-to-start links with explicit lags. Day offsets use an exclusive finish convention.
Activity ID | Zone | Level | Activity | Trade | Quantity | Unit | Daily output | Crew | Duration wd | ES offset | EF offset | LS offset | LF offset | Total float wd | Start date | Finish date | Direct budget USD | Fixed duration | Daily direct value USD
P-001 | SITE | ALL | Mobilisation and temporary facilities | Site | 1 | lot | 1 | 20 | 18 | 0 | 18 | 0 | 18 | 0 | 2026-11-02 | 2026-11-21 | 0 | 18 | 0
P-010 | POD | B1 | Excavation and surplus disposal | Earthworks | 69192 | m3 | 1800 | 24 | 39 | 18 | 57 | 18 | 57 | 0 | 2026-11-23 | 2027-01-06 | 1009684.8 |  | 25889.3538
P-020 | POD | B1 | Blinding and underslab membrane | Concrete | 1440 | m3 | 160 | 18 | 9 | 57 | 66 | 57 | 66 | 0 | 2027-01-07 | 2027-01-16 | 424800 |  | 47200
P-030 | POD | B1 | Raft reinforcement and preparation | Rebar | 2315.3629 | t | 55 | 55 | 43 | 66 | 109 | 66 | 109 | 0 | 2027-01-18 | 2027-03-08 | 2012050.3419 |  | 46791.8684
P-040 | POD | B1 | Raft base and tower thickening pours | Concrete | 12240 | m3 | 680 | 28 | 18 | 109 | 127 | 109 | 127 | 0 | 2027-03-09 | 2027-03-29 | 1664640 |  | 92480
P-050 | POD | B1 | Basement perimeter walls | Formwork | 502.74 | m3 | 40 | 24 | 13 | 134 | 147 | 412 | 425 | 278 | 2027-04-07 | 2027-04-21 | 155011.5 |  | 11923.9615
P-060 | POD | L00 | Podium roof structural package | Formwork | 2520 | m3 | 180 | 30 | 14 | 147 | 161 | 445 | 459 | 298 | 2027-04-22 | 2027-05-07 | 582120 |  | 41580
P-070 | SITE | B1 | Backfill and perimeter reinstatement | Earthworks | 4392 | m3 | 500 | 16 | 9 | 154 | 163 | 432 | 441 | 278 | 2027-04-30 | 2027-05-10 | 67197.6 |  | 7466.4
T1-L00-F | T1 | L00 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 134 | 140 | 194 | 200 | 60 | 2027-04-07 | 2027-04-13 | 29364.32 |  | 4894.0533
T1-L00-R | T1 | L00 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 140 | 145 | 200 | 205 | 60 | 2027-04-14 | 2027-04-19 | 25795.5172 |  | 5159.1034
T1-L00-C | T1 | L00 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 145 | 147 | 205 | 207 | 60 | 2027-04-20 | 2027-04-21 | 33527.397 |  | 16763.6985
T1-L00-H | T1 | L00 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 147 | 152 | 207 | 212 | 60 | 2027-04-22 | 2027-04-27 | 0 | 5 | 0
T1-L01-F | T1 | L01 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 152 | 158 | 212 | 218 | 60 | 2027-04-28 | 2027-05-04 | 29364.32 |  | 4894.0533
T1-L01-R | T1 | L01 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 158 | 163 | 218 | 223 | 60 | 2027-05-05 | 2027-05-10 | 25795.5172 |  | 5159.1034
T1-L01-C | T1 | L01 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 163 | 165 | 223 | 225 | 60 | 2027-05-11 | 2027-05-12 | 33527.397 |  | 16763.6985
T1-L01-H | T1 | L01 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 165 | 170 | 225 | 230 | 60 | 2027-05-13 | 2027-05-18 | 0 | 5 | 0
T1-L02-F | T1 | L02 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 170 | 176 | 230 | 236 | 60 | 2027-05-19 | 2027-05-25 | 29364.32 |  | 4894.0533
T1-L02-R | T1 | L02 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 176 | 181 | 236 | 241 | 60 | 2027-05-26 | 2027-05-31 | 25795.5172 |  | 5159.1034
T1-L02-C | T1 | L02 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 181 | 183 | 241 | 243 | 60 | 2027-06-01 | 2027-06-02 | 33527.397 |  | 16763.6985
T1-L02-H | T1 | L02 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 183 | 188 | 243 | 248 | 60 | 2027-06-03 | 2027-06-08 | 0 | 5 | 0
T1-L03-F | T1 | L03 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 188 | 194 | 248 | 254 | 60 | 2027-06-09 | 2027-06-15 | 29364.32 |  | 4894.0533
T1-L03-R | T1 | L03 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 194 | 199 | 254 | 259 | 60 | 2027-06-16 | 2027-06-21 | 25795.5172 |  | 5159.1034
T1-L03-C | T1 | L03 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 199 | 201 | 259 | 261 | 60 | 2027-06-22 | 2027-06-23 | 33527.397 |  | 16763.6985
T1-L03-H | T1 | L03 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 201 | 206 | 261 | 266 | 60 | 2027-06-24 | 2027-06-29 | 0 | 5 | 0
T1-L04-F | T1 | L04 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 206 | 212 | 266 | 272 | 60 | 2027-06-30 | 2027-07-06 | 29364.32 |  | 4894.0533
T1-L04-R | T1 | L04 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 212 | 217 | 272 | 277 | 60 | 2027-07-07 | 2027-07-12 | 25795.5172 |  | 5159.1034
T1-L04-C | T1 | L04 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 217 | 219 | 277 | 279 | 60 | 2027-07-13 | 2027-07-14 | 33527.397 |  | 16763.6985
T1-L04-H | T1 | L04 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 219 | 224 | 279 | 284 | 60 | 2027-07-15 | 2027-07-20 | 0 | 5 | 0
T1-L05-F | T1 | L05 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 224 | 230 | 284 | 290 | 60 | 2027-07-21 | 2027-07-27 | 29364.32 |  | 4894.0533
T1-L05-R | T1 | L05 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 230 | 235 | 290 | 295 | 60 | 2027-07-28 | 2027-08-02 | 25795.5172 |  | 5159.1034
T1-L05-C | T1 | L05 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 235 | 237 | 295 | 297 | 60 | 2027-08-03 | 2027-08-04 | 33527.397 |  | 16763.6985
T1-L05-H | T1 | L05 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 237 | 242 | 297 | 302 | 60 | 2027-08-05 | 2027-08-10 | 0 | 5 | 0
T1-L06-F | T1 | L06 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 242 | 248 | 302 | 308 | 60 | 2027-08-11 | 2027-08-17 | 29364.32 |  | 4894.0533
T1-L06-R | T1 | L06 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 248 | 253 | 308 | 313 | 60 | 2027-08-18 | 2027-08-23 | 25795.5172 |  | 5159.1034
T1-L06-C | T1 | L06 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 253 | 255 | 313 | 315 | 60 | 2027-08-24 | 2027-08-25 | 33527.397 |  | 16763.6985
T1-L06-H | T1 | L06 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 255 | 260 | 315 | 320 | 60 | 2027-08-26 | 2027-08-31 | 0 | 5 | 0
T1-L07-F | T1 | L07 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 260 | 266 | 320 | 326 | 60 | 2027-09-01 | 2027-09-07 | 29364.32 |  | 4894.0533
T1-L07-R | T1 | L07 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 266 | 271 | 326 | 331 | 60 | 2027-09-08 | 2027-09-13 | 25795.5172 |  | 5159.1034
T1-L07-C | T1 | L07 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 271 | 273 | 331 | 333 | 60 | 2027-09-14 | 2027-09-15 | 33527.397 |  | 16763.6985
T1-L07-H | T1 | L07 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 273 | 278 | 333 | 338 | 60 | 2027-09-16 | 2027-09-21 | 0 | 5 | 0
T1-L08-F | T1 | L08 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 278 | 284 | 338 | 344 | 60 | 2027-09-22 | 2027-09-28 | 29364.32 |  | 4894.0533
T1-L08-R | T1 | L08 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 284 | 289 | 344 | 349 | 60 | 2027-09-29 | 2027-10-04 | 25795.5172 |  | 5159.1034
T1-L08-C | T1 | L08 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 289 | 291 | 349 | 351 | 60 | 2027-10-05 | 2027-10-06 | 33527.397 |  | 16763.6985
T1-L08-H | T1 | L08 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 291 | 296 | 351 | 356 | 60 | 2027-10-07 | 2027-10-12 | 0 | 5 | 0
T1-L09-F | T1 | L09 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 296 | 302 | 356 | 362 | 60 | 2027-10-13 | 2027-10-19 | 29364.32 |  | 4894.0533
T1-L09-R | T1 | L09 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 302 | 307 | 362 | 367 | 60 | 2027-10-20 | 2027-10-25 | 25795.5172 |  | 5159.1034
T1-L09-C | T1 | L09 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 307 | 309 | 367 | 369 | 60 | 2027-10-26 | 2027-10-27 | 33527.397 |  | 16763.6985
T1-L09-H | T1 | L09 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 309 | 314 | 369 | 374 | 60 | 2027-10-28 | 2027-11-02 | 0 | 5 | 0
T1-L10-F | T1 | L10 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 314 | 320 | 374 | 380 | 60 | 2027-11-03 | 2027-11-09 | 29364.32 |  | 4894.0533
T1-L10-R | T1 | L10 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 320 | 325 | 380 | 385 | 60 | 2027-11-10 | 2027-11-15 | 25795.5172 |  | 5159.1034
T1-L10-C | T1 | L10 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 325 | 327 | 385 | 387 | 60 | 2027-11-16 | 2027-11-17 | 33527.397 |  | 16763.6985
T1-L10-H | T1 | L10 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 327 | 332 | 387 | 392 | 60 | 2027-11-18 | 2027-11-23 | 0 | 5 | 0
T1-L11-F | T1 | L11 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 332 | 338 | 392 | 398 | 60 | 2027-11-24 | 2027-11-30 | 29364.32 |  | 4894.0533
T1-L11-R | T1 | L11 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 338 | 343 | 398 | 403 | 60 | 2027-12-01 | 2027-12-06 | 25795.5172 |  | 5159.1034
T1-L11-C | T1 | L11 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 343 | 345 | 403 | 405 | 60 | 2027-12-07 | 2027-12-08 | 33527.397 |  | 16763.6985
T1-L11-H | T1 | L11 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 345 | 350 | 405 | 410 | 60 | 2027-12-09 | 2027-12-14 | 0 | 5 | 0
T1-L12-F | T1 | L12 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 350 | 356 | 410 | 416 | 60 | 2027-12-15 | 2027-12-21 | 29364.32 |  | 4894.0533
T1-L12-R | T1 | L12 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 356 | 361 | 416 | 421 | 60 | 2027-12-22 | 2027-12-27 | 25795.5172 |  | 5159.1034
T1-L12-C | T1 | L12 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 361 | 363 | 421 | 423 | 60 | 2027-12-28 | 2027-12-29 | 33527.397 |  | 16763.6985
T1-L12-H | T1 | L12 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 363 | 368 | 423 | 428 | 60 | 2027-12-30 | 2028-01-04 | 0 | 5 | 0
T1-RF | T1 | ROOF | Roof membrane and weatherproofing | Envelope | 2400 | m2 | 180 | 10 | 14 | 373 | 387 | 438 | 452 | 65 | 2028-01-11 | 2028-01-26 | 48000 |  | 3428.5714
T1-FA | T1 | ALL | Insulated facade installation | Envelope | 3234.816 | m2 | 150 | 16 | 22 | 306 | 328 | 430 | 452 | 124 | 2027-10-25 | 2027-11-18 | 271724.544 |  | 12351.1156
T1-GL | T1 | ALL | Glazing and frame installation | Envelope | 1257.984 | m2 | 90 | 12 | 14 | 387 | 401 | 452 | 466 | 65 | 2028-01-27 | 2028-02-11 | 276756.48 |  | 19768.32
T1-L00-M | T1 | L00 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 211 | 216 | 433 | 438 | 222 | 2027-07-06 | 2027-07-10 | 12204.27 |  | 2440.854
T1-L00-P | T1 | L00 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 219 | 225 | 441 | 447 | 222 | 2027-07-15 | 2027-07-21 | 15067 |  | 2511.1667
T1-L00-S | T1 | L00 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 227 | 230 | 449 | 452 | 222 | 2027-07-24 | 2027-07-27 | 9048 |  | 3016
T1-L00-T | T1 | L00 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 401 | 407 | 466 | 472 | 65 | 2028-02-12 | 2028-02-18 | 24012 |  | 4002
T1-L00-A | T1 | L00 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 409 | 414 | 474 | 479 | 65 | 2028-02-22 | 2028-02-26 | 10245.56 |  | 2049.112
T1-L00-D | T1 | L00 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 414 | 417 | 479 | 482 | 65 | 2028-02-28 | 2028-03-01 | 5796 |  | 1932
T1-L01-M | T1 | L01 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 229 | 234 | 433 | 438 | 204 | 2027-07-27 | 2027-07-31 | 12204.27 |  | 2440.854
T1-L01-P | T1 | L01 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 237 | 243 | 441 | 447 | 204 | 2027-08-05 | 2027-08-11 | 15067 |  | 2511.1667
T1-L01-S | T1 | L01 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 245 | 248 | 449 | 452 | 204 | 2027-08-14 | 2027-08-17 | 9048 |  | 3016
T1-L01-T | T1 | L01 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 401 | 407 | 466 | 472 | 65 | 2028-02-12 | 2028-02-18 | 24012 |  | 4002
T1-L01-A | T1 | L01 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 409 | 414 | 474 | 479 | 65 | 2028-02-22 | 2028-02-26 | 10245.56 |  | 2049.112
T1-L01-D | T1 | L01 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 414 | 417 | 479 | 482 | 65 | 2028-02-28 | 2028-03-01 | 5796 |  | 1932
T1-L02-M | T1 | L02 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 247 | 252 | 433 | 438 | 186 | 2027-08-17 | 2027-08-21 | 12204.27 |  | 2440.854
T1-L02-P | T1 | L02 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 255 | 261 | 441 | 447 | 186 | 2027-08-26 | 2027-09-01 | 15067 |  | 2511.1667
T1-L02-S | T1 | L02 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 263 | 266 | 449 | 452 | 186 | 2027-09-04 | 2027-09-07 | 9048 |  | 3016
T1-L02-T | T1 | L02 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 401 | 407 | 466 | 472 | 65 | 2028-02-12 | 2028-02-18 | 24012 |  | 4002
T1-L02-A | T1 | L02 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 409 | 414 | 474 | 479 | 65 | 2028-02-22 | 2028-02-26 | 10245.56 |  | 2049.112
T1-L02-D | T1 | L02 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 414 | 417 | 479 | 482 | 65 | 2028-02-28 | 2028-03-01 | 5796 |  | 1932
T1-L03-M | T1 | L03 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 265 | 270 | 433 | 438 | 168 | 2027-09-07 | 2027-09-11 | 12204.27 |  | 2440.854
T1-L03-P | T1 | L03 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 273 | 279 | 441 | 447 | 168 | 2027-09-16 | 2027-09-22 | 15067 |  | 2511.1667
T1-L03-S | T1 | L03 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 281 | 284 | 449 | 452 | 168 | 2027-09-25 | 2027-09-28 | 9048 |  | 3016
T1-L03-T | T1 | L03 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 401 | 407 | 466 | 472 | 65 | 2028-02-12 | 2028-02-18 | 24012 |  | 4002
T1-L03-A | T1 | L03 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 409 | 414 | 474 | 479 | 65 | 2028-02-22 | 2028-02-26 | 10245.56 |  | 2049.112
T1-L03-D | T1 | L03 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 414 | 417 | 479 | 482 | 65 | 2028-02-28 | 2028-03-01 | 5796 |  | 1932
T1-L04-M | T1 | L04 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 283 | 288 | 433 | 438 | 150 | 2027-09-28 | 2027-10-02 | 12204.27 |  | 2440.854
T1-L04-P | T1 | L04 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 291 | 297 | 441 | 447 | 150 | 2027-10-07 | 2027-10-13 | 15067 |  | 2511.1667
T1-L04-S | T1 | L04 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 299 | 302 | 449 | 452 | 150 | 2027-10-16 | 2027-10-19 | 9048 |  | 3016
T1-L04-T | T1 | L04 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 401 | 407 | 466 | 472 | 65 | 2028-02-12 | 2028-02-18 | 24012 |  | 4002
T1-L04-A | T1 | L04 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 409 | 414 | 474 | 479 | 65 | 2028-02-22 | 2028-02-26 | 10245.56 |  | 2049.112
T1-L04-D | T1 | L04 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 414 | 417 | 479 | 482 | 65 | 2028-02-28 | 2028-03-01 | 5796 |  | 1932
T1-L05-M | T1 | L05 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 301 | 306 | 433 | 438 | 132 | 2027-10-19 | 2027-10-23 | 12204.27 |  | 2440.854
T1-L05-P | T1 | L05 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 309 | 315 | 441 | 447 | 132 | 2027-10-28 | 2027-11-03 | 15067 |  | 2511.1667
T1-L05-S | T1 | L05 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 317 | 320 | 449 | 452 | 132 | 2027-11-06 | 2027-11-09 | 9048 |  | 3016
T1-L05-T | T1 | L05 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 401 | 407 | 466 | 472 | 65 | 2028-02-12 | 2028-02-18 | 24012 |  | 4002
T1-L05-A | T1 | L05 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 409 | 414 | 474 | 479 | 65 | 2028-02-22 | 2028-02-26 | 10245.56 |  | 2049.112
T1-L05-D | T1 | L05 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 414 | 417 | 479 | 482 | 65 | 2028-02-28 | 2028-03-01 | 5796 |  | 1932
T1-L06-M | T1 | L06 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 319 | 324 | 433 | 438 | 114 | 2027-11-09 | 2027-11-13 | 12204.27 |  | 2440.854
T1-L06-P | T1 | L06 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 327 | 333 | 441 | 447 | 114 | 2027-11-18 | 2027-11-24 | 15067 |  | 2511.1667
T1-L06-S | T1 | L06 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 335 | 338 | 449 | 452 | 114 | 2027-11-27 | 2027-11-30 | 9048 |  | 3016
T1-L06-T | T1 | L06 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 401 | 407 | 466 | 472 | 65 | 2028-02-12 | 2028-02-18 | 24012 |  | 4002
T1-L06-A | T1 | L06 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 409 | 414 | 474 | 479 | 65 | 2028-02-22 | 2028-02-26 | 10245.56 |  | 2049.112
T1-L06-D | T1 | L06 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 414 | 417 | 479 | 482 | 65 | 2028-02-28 | 2028-03-01 | 5796 |  | 1932
T1-L07-M | T1 | L07 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 337 | 342 | 433 | 438 | 96 | 2027-11-30 | 2027-12-04 | 12204.27 |  | 2440.854
T1-L07-P | T1 | L07 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 345 | 351 | 441 | 447 | 96 | 2027-12-09 | 2027-12-15 | 15067 |  | 2511.1667
T1-L07-S | T1 | L07 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 353 | 356 | 449 | 452 | 96 | 2027-12-18 | 2027-12-21 | 9048 |  | 3016
T1-L07-T | T1 | L07 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 401 | 407 | 466 | 472 | 65 | 2028-02-12 | 2028-02-18 | 24012 |  | 4002
T1-L07-A | T1 | L07 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 409 | 414 | 474 | 479 | 65 | 2028-02-22 | 2028-02-26 | 10245.56 |  | 2049.112
T1-L07-D | T1 | L07 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 414 | 417 | 479 | 482 | 65 | 2028-02-28 | 2028-03-01 | 5796 |  | 1932
T1-L08-M | T1 | L08 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 355 | 360 | 433 | 438 | 78 | 2027-12-21 | 2027-12-25 | 12204.27 |  | 2440.854
T1-L08-P | T1 | L08 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 363 | 369 | 441 | 447 | 78 | 2027-12-30 | 2028-01-05 | 15067 |  | 2511.1667
T1-L08-S | T1 | L08 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 371 | 374 | 449 | 452 | 78 | 2028-01-08 | 2028-01-11 | 9048 |  | 3016
T1-L08-T | T1 | L08 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 401 | 407 | 466 | 472 | 65 | 2028-02-12 | 2028-02-18 | 24012 |  | 4002
T1-L08-A | T1 | L08 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 409 | 414 | 474 | 479 | 65 | 2028-02-22 | 2028-02-26 | 10245.56 |  | 2049.112
T1-L08-D | T1 | L08 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 414 | 417 | 479 | 482 | 65 | 2028-02-28 | 2028-03-01 | 5796 |  | 1932
T1-L09-M | T1 | L09 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 373 | 378 | 433 | 438 | 60 | 2028-01-11 | 2028-01-15 | 12204.27 |  | 2440.854
T1-L09-P | T1 | L09 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 381 | 387 | 441 | 447 | 60 | 2028-01-20 | 2028-01-26 | 15067 |  | 2511.1667
T1-L09-S | T1 | L09 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 389 | 392 | 449 | 452 | 60 | 2028-01-29 | 2028-02-01 | 9048 |  | 3016
T1-L09-T | T1 | L09 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 406 | 412 | 466 | 472 | 60 | 2028-02-18 | 2028-02-24 | 24012 |  | 4002
T1-L09-A | T1 | L09 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 414 | 419 | 474 | 479 | 60 | 2028-02-28 | 2028-03-03 | 10245.56 |  | 2049.112
T1-L09-D | T1 | L09 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 419 | 422 | 479 | 482 | 60 | 2028-03-04 | 2028-03-07 | 5796 |  | 1932
T1-L10-M | T1 | L10 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 373 | 378 | 433 | 438 | 60 | 2028-01-11 | 2028-01-15 | 12204.27 |  | 2440.854
T1-L10-P | T1 | L10 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 381 | 387 | 441 | 447 | 60 | 2028-01-20 | 2028-01-26 | 15067 |  | 2511.1667
T1-L10-S | T1 | L10 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 389 | 392 | 449 | 452 | 60 | 2028-01-29 | 2028-02-01 | 9048 |  | 3016
T1-L10-T | T1 | L10 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 406 | 412 | 466 | 472 | 60 | 2028-02-18 | 2028-02-24 | 24012 |  | 4002
T1-L10-A | T1 | L10 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 414 | 419 | 474 | 479 | 60 | 2028-02-28 | 2028-03-03 | 10245.56 |  | 2049.112
T1-L10-D | T1 | L10 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 419 | 422 | 479 | 482 | 60 | 2028-03-04 | 2028-03-07 | 5796 |  | 1932
T1-L11-M | T1 | L11 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 373 | 378 | 433 | 438 | 60 | 2028-01-11 | 2028-01-15 | 12204.27 |  | 2440.854
T1-L11-P | T1 | L11 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 381 | 387 | 441 | 447 | 60 | 2028-01-20 | 2028-01-26 | 15067 |  | 2511.1667
T1-L11-S | T1 | L11 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 389 | 392 | 449 | 452 | 60 | 2028-01-29 | 2028-02-01 | 9048 |  | 3016
T1-L11-T | T1 | L11 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 406 | 412 | 466 | 472 | 60 | 2028-02-18 | 2028-02-24 | 24012 |  | 4002
T1-L11-A | T1 | L11 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 414 | 419 | 474 | 479 | 60 | 2028-02-28 | 2028-03-03 | 10245.56 |  | 2049.112
T1-L11-D | T1 | L11 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 419 | 422 | 479 | 482 | 60 | 2028-03-04 | 2028-03-07 | 5796 |  | 1932
T1-L12-M | T1 | L12 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 373 | 378 | 433 | 438 | 60 | 2028-01-11 | 2028-01-15 | 12204.27 |  | 2440.854
T1-L12-P | T1 | L12 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 381 | 387 | 441 | 447 | 60 | 2028-01-20 | 2028-01-26 | 15067 |  | 2511.1667
T1-L12-S | T1 | L12 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 389 | 392 | 449 | 452 | 60 | 2028-01-29 | 2028-02-01 | 9048 |  | 3016
T1-L12-T | T1 | L12 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 406 | 412 | 466 | 472 | 60 | 2028-02-18 | 2028-02-24 | 24012 |  | 4002
T1-L12-A | T1 | L12 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 414 | 419 | 474 | 479 | 60 | 2028-02-28 | 2028-03-03 | 10245.56 |  | 2049.112
T1-L12-D | T1 | L12 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 419 | 422 | 479 | 482 | 60 | 2028-03-04 | 2028-03-07 | 5796 |  | 1932
T2-L00-F | T2 | L00 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 146 | 152 | 194 | 200 | 48 | 2027-04-21 | 2027-04-27 | 29364.32 |  | 4894.0533
T2-L00-R | T2 | L00 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 152 | 157 | 200 | 205 | 48 | 2027-04-28 | 2027-05-03 | 25795.5172 |  | 5159.1034
T2-L00-C | T2 | L00 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 157 | 159 | 205 | 207 | 48 | 2027-05-04 | 2027-05-05 | 33527.397 |  | 16763.6985
T2-L00-H | T2 | L00 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 159 | 164 | 207 | 212 | 48 | 2027-05-06 | 2027-05-11 | 0 | 5 | 0
T2-L01-F | T2 | L01 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 164 | 170 | 212 | 218 | 48 | 2027-05-12 | 2027-05-18 | 29364.32 |  | 4894.0533
T2-L01-R | T2 | L01 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 170 | 175 | 218 | 223 | 48 | 2027-05-19 | 2027-05-24 | 25795.5172 |  | 5159.1034
T2-L01-C | T2 | L01 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 175 | 177 | 223 | 225 | 48 | 2027-05-25 | 2027-05-26 | 33527.397 |  | 16763.6985
T2-L01-H | T2 | L01 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 177 | 182 | 225 | 230 | 48 | 2027-05-27 | 2027-06-01 | 0 | 5 | 0
T2-L02-F | T2 | L02 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 182 | 188 | 230 | 236 | 48 | 2027-06-02 | 2027-06-08 | 29364.32 |  | 4894.0533
T2-L02-R | T2 | L02 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 188 | 193 | 236 | 241 | 48 | 2027-06-09 | 2027-06-14 | 25795.5172 |  | 5159.1034
T2-L02-C | T2 | L02 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 193 | 195 | 241 | 243 | 48 | 2027-06-15 | 2027-06-16 | 33527.397 |  | 16763.6985
T2-L02-H | T2 | L02 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 195 | 200 | 243 | 248 | 48 | 2027-06-17 | 2027-06-22 | 0 | 5 | 0
T2-L03-F | T2 | L03 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 200 | 206 | 248 | 254 | 48 | 2027-06-23 | 2027-06-29 | 29364.32 |  | 4894.0533
T2-L03-R | T2 | L03 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 206 | 211 | 254 | 259 | 48 | 2027-06-30 | 2027-07-05 | 25795.5172 |  | 5159.1034
T2-L03-C | T2 | L03 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 211 | 213 | 259 | 261 | 48 | 2027-07-06 | 2027-07-07 | 33527.397 |  | 16763.6985
T2-L03-H | T2 | L03 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 213 | 218 | 261 | 266 | 48 | 2027-07-08 | 2027-07-13 | 0 | 5 | 0
T2-L04-F | T2 | L04 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 218 | 224 | 266 | 272 | 48 | 2027-07-14 | 2027-07-20 | 29364.32 |  | 4894.0533
T2-L04-R | T2 | L04 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 224 | 229 | 272 | 277 | 48 | 2027-07-21 | 2027-07-26 | 25795.5172 |  | 5159.1034
T2-L04-C | T2 | L04 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 229 | 231 | 277 | 279 | 48 | 2027-07-27 | 2027-07-28 | 33527.397 |  | 16763.6985
T2-L04-H | T2 | L04 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 231 | 236 | 279 | 284 | 48 | 2027-07-29 | 2027-08-03 | 0 | 5 | 0
T2-L05-F | T2 | L05 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 236 | 242 | 284 | 290 | 48 | 2027-08-04 | 2027-08-10 | 29364.32 |  | 4894.0533
T2-L05-R | T2 | L05 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 242 | 247 | 290 | 295 | 48 | 2027-08-11 | 2027-08-16 | 25795.5172 |  | 5159.1034
T2-L05-C | T2 | L05 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 247 | 249 | 295 | 297 | 48 | 2027-08-17 | 2027-08-18 | 33527.397 |  | 16763.6985
T2-L05-H | T2 | L05 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 249 | 254 | 297 | 302 | 48 | 2027-08-19 | 2027-08-24 | 0 | 5 | 0
T2-L06-F | T2 | L06 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 254 | 260 | 302 | 308 | 48 | 2027-08-25 | 2027-08-31 | 29364.32 |  | 4894.0533
T2-L06-R | T2 | L06 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 260 | 265 | 308 | 313 | 48 | 2027-09-01 | 2027-09-06 | 25795.5172 |  | 5159.1034
T2-L06-C | T2 | L06 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 265 | 267 | 313 | 315 | 48 | 2027-09-07 | 2027-09-08 | 33527.397 |  | 16763.6985
T2-L06-H | T2 | L06 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 267 | 272 | 315 | 320 | 48 | 2027-09-09 | 2027-09-14 | 0 | 5 | 0
T2-L07-F | T2 | L07 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 272 | 278 | 320 | 326 | 48 | 2027-09-15 | 2027-09-21 | 29364.32 |  | 4894.0533
T2-L07-R | T2 | L07 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 278 | 283 | 326 | 331 | 48 | 2027-09-22 | 2027-09-27 | 25795.5172 |  | 5159.1034
T2-L07-C | T2 | L07 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 283 | 285 | 331 | 333 | 48 | 2027-09-28 | 2027-09-29 | 33527.397 |  | 16763.6985
T2-L07-H | T2 | L07 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 285 | 290 | 333 | 338 | 48 | 2027-09-30 | 2027-10-05 | 0 | 5 | 0
T2-L08-F | T2 | L08 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 290 | 296 | 338 | 344 | 48 | 2027-10-06 | 2027-10-12 | 29364.32 |  | 4894.0533
T2-L08-R | T2 | L08 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 296 | 301 | 344 | 349 | 48 | 2027-10-13 | 2027-10-18 | 25795.5172 |  | 5159.1034
T2-L08-C | T2 | L08 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 301 | 303 | 349 | 351 | 48 | 2027-10-19 | 2027-10-20 | 33527.397 |  | 16763.6985
T2-L08-H | T2 | L08 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 303 | 308 | 351 | 356 | 48 | 2027-10-21 | 2027-10-26 | 0 | 5 | 0
T2-L09-F | T2 | L09 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 308 | 314 | 356 | 362 | 48 | 2027-10-27 | 2027-11-02 | 29364.32 |  | 4894.0533
T2-L09-R | T2 | L09 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 314 | 319 | 362 | 367 | 48 | 2027-11-03 | 2027-11-08 | 25795.5172 |  | 5159.1034
T2-L09-C | T2 | L09 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 319 | 321 | 367 | 369 | 48 | 2027-11-09 | 2027-11-10 | 33527.397 |  | 16763.6985
T2-L09-H | T2 | L09 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 321 | 326 | 369 | 374 | 48 | 2027-11-11 | 2027-11-16 | 0 | 5 | 0
T2-L10-F | T2 | L10 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 326 | 332 | 374 | 380 | 48 | 2027-11-17 | 2027-11-23 | 29364.32 |  | 4894.0533
T2-L10-R | T2 | L10 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 332 | 337 | 380 | 385 | 48 | 2027-11-24 | 2027-11-29 | 25795.5172 |  | 5159.1034
T2-L10-C | T2 | L10 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 337 | 339 | 385 | 387 | 48 | 2027-11-30 | 2027-12-01 | 33527.397 |  | 16763.6985
T2-L10-H | T2 | L10 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 339 | 344 | 387 | 392 | 48 | 2027-12-02 | 2027-12-07 | 0 | 5 | 0
T2-L11-F | T2 | L11 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 344 | 350 | 392 | 398 | 48 | 2027-12-08 | 2027-12-14 | 29364.32 |  | 4894.0533
T2-L11-R | T2 | L11 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 350 | 355 | 398 | 403 | 48 | 2027-12-15 | 2027-12-20 | 25795.5172 |  | 5159.1034
T2-L11-C | T2 | L11 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 355 | 357 | 403 | 405 | 48 | 2027-12-21 | 2027-12-22 | 33527.397 |  | 16763.6985
T2-L11-H | T2 | L11 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 357 | 362 | 405 | 410 | 48 | 2027-12-23 | 2027-12-28 | 0 | 5 | 0
T2-L12-F | T2 | L12 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 362 | 368 | 410 | 416 | 48 | 2027-12-29 | 2028-01-04 | 29364.32 |  | 4894.0533
T2-L12-R | T2 | L12 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 368 | 373 | 416 | 421 | 48 | 2028-01-05 | 2028-01-10 | 25795.5172 |  | 5159.1034
T2-L12-C | T2 | L12 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 373 | 375 | 421 | 423 | 48 | 2028-01-11 | 2028-01-12 | 33527.397 |  | 16763.6985
T2-L12-H | T2 | L12 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 375 | 380 | 423 | 428 | 48 | 2028-01-13 | 2028-01-18 | 0 | 5 | 0
T2-RF | T2 | ROOF | Roof membrane and weatherproofing | Envelope | 2400 | m2 | 180 | 10 | 14 | 385 | 399 | 438 | 452 | 53 | 2028-01-25 | 2028-02-09 | 48000 |  | 3428.5714
T2-FA | T2 | ALL | Insulated facade installation | Envelope | 3234.816 | m2 | 150 | 16 | 22 | 318 | 340 | 430 | 452 | 112 | 2027-11-08 | 2027-12-02 | 271724.544 |  | 12351.1156
T2-GL | T2 | ALL | Glazing and frame installation | Envelope | 1257.984 | m2 | 90 | 12 | 14 | 399 | 413 | 452 | 466 | 53 | 2028-02-10 | 2028-02-25 | 276756.48 |  | 19768.32
T2-L00-M | T2 | L00 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 223 | 228 | 433 | 438 | 210 | 2027-07-20 | 2027-07-24 | 12204.27 |  | 2440.854
T2-L00-P | T2 | L00 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 231 | 237 | 441 | 447 | 210 | 2027-07-29 | 2027-08-04 | 15067 |  | 2511.1667
T2-L00-S | T2 | L00 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 239 | 242 | 449 | 452 | 210 | 2027-08-07 | 2027-08-10 | 9048 |  | 3016
T2-L00-T | T2 | L00 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 413 | 419 | 466 | 472 | 53 | 2028-02-26 | 2028-03-03 | 24012 |  | 4002
T2-L00-A | T2 | L00 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 421 | 426 | 474 | 479 | 53 | 2028-03-07 | 2028-03-11 | 10245.56 |  | 2049.112
T2-L00-D | T2 | L00 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 426 | 429 | 479 | 482 | 53 | 2028-03-13 | 2028-03-15 | 5796 |  | 1932
T2-L01-M | T2 | L01 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 241 | 246 | 433 | 438 | 192 | 2027-08-10 | 2027-08-14 | 12204.27 |  | 2440.854
T2-L01-P | T2 | L01 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 249 | 255 | 441 | 447 | 192 | 2027-08-19 | 2027-08-25 | 15067 |  | 2511.1667
T2-L01-S | T2 | L01 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 257 | 260 | 449 | 452 | 192 | 2027-08-28 | 2027-08-31 | 9048 |  | 3016
T2-L01-T | T2 | L01 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 413 | 419 | 466 | 472 | 53 | 2028-02-26 | 2028-03-03 | 24012 |  | 4002
T2-L01-A | T2 | L01 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 421 | 426 | 474 | 479 | 53 | 2028-03-07 | 2028-03-11 | 10245.56 |  | 2049.112
T2-L01-D | T2 | L01 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 426 | 429 | 479 | 482 | 53 | 2028-03-13 | 2028-03-15 | 5796 |  | 1932
T2-L02-M | T2 | L02 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 259 | 264 | 433 | 438 | 174 | 2027-08-31 | 2027-09-04 | 12204.27 |  | 2440.854
T2-L02-P | T2 | L02 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 267 | 273 | 441 | 447 | 174 | 2027-09-09 | 2027-09-15 | 15067 |  | 2511.1667
T2-L02-S | T2 | L02 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 275 | 278 | 449 | 452 | 174 | 2027-09-18 | 2027-09-21 | 9048 |  | 3016
T2-L02-T | T2 | L02 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 413 | 419 | 466 | 472 | 53 | 2028-02-26 | 2028-03-03 | 24012 |  | 4002
T2-L02-A | T2 | L02 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 421 | 426 | 474 | 479 | 53 | 2028-03-07 | 2028-03-11 | 10245.56 |  | 2049.112
T2-L02-D | T2 | L02 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 426 | 429 | 479 | 482 | 53 | 2028-03-13 | 2028-03-15 | 5796 |  | 1932
T2-L03-M | T2 | L03 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 277 | 282 | 433 | 438 | 156 | 2027-09-21 | 2027-09-25 | 12204.27 |  | 2440.854
T2-L03-P | T2 | L03 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 285 | 291 | 441 | 447 | 156 | 2027-09-30 | 2027-10-06 | 15067 |  | 2511.1667
T2-L03-S | T2 | L03 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 293 | 296 | 449 | 452 | 156 | 2027-10-09 | 2027-10-12 | 9048 |  | 3016
T2-L03-T | T2 | L03 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 413 | 419 | 466 | 472 | 53 | 2028-02-26 | 2028-03-03 | 24012 |  | 4002
T2-L03-A | T2 | L03 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 421 | 426 | 474 | 479 | 53 | 2028-03-07 | 2028-03-11 | 10245.56 |  | 2049.112
T2-L03-D | T2 | L03 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 426 | 429 | 479 | 482 | 53 | 2028-03-13 | 2028-03-15 | 5796 |  | 1932
T2-L04-M | T2 | L04 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 295 | 300 | 433 | 438 | 138 | 2027-10-12 | 2027-10-16 | 12204.27 |  | 2440.854
T2-L04-P | T2 | L04 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 303 | 309 | 441 | 447 | 138 | 2027-10-21 | 2027-10-27 | 15067 |  | 2511.1667
T2-L04-S | T2 | L04 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 311 | 314 | 449 | 452 | 138 | 2027-10-30 | 2027-11-02 | 9048 |  | 3016
T2-L04-T | T2 | L04 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 413 | 419 | 466 | 472 | 53 | 2028-02-26 | 2028-03-03 | 24012 |  | 4002
T2-L04-A | T2 | L04 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 421 | 426 | 474 | 479 | 53 | 2028-03-07 | 2028-03-11 | 10245.56 |  | 2049.112
T2-L04-D | T2 | L04 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 426 | 429 | 479 | 482 | 53 | 2028-03-13 | 2028-03-15 | 5796 |  | 1932
T2-L05-M | T2 | L05 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 313 | 318 | 433 | 438 | 120 | 2027-11-02 | 2027-11-06 | 12204.27 |  | 2440.854
T2-L05-P | T2 | L05 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 321 | 327 | 441 | 447 | 120 | 2027-11-11 | 2027-11-17 | 15067 |  | 2511.1667
T2-L05-S | T2 | L05 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 329 | 332 | 449 | 452 | 120 | 2027-11-20 | 2027-11-23 | 9048 |  | 3016
T2-L05-T | T2 | L05 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 413 | 419 | 466 | 472 | 53 | 2028-02-26 | 2028-03-03 | 24012 |  | 4002
T2-L05-A | T2 | L05 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 421 | 426 | 474 | 479 | 53 | 2028-03-07 | 2028-03-11 | 10245.56 |  | 2049.112
T2-L05-D | T2 | L05 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 426 | 429 | 479 | 482 | 53 | 2028-03-13 | 2028-03-15 | 5796 |  | 1932
T2-L06-M | T2 | L06 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 331 | 336 | 433 | 438 | 102 | 2027-11-23 | 2027-11-27 | 12204.27 |  | 2440.854
T2-L06-P | T2 | L06 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 339 | 345 | 441 | 447 | 102 | 2027-12-02 | 2027-12-08 | 15067 |  | 2511.1667
T2-L06-S | T2 | L06 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 347 | 350 | 449 | 452 | 102 | 2027-12-11 | 2027-12-14 | 9048 |  | 3016
T2-L06-T | T2 | L06 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 413 | 419 | 466 | 472 | 53 | 2028-02-26 | 2028-03-03 | 24012 |  | 4002
T2-L06-A | T2 | L06 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 421 | 426 | 474 | 479 | 53 | 2028-03-07 | 2028-03-11 | 10245.56 |  | 2049.112
T2-L06-D | T2 | L06 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 426 | 429 | 479 | 482 | 53 | 2028-03-13 | 2028-03-15 | 5796 |  | 1932
T2-L07-M | T2 | L07 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 349 | 354 | 433 | 438 | 84 | 2027-12-14 | 2027-12-18 | 12204.27 |  | 2440.854
T2-L07-P | T2 | L07 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 357 | 363 | 441 | 447 | 84 | 2027-12-23 | 2027-12-29 | 15067 |  | 2511.1667
T2-L07-S | T2 | L07 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 365 | 368 | 449 | 452 | 84 | 2028-01-01 | 2028-01-04 | 9048 |  | 3016
T2-L07-T | T2 | L07 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 413 | 419 | 466 | 472 | 53 | 2028-02-26 | 2028-03-03 | 24012 |  | 4002
T2-L07-A | T2 | L07 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 421 | 426 | 474 | 479 | 53 | 2028-03-07 | 2028-03-11 | 10245.56 |  | 2049.112
T2-L07-D | T2 | L07 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 426 | 429 | 479 | 482 | 53 | 2028-03-13 | 2028-03-15 | 5796 |  | 1932
T2-L08-M | T2 | L08 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 367 | 372 | 433 | 438 | 66 | 2028-01-04 | 2028-01-08 | 12204.27 |  | 2440.854
T2-L08-P | T2 | L08 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 375 | 381 | 441 | 447 | 66 | 2028-01-13 | 2028-01-19 | 15067 |  | 2511.1667
T2-L08-S | T2 | L08 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 383 | 386 | 449 | 452 | 66 | 2028-01-22 | 2028-01-25 | 9048 |  | 3016
T2-L08-T | T2 | L08 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 413 | 419 | 466 | 472 | 53 | 2028-02-26 | 2028-03-03 | 24012 |  | 4002
T2-L08-A | T2 | L08 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 421 | 426 | 474 | 479 | 53 | 2028-03-07 | 2028-03-11 | 10245.56 |  | 2049.112
T2-L08-D | T2 | L08 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 426 | 429 | 479 | 482 | 53 | 2028-03-13 | 2028-03-15 | 5796 |  | 1932
T2-L09-M | T2 | L09 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 385 | 390 | 433 | 438 | 48 | 2028-01-25 | 2028-01-29 | 12204.27 |  | 2440.854
T2-L09-P | T2 | L09 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 393 | 399 | 441 | 447 | 48 | 2028-02-03 | 2028-02-09 | 15067 |  | 2511.1667
T2-L09-S | T2 | L09 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 401 | 404 | 449 | 452 | 48 | 2028-02-12 | 2028-02-15 | 9048 |  | 3016
T2-L09-T | T2 | L09 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 418 | 424 | 466 | 472 | 48 | 2028-03-03 | 2028-03-09 | 24012 |  | 4002
T2-L09-A | T2 | L09 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 426 | 431 | 474 | 479 | 48 | 2028-03-13 | 2028-03-17 | 10245.56 |  | 2049.112
T2-L09-D | T2 | L09 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 431 | 434 | 479 | 482 | 48 | 2028-03-18 | 2028-03-21 | 5796 |  | 1932
T2-L10-M | T2 | L10 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 385 | 390 | 433 | 438 | 48 | 2028-01-25 | 2028-01-29 | 12204.27 |  | 2440.854
T2-L10-P | T2 | L10 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 393 | 399 | 441 | 447 | 48 | 2028-02-03 | 2028-02-09 | 15067 |  | 2511.1667
T2-L10-S | T2 | L10 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 401 | 404 | 449 | 452 | 48 | 2028-02-12 | 2028-02-15 | 9048 |  | 3016
T2-L10-T | T2 | L10 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 418 | 424 | 466 | 472 | 48 | 2028-03-03 | 2028-03-09 | 24012 |  | 4002
T2-L10-A | T2 | L10 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 426 | 431 | 474 | 479 | 48 | 2028-03-13 | 2028-03-17 | 10245.56 |  | 2049.112
T2-L10-D | T2 | L10 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 431 | 434 | 479 | 482 | 48 | 2028-03-18 | 2028-03-21 | 5796 |  | 1932
T2-L11-M | T2 | L11 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 385 | 390 | 433 | 438 | 48 | 2028-01-25 | 2028-01-29 | 12204.27 |  | 2440.854
T2-L11-P | T2 | L11 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 393 | 399 | 441 | 447 | 48 | 2028-02-03 | 2028-02-09 | 15067 |  | 2511.1667
T2-L11-S | T2 | L11 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 401 | 404 | 449 | 452 | 48 | 2028-02-12 | 2028-02-15 | 9048 |  | 3016
T2-L11-T | T2 | L11 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 418 | 424 | 466 | 472 | 48 | 2028-03-03 | 2028-03-09 | 24012 |  | 4002
T2-L11-A | T2 | L11 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 426 | 431 | 474 | 479 | 48 | 2028-03-13 | 2028-03-17 | 10245.56 |  | 2049.112
T2-L11-D | T2 | L11 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 431 | 434 | 479 | 482 | 48 | 2028-03-18 | 2028-03-21 | 5796 |  | 1932
T2-L12-M | T2 | L12 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 385 | 390 | 433 | 438 | 48 | 2028-01-25 | 2028-01-29 | 12204.27 |  | 2440.854
T2-L12-P | T2 | L12 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 393 | 399 | 441 | 447 | 48 | 2028-02-03 | 2028-02-09 | 15067 |  | 2511.1667
T2-L12-S | T2 | L12 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 401 | 404 | 449 | 452 | 48 | 2028-02-12 | 2028-02-15 | 9048 |  | 3016
T2-L12-T | T2 | L12 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 418 | 424 | 466 | 472 | 48 | 2028-03-03 | 2028-03-09 | 24012 |  | 4002
T2-L12-A | T2 | L12 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 426 | 431 | 474 | 479 | 48 | 2028-03-13 | 2028-03-17 | 10245.56 |  | 2049.112
T2-L12-D | T2 | L12 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 431 | 434 | 479 | 482 | 48 | 2028-03-18 | 2028-03-21 | 5796 |  | 1932
T3-L00-F | T3 | L00 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 158 | 164 | 194 | 200 | 36 | 2027-05-05 | 2027-05-11 | 29364.32 |  | 4894.0533
T3-L00-R | T3 | L00 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 164 | 169 | 200 | 205 | 36 | 2027-05-12 | 2027-05-17 | 25795.5172 |  | 5159.1034
T3-L00-C | T3 | L00 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 169 | 171 | 205 | 207 | 36 | 2027-05-18 | 2027-05-19 | 33527.397 |  | 16763.6985
T3-L00-H | T3 | L00 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 171 | 176 | 207 | 212 | 36 | 2027-05-20 | 2027-05-25 | 0 | 5 | 0
T3-L01-F | T3 | L01 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 176 | 182 | 212 | 218 | 36 | 2027-05-26 | 2027-06-01 | 29364.32 |  | 4894.0533
T3-L01-R | T3 | L01 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 182 | 187 | 218 | 223 | 36 | 2027-06-02 | 2027-06-07 | 25795.5172 |  | 5159.1034
T3-L01-C | T3 | L01 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 187 | 189 | 223 | 225 | 36 | 2027-06-08 | 2027-06-09 | 33527.397 |  | 16763.6985
T3-L01-H | T3 | L01 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 189 | 194 | 225 | 230 | 36 | 2027-06-10 | 2027-06-15 | 0 | 5 | 0
T3-L02-F | T3 | L02 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 194 | 200 | 230 | 236 | 36 | 2027-06-16 | 2027-06-22 | 29364.32 |  | 4894.0533
T3-L02-R | T3 | L02 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 200 | 205 | 236 | 241 | 36 | 2027-06-23 | 2027-06-28 | 25795.5172 |  | 5159.1034
T3-L02-C | T3 | L02 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 205 | 207 | 241 | 243 | 36 | 2027-06-29 | 2027-06-30 | 33527.397 |  | 16763.6985
T3-L02-H | T3 | L02 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 207 | 212 | 243 | 248 | 36 | 2027-07-01 | 2027-07-06 | 0 | 5 | 0
T3-L03-F | T3 | L03 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 212 | 218 | 248 | 254 | 36 | 2027-07-07 | 2027-07-13 | 29364.32 |  | 4894.0533
T3-L03-R | T3 | L03 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 218 | 223 | 254 | 259 | 36 | 2027-07-14 | 2027-07-19 | 25795.5172 |  | 5159.1034
T3-L03-C | T3 | L03 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 223 | 225 | 259 | 261 | 36 | 2027-07-20 | 2027-07-21 | 33527.397 |  | 16763.6985
T3-L03-H | T3 | L03 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 225 | 230 | 261 | 266 | 36 | 2027-07-22 | 2027-07-27 | 0 | 5 | 0
T3-L04-F | T3 | L04 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 230 | 236 | 266 | 272 | 36 | 2027-07-28 | 2027-08-03 | 29364.32 |  | 4894.0533
T3-L04-R | T3 | L04 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 236 | 241 | 272 | 277 | 36 | 2027-08-04 | 2027-08-09 | 25795.5172 |  | 5159.1034
T3-L04-C | T3 | L04 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 241 | 243 | 277 | 279 | 36 | 2027-08-10 | 2027-08-11 | 33527.397 |  | 16763.6985
T3-L04-H | T3 | L04 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 243 | 248 | 279 | 284 | 36 | 2027-08-12 | 2027-08-17 | 0 | 5 | 0
T3-L05-F | T3 | L05 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 248 | 254 | 284 | 290 | 36 | 2027-08-18 | 2027-08-24 | 29364.32 |  | 4894.0533
T3-L05-R | T3 | L05 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 254 | 259 | 290 | 295 | 36 | 2027-08-25 | 2027-08-30 | 25795.5172 |  | 5159.1034
T3-L05-C | T3 | L05 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 259 | 261 | 295 | 297 | 36 | 2027-08-31 | 2027-09-01 | 33527.397 |  | 16763.6985
T3-L05-H | T3 | L05 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 261 | 266 | 297 | 302 | 36 | 2027-09-02 | 2027-09-07 | 0 | 5 | 0
T3-L06-F | T3 | L06 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 266 | 272 | 302 | 308 | 36 | 2027-09-08 | 2027-09-14 | 29364.32 |  | 4894.0533
T3-L06-R | T3 | L06 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 272 | 277 | 308 | 313 | 36 | 2027-09-15 | 2027-09-20 | 25795.5172 |  | 5159.1034
T3-L06-C | T3 | L06 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 277 | 279 | 313 | 315 | 36 | 2027-09-21 | 2027-09-22 | 33527.397 |  | 16763.6985
T3-L06-H | T3 | L06 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 279 | 284 | 315 | 320 | 36 | 2027-09-23 | 2027-09-28 | 0 | 5 | 0
T3-L07-F | T3 | L07 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 284 | 290 | 320 | 326 | 36 | 2027-09-29 | 2027-10-05 | 29364.32 |  | 4894.0533
T3-L07-R | T3 | L07 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 290 | 295 | 326 | 331 | 36 | 2027-10-06 | 2027-10-11 | 25795.5172 |  | 5159.1034
T3-L07-C | T3 | L07 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 295 | 297 | 331 | 333 | 36 | 2027-10-12 | 2027-10-13 | 33527.397 |  | 16763.6985
T3-L07-H | T3 | L07 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 297 | 302 | 333 | 338 | 36 | 2027-10-14 | 2027-10-19 | 0 | 5 | 0
T3-L08-F | T3 | L08 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 302 | 308 | 338 | 344 | 36 | 2027-10-20 | 2027-10-26 | 29364.32 |  | 4894.0533
T3-L08-R | T3 | L08 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 308 | 313 | 344 | 349 | 36 | 2027-10-27 | 2027-11-01 | 25795.5172 |  | 5159.1034
T3-L08-C | T3 | L08 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 313 | 315 | 349 | 351 | 36 | 2027-11-02 | 2027-11-03 | 33527.397 |  | 16763.6985
T3-L08-H | T3 | L08 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 315 | 320 | 351 | 356 | 36 | 2027-11-04 | 2027-11-09 | 0 | 5 | 0
T3-L09-F | T3 | L09 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 320 | 326 | 356 | 362 | 36 | 2027-11-10 | 2027-11-16 | 29364.32 |  | 4894.0533
T3-L09-R | T3 | L09 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 326 | 331 | 362 | 367 | 36 | 2027-11-17 | 2027-11-22 | 25795.5172 |  | 5159.1034
T3-L09-C | T3 | L09 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 331 | 333 | 367 | 369 | 36 | 2027-11-23 | 2027-11-24 | 33527.397 |  | 16763.6985
T3-L09-H | T3 | L09 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 333 | 338 | 369 | 374 | 36 | 2027-11-25 | 2027-11-30 | 0 | 5 | 0
T3-L10-F | T3 | L10 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 338 | 344 | 374 | 380 | 36 | 2027-12-01 | 2027-12-07 | 29364.32 |  | 4894.0533
T3-L10-R | T3 | L10 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 344 | 349 | 380 | 385 | 36 | 2027-12-08 | 2027-12-13 | 25795.5172 |  | 5159.1034
T3-L10-C | T3 | L10 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 349 | 351 | 385 | 387 | 36 | 2027-12-14 | 2027-12-15 | 33527.397 |  | 16763.6985
T3-L10-H | T3 | L10 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 351 | 356 | 387 | 392 | 36 | 2027-12-16 | 2027-12-21 | 0 | 5 | 0
T3-L11-F | T3 | L11 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 356 | 362 | 392 | 398 | 36 | 2027-12-22 | 2027-12-28 | 29364.32 |  | 4894.0533
T3-L11-R | T3 | L11 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 362 | 367 | 398 | 403 | 36 | 2027-12-29 | 2028-01-03 | 25795.5172 |  | 5159.1034
T3-L11-C | T3 | L11 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 367 | 369 | 403 | 405 | 36 | 2028-01-04 | 2028-01-05 | 33527.397 |  | 16763.6985
T3-L11-H | T3 | L11 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 369 | 374 | 405 | 410 | 36 | 2028-01-06 | 2028-01-11 | 0 | 5 | 0
T3-L12-F | T3 | L12 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 374 | 380 | 410 | 416 | 36 | 2028-01-12 | 2028-01-18 | 29364.32 |  | 4894.0533
T3-L12-R | T3 | L12 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 380 | 385 | 416 | 421 | 36 | 2028-01-19 | 2028-01-24 | 25795.5172 |  | 5159.1034
T3-L12-C | T3 | L12 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 385 | 387 | 421 | 423 | 36 | 2028-01-25 | 2028-01-26 | 33527.397 |  | 16763.6985
T3-L12-H | T3 | L12 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 387 | 392 | 423 | 428 | 36 | 2028-01-27 | 2028-02-01 | 0 | 5 | 0
T3-RF | T3 | ROOF | Roof membrane and weatherproofing | Envelope | 2400 | m2 | 180 | 10 | 14 | 397 | 411 | 438 | 452 | 41 | 2028-02-08 | 2028-02-23 | 48000 |  | 3428.5714
T3-FA | T3 | ALL | Insulated facade installation | Envelope | 3234.816 | m2 | 150 | 16 | 22 | 330 | 352 | 430 | 452 | 100 | 2027-11-22 | 2027-12-16 | 271724.544 |  | 12351.1156
T3-GL | T3 | ALL | Glazing and frame installation | Envelope | 1257.984 | m2 | 90 | 12 | 14 | 411 | 425 | 452 | 466 | 41 | 2028-02-24 | 2028-03-10 | 276756.48 |  | 19768.32
T3-L00-M | T3 | L00 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 235 | 240 | 433 | 438 | 198 | 2027-08-03 | 2027-08-07 | 12204.27 |  | 2440.854
T3-L00-P | T3 | L00 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 243 | 249 | 441 | 447 | 198 | 2027-08-12 | 2027-08-18 | 15067 |  | 2511.1667
T3-L00-S | T3 | L00 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 251 | 254 | 449 | 452 | 198 | 2027-08-21 | 2027-08-24 | 9048 |  | 3016
T3-L00-T | T3 | L00 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 425 | 431 | 466 | 472 | 41 | 2028-03-11 | 2028-03-17 | 24012 |  | 4002
T3-L00-A | T3 | L00 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 433 | 438 | 474 | 479 | 41 | 2028-03-21 | 2028-03-25 | 10245.56 |  | 2049.112
T3-L00-D | T3 | L00 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 438 | 441 | 479 | 482 | 41 | 2028-03-27 | 2028-03-29 | 5796 |  | 1932
T3-L01-M | T3 | L01 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 253 | 258 | 433 | 438 | 180 | 2027-08-24 | 2027-08-28 | 12204.27 |  | 2440.854
T3-L01-P | T3 | L01 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 261 | 267 | 441 | 447 | 180 | 2027-09-02 | 2027-09-08 | 15067 |  | 2511.1667
T3-L01-S | T3 | L01 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 269 | 272 | 449 | 452 | 180 | 2027-09-11 | 2027-09-14 | 9048 |  | 3016
T3-L01-T | T3 | L01 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 425 | 431 | 466 | 472 | 41 | 2028-03-11 | 2028-03-17 | 24012 |  | 4002
T3-L01-A | T3 | L01 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 433 | 438 | 474 | 479 | 41 | 2028-03-21 | 2028-03-25 | 10245.56 |  | 2049.112
T3-L01-D | T3 | L01 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 438 | 441 | 479 | 482 | 41 | 2028-03-27 | 2028-03-29 | 5796 |  | 1932
T3-L02-M | T3 | L02 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 271 | 276 | 433 | 438 | 162 | 2027-09-14 | 2027-09-18 | 12204.27 |  | 2440.854
T3-L02-P | T3 | L02 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 279 | 285 | 441 | 447 | 162 | 2027-09-23 | 2027-09-29 | 15067 |  | 2511.1667
T3-L02-S | T3 | L02 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 287 | 290 | 449 | 452 | 162 | 2027-10-02 | 2027-10-05 | 9048 |  | 3016
T3-L02-T | T3 | L02 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 425 | 431 | 466 | 472 | 41 | 2028-03-11 | 2028-03-17 | 24012 |  | 4002
T3-L02-A | T3 | L02 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 433 | 438 | 474 | 479 | 41 | 2028-03-21 | 2028-03-25 | 10245.56 |  | 2049.112
T3-L02-D | T3 | L02 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 438 | 441 | 479 | 482 | 41 | 2028-03-27 | 2028-03-29 | 5796 |  | 1932
T3-L03-M | T3 | L03 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 289 | 294 | 433 | 438 | 144 | 2027-10-05 | 2027-10-09 | 12204.27 |  | 2440.854
T3-L03-P | T3 | L03 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 297 | 303 | 441 | 447 | 144 | 2027-10-14 | 2027-10-20 | 15067 |  | 2511.1667
T3-L03-S | T3 | L03 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 305 | 308 | 449 | 452 | 144 | 2027-10-23 | 2027-10-26 | 9048 |  | 3016
T3-L03-T | T3 | L03 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 425 | 431 | 466 | 472 | 41 | 2028-03-11 | 2028-03-17 | 24012 |  | 4002
T3-L03-A | T3 | L03 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 433 | 438 | 474 | 479 | 41 | 2028-03-21 | 2028-03-25 | 10245.56 |  | 2049.112
T3-L03-D | T3 | L03 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 438 | 441 | 479 | 482 | 41 | 2028-03-27 | 2028-03-29 | 5796 |  | 1932
T3-L04-M | T3 | L04 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 307 | 312 | 433 | 438 | 126 | 2027-10-26 | 2027-10-30 | 12204.27 |  | 2440.854
T3-L04-P | T3 | L04 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 315 | 321 | 441 | 447 | 126 | 2027-11-04 | 2027-11-10 | 15067 |  | 2511.1667
T3-L04-S | T3 | L04 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 323 | 326 | 449 | 452 | 126 | 2027-11-13 | 2027-11-16 | 9048 |  | 3016
T3-L04-T | T3 | L04 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 425 | 431 | 466 | 472 | 41 | 2028-03-11 | 2028-03-17 | 24012 |  | 4002
T3-L04-A | T3 | L04 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 433 | 438 | 474 | 479 | 41 | 2028-03-21 | 2028-03-25 | 10245.56 |  | 2049.112
T3-L04-D | T3 | L04 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 438 | 441 | 479 | 482 | 41 | 2028-03-27 | 2028-03-29 | 5796 |  | 1932
T3-L05-M | T3 | L05 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 325 | 330 | 433 | 438 | 108 | 2027-11-16 | 2027-11-20 | 12204.27 |  | 2440.854
T3-L05-P | T3 | L05 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 333 | 339 | 441 | 447 | 108 | 2027-11-25 | 2027-12-01 | 15067 |  | 2511.1667
T3-L05-S | T3 | L05 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 341 | 344 | 449 | 452 | 108 | 2027-12-04 | 2027-12-07 | 9048 |  | 3016
T3-L05-T | T3 | L05 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 425 | 431 | 466 | 472 | 41 | 2028-03-11 | 2028-03-17 | 24012 |  | 4002
T3-L05-A | T3 | L05 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 433 | 438 | 474 | 479 | 41 | 2028-03-21 | 2028-03-25 | 10245.56 |  | 2049.112
T3-L05-D | T3 | L05 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 438 | 441 | 479 | 482 | 41 | 2028-03-27 | 2028-03-29 | 5796 |  | 1932
T3-L06-M | T3 | L06 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 343 | 348 | 433 | 438 | 90 | 2027-12-07 | 2027-12-11 | 12204.27 |  | 2440.854
T3-L06-P | T3 | L06 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 351 | 357 | 441 | 447 | 90 | 2027-12-16 | 2027-12-22 | 15067 |  | 2511.1667
T3-L06-S | T3 | L06 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 359 | 362 | 449 | 452 | 90 | 2027-12-25 | 2027-12-28 | 9048 |  | 3016
T3-L06-T | T3 | L06 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 425 | 431 | 466 | 472 | 41 | 2028-03-11 | 2028-03-17 | 24012 |  | 4002
T3-L06-A | T3 | L06 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 433 | 438 | 474 | 479 | 41 | 2028-03-21 | 2028-03-25 | 10245.56 |  | 2049.112
T3-L06-D | T3 | L06 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 438 | 441 | 479 | 482 | 41 | 2028-03-27 | 2028-03-29 | 5796 |  | 1932
T3-L07-M | T3 | L07 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 361 | 366 | 433 | 438 | 72 | 2027-12-28 | 2028-01-01 | 12204.27 |  | 2440.854
T3-L07-P | T3 | L07 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 369 | 375 | 441 | 447 | 72 | 2028-01-06 | 2028-01-12 | 15067 |  | 2511.1667
T3-L07-S | T3 | L07 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 377 | 380 | 449 | 452 | 72 | 2028-01-15 | 2028-01-18 | 9048 |  | 3016
T3-L07-T | T3 | L07 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 425 | 431 | 466 | 472 | 41 | 2028-03-11 | 2028-03-17 | 24012 |  | 4002
T3-L07-A | T3 | L07 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 433 | 438 | 474 | 479 | 41 | 2028-03-21 | 2028-03-25 | 10245.56 |  | 2049.112
T3-L07-D | T3 | L07 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 438 | 441 | 479 | 482 | 41 | 2028-03-27 | 2028-03-29 | 5796 |  | 1932
T3-L08-M | T3 | L08 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 379 | 384 | 433 | 438 | 54 | 2028-01-18 | 2028-01-22 | 12204.27 |  | 2440.854
T3-L08-P | T3 | L08 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 387 | 393 | 441 | 447 | 54 | 2028-01-27 | 2028-02-02 | 15067 |  | 2511.1667
T3-L08-S | T3 | L08 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 395 | 398 | 449 | 452 | 54 | 2028-02-05 | 2028-02-08 | 9048 |  | 3016
T3-L08-T | T3 | L08 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 425 | 431 | 466 | 472 | 41 | 2028-03-11 | 2028-03-17 | 24012 |  | 4002
T3-L08-A | T3 | L08 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 433 | 438 | 474 | 479 | 41 | 2028-03-21 | 2028-03-25 | 10245.56 |  | 2049.112
T3-L08-D | T3 | L08 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 438 | 441 | 479 | 482 | 41 | 2028-03-27 | 2028-03-29 | 5796 |  | 1932
T3-L09-M | T3 | L09 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 397 | 402 | 433 | 438 | 36 | 2028-02-08 | 2028-02-12 | 12204.27 |  | 2440.854
T3-L09-P | T3 | L09 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 405 | 411 | 441 | 447 | 36 | 2028-02-17 | 2028-02-23 | 15067 |  | 2511.1667
T3-L09-S | T3 | L09 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 413 | 416 | 449 | 452 | 36 | 2028-02-26 | 2028-02-29 | 9048 |  | 3016
T3-L09-T | T3 | L09 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 430 | 436 | 466 | 472 | 36 | 2028-03-17 | 2028-03-23 | 24012 |  | 4002
T3-L09-A | T3 | L09 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 438 | 443 | 474 | 479 | 36 | 2028-03-27 | 2028-03-31 | 10245.56 |  | 2049.112
T3-L09-D | T3 | L09 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 443 | 446 | 479 | 482 | 36 | 2028-04-01 | 2028-04-04 | 5796 |  | 1932
T3-L10-M | T3 | L10 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 397 | 402 | 433 | 438 | 36 | 2028-02-08 | 2028-02-12 | 12204.27 |  | 2440.854
T3-L10-P | T3 | L10 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 405 | 411 | 441 | 447 | 36 | 2028-02-17 | 2028-02-23 | 15067 |  | 2511.1667
T3-L10-S | T3 | L10 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 413 | 416 | 449 | 452 | 36 | 2028-02-26 | 2028-02-29 | 9048 |  | 3016
T3-L10-T | T3 | L10 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 430 | 436 | 466 | 472 | 36 | 2028-03-17 | 2028-03-23 | 24012 |  | 4002
T3-L10-A | T3 | L10 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 438 | 443 | 474 | 479 | 36 | 2028-03-27 | 2028-03-31 | 10245.56 |  | 2049.112
T3-L10-D | T3 | L10 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 443 | 446 | 479 | 482 | 36 | 2028-04-01 | 2028-04-04 | 5796 |  | 1932
T3-L11-M | T3 | L11 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 397 | 402 | 433 | 438 | 36 | 2028-02-08 | 2028-02-12 | 12204.27 |  | 2440.854
T3-L11-P | T3 | L11 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 405 | 411 | 441 | 447 | 36 | 2028-02-17 | 2028-02-23 | 15067 |  | 2511.1667
T3-L11-S | T3 | L11 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 413 | 416 | 449 | 452 | 36 | 2028-02-26 | 2028-02-29 | 9048 |  | 3016
T3-L11-T | T3 | L11 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 430 | 436 | 466 | 472 | 36 | 2028-03-17 | 2028-03-23 | 24012 |  | 4002
T3-L11-A | T3 | L11 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 438 | 443 | 474 | 479 | 36 | 2028-03-27 | 2028-03-31 | 10245.56 |  | 2049.112
T3-L11-D | T3 | L11 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 443 | 446 | 479 | 482 | 36 | 2028-04-01 | 2028-04-04 | 5796 |  | 1932
T3-L12-M | T3 | L12 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 397 | 402 | 433 | 438 | 36 | 2028-02-08 | 2028-02-12 | 12204.27 |  | 2440.854
T3-L12-P | T3 | L12 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 405 | 411 | 441 | 447 | 36 | 2028-02-17 | 2028-02-23 | 15067 |  | 2511.1667
T3-L12-S | T3 | L12 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 413 | 416 | 449 | 452 | 36 | 2028-02-26 | 2028-02-29 | 9048 |  | 3016
T3-L12-T | T3 | L12 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 430 | 436 | 466 | 472 | 36 | 2028-03-17 | 2028-03-23 | 24012 |  | 4002
T3-L12-A | T3 | L12 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 438 | 443 | 474 | 479 | 36 | 2028-03-27 | 2028-03-31 | 10245.56 |  | 2049.112
T3-L12-D | T3 | L12 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 443 | 446 | 479 | 482 | 36 | 2028-04-01 | 2028-04-04 | 5796 |  | 1932
T4-L00-F | T4 | L00 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 170 | 176 | 194 | 200 | 24 | 2027-05-19 | 2027-05-25 | 29364.32 |  | 4894.0533
T4-L00-R | T4 | L00 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 176 | 181 | 200 | 205 | 24 | 2027-05-26 | 2027-05-31 | 25795.5172 |  | 5159.1034
T4-L00-C | T4 | L00 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 181 | 183 | 205 | 207 | 24 | 2027-06-01 | 2027-06-02 | 33527.397 |  | 16763.6985
T4-L00-H | T4 | L00 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 183 | 188 | 207 | 212 | 24 | 2027-06-03 | 2027-06-08 | 0 | 5 | 0
T4-L01-F | T4 | L01 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 188 | 194 | 212 | 218 | 24 | 2027-06-09 | 2027-06-15 | 29364.32 |  | 4894.0533
T4-L01-R | T4 | L01 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 194 | 199 | 218 | 223 | 24 | 2027-06-16 | 2027-06-21 | 25795.5172 |  | 5159.1034
T4-L01-C | T4 | L01 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 199 | 201 | 223 | 225 | 24 | 2027-06-22 | 2027-06-23 | 33527.397 |  | 16763.6985
T4-L01-H | T4 | L01 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 201 | 206 | 225 | 230 | 24 | 2027-06-24 | 2027-06-29 | 0 | 5 | 0
T4-L02-F | T4 | L02 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 206 | 212 | 230 | 236 | 24 | 2027-06-30 | 2027-07-06 | 29364.32 |  | 4894.0533
T4-L02-R | T4 | L02 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 212 | 217 | 236 | 241 | 24 | 2027-07-07 | 2027-07-12 | 25795.5172 |  | 5159.1034
T4-L02-C | T4 | L02 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 217 | 219 | 241 | 243 | 24 | 2027-07-13 | 2027-07-14 | 33527.397 |  | 16763.6985
T4-L02-H | T4 | L02 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 219 | 224 | 243 | 248 | 24 | 2027-07-15 | 2027-07-20 | 0 | 5 | 0
T4-L03-F | T4 | L03 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 224 | 230 | 248 | 254 | 24 | 2027-07-21 | 2027-07-27 | 29364.32 |  | 4894.0533
T4-L03-R | T4 | L03 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 230 | 235 | 254 | 259 | 24 | 2027-07-28 | 2027-08-02 | 25795.5172 |  | 5159.1034
T4-L03-C | T4 | L03 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 235 | 237 | 259 | 261 | 24 | 2027-08-03 | 2027-08-04 | 33527.397 |  | 16763.6985
T4-L03-H | T4 | L03 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 237 | 242 | 261 | 266 | 24 | 2027-08-05 | 2027-08-10 | 0 | 5 | 0
T4-L04-F | T4 | L04 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 242 | 248 | 266 | 272 | 24 | 2027-08-11 | 2027-08-17 | 29364.32 |  | 4894.0533
T4-L04-R | T4 | L04 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 248 | 253 | 272 | 277 | 24 | 2027-08-18 | 2027-08-23 | 25795.5172 |  | 5159.1034
T4-L04-C | T4 | L04 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 253 | 255 | 277 | 279 | 24 | 2027-08-24 | 2027-08-25 | 33527.397 |  | 16763.6985
T4-L04-H | T4 | L04 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 255 | 260 | 279 | 284 | 24 | 2027-08-26 | 2027-08-31 | 0 | 5 | 0
T4-L05-F | T4 | L05 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 260 | 266 | 284 | 290 | 24 | 2027-09-01 | 2027-09-07 | 29364.32 |  | 4894.0533
T4-L05-R | T4 | L05 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 266 | 271 | 290 | 295 | 24 | 2027-09-08 | 2027-09-13 | 25795.5172 |  | 5159.1034
T4-L05-C | T4 | L05 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 271 | 273 | 295 | 297 | 24 | 2027-09-14 | 2027-09-15 | 33527.397 |  | 16763.6985
T4-L05-H | T4 | L05 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 273 | 278 | 297 | 302 | 24 | 2027-09-16 | 2027-09-21 | 0 | 5 | 0
T4-L06-F | T4 | L06 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 278 | 284 | 302 | 308 | 24 | 2027-09-22 | 2027-09-28 | 29364.32 |  | 4894.0533
T4-L06-R | T4 | L06 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 284 | 289 | 308 | 313 | 24 | 2027-09-29 | 2027-10-04 | 25795.5172 |  | 5159.1034
T4-L06-C | T4 | L06 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 289 | 291 | 313 | 315 | 24 | 2027-10-05 | 2027-10-06 | 33527.397 |  | 16763.6985
T4-L06-H | T4 | L06 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 291 | 296 | 315 | 320 | 24 | 2027-10-07 | 2027-10-12 | 0 | 5 | 0
T4-L07-F | T4 | L07 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 296 | 302 | 320 | 326 | 24 | 2027-10-13 | 2027-10-19 | 29364.32 |  | 4894.0533
T4-L07-R | T4 | L07 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 302 | 307 | 326 | 331 | 24 | 2027-10-20 | 2027-10-25 | 25795.5172 |  | 5159.1034
T4-L07-C | T4 | L07 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 307 | 309 | 331 | 333 | 24 | 2027-10-26 | 2027-10-27 | 33527.397 |  | 16763.6985
T4-L07-H | T4 | L07 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 309 | 314 | 333 | 338 | 24 | 2027-10-28 | 2027-11-02 | 0 | 5 | 0
T4-L08-F | T4 | L08 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 314 | 320 | 338 | 344 | 24 | 2027-11-03 | 2027-11-09 | 29364.32 |  | 4894.0533
T4-L08-R | T4 | L08 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 320 | 325 | 344 | 349 | 24 | 2027-11-10 | 2027-11-15 | 25795.5172 |  | 5159.1034
T4-L08-C | T4 | L08 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 325 | 327 | 349 | 351 | 24 | 2027-11-16 | 2027-11-17 | 33527.397 |  | 16763.6985
T4-L08-H | T4 | L08 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 327 | 332 | 351 | 356 | 24 | 2027-11-18 | 2027-11-23 | 0 | 5 | 0
T4-L09-F | T4 | L09 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 332 | 338 | 356 | 362 | 24 | 2027-11-24 | 2027-11-30 | 29364.32 |  | 4894.0533
T4-L09-R | T4 | L09 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 338 | 343 | 362 | 367 | 24 | 2027-12-01 | 2027-12-06 | 25795.5172 |  | 5159.1034
T4-L09-C | T4 | L09 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 343 | 345 | 367 | 369 | 24 | 2027-12-07 | 2027-12-08 | 33527.397 |  | 16763.6985
T4-L09-H | T4 | L09 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 345 | 350 | 369 | 374 | 24 | 2027-12-09 | 2027-12-14 | 0 | 5 | 0
T4-L10-F | T4 | L10 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 350 | 356 | 374 | 380 | 24 | 2027-12-15 | 2027-12-21 | 29364.32 |  | 4894.0533
T4-L10-R | T4 | L10 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 356 | 361 | 380 | 385 | 24 | 2027-12-22 | 2027-12-27 | 25795.5172 |  | 5159.1034
T4-L10-C | T4 | L10 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 361 | 363 | 385 | 387 | 24 | 2027-12-28 | 2027-12-29 | 33527.397 |  | 16763.6985
T4-L10-H | T4 | L10 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 363 | 368 | 387 | 392 | 24 | 2027-12-30 | 2028-01-04 | 0 | 5 | 0
T4-L11-F | T4 | L11 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 368 | 374 | 392 | 398 | 24 | 2028-01-05 | 2028-01-11 | 29364.32 |  | 4894.0533
T4-L11-R | T4 | L11 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 374 | 379 | 398 | 403 | 24 | 2028-01-12 | 2028-01-17 | 25795.5172 |  | 5159.1034
T4-L11-C | T4 | L11 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 379 | 381 | 403 | 405 | 24 | 2028-01-18 | 2028-01-19 | 33527.397 |  | 16763.6985
T4-L11-H | T4 | L11 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 381 | 386 | 405 | 410 | 24 | 2028-01-20 | 2028-01-25 | 0 | 5 | 0
T4-L12-F | T4 | L12 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 386 | 392 | 410 | 416 | 24 | 2028-01-26 | 2028-02-01 | 29364.32 |  | 4894.0533
T4-L12-R | T4 | L12 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 392 | 397 | 416 | 421 | 24 | 2028-02-02 | 2028-02-07 | 25795.5172 |  | 5159.1034
T4-L12-C | T4 | L12 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 397 | 399 | 421 | 423 | 24 | 2028-02-08 | 2028-02-09 | 33527.397 |  | 16763.6985
T4-L12-H | T4 | L12 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 399 | 404 | 423 | 428 | 24 | 2028-02-10 | 2028-02-15 | 0 | 5 | 0
T4-RF | T4 | ROOF | Roof membrane and weatherproofing | Envelope | 2400 | m2 | 180 | 10 | 14 | 409 | 423 | 438 | 452 | 29 | 2028-02-22 | 2028-03-08 | 48000 |  | 3428.5714
T4-FA | T4 | ALL | Insulated facade installation | Envelope | 3234.816 | m2 | 150 | 16 | 22 | 342 | 364 | 430 | 452 | 88 | 2027-12-06 | 2027-12-30 | 271724.544 |  | 12351.1156
T4-GL | T4 | ALL | Glazing and frame installation | Envelope | 1257.984 | m2 | 90 | 12 | 14 | 423 | 437 | 452 | 466 | 29 | 2028-03-09 | 2028-03-24 | 276756.48 |  | 19768.32
T4-L00-M | T4 | L00 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 247 | 252 | 433 | 438 | 186 | 2027-08-17 | 2027-08-21 | 12204.27 |  | 2440.854
T4-L00-P | T4 | L00 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 255 | 261 | 441 | 447 | 186 | 2027-08-26 | 2027-09-01 | 15067 |  | 2511.1667
T4-L00-S | T4 | L00 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 263 | 266 | 449 | 452 | 186 | 2027-09-04 | 2027-09-07 | 9048 |  | 3016
T4-L00-T | T4 | L00 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 437 | 443 | 466 | 472 | 29 | 2028-03-25 | 2028-03-31 | 24012 |  | 4002
T4-L00-A | T4 | L00 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 445 | 450 | 474 | 479 | 29 | 2028-04-04 | 2028-04-08 | 10245.56 |  | 2049.112
T4-L00-D | T4 | L00 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 450 | 453 | 479 | 482 | 29 | 2028-04-10 | 2028-04-12 | 5796 |  | 1932
T4-L01-M | T4 | L01 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 265 | 270 | 433 | 438 | 168 | 2027-09-07 | 2027-09-11 | 12204.27 |  | 2440.854
T4-L01-P | T4 | L01 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 273 | 279 | 441 | 447 | 168 | 2027-09-16 | 2027-09-22 | 15067 |  | 2511.1667
T4-L01-S | T4 | L01 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 281 | 284 | 449 | 452 | 168 | 2027-09-25 | 2027-09-28 | 9048 |  | 3016
T4-L01-T | T4 | L01 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 437 | 443 | 466 | 472 | 29 | 2028-03-25 | 2028-03-31 | 24012 |  | 4002
T4-L01-A | T4 | L01 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 445 | 450 | 474 | 479 | 29 | 2028-04-04 | 2028-04-08 | 10245.56 |  | 2049.112
T4-L01-D | T4 | L01 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 450 | 453 | 479 | 482 | 29 | 2028-04-10 | 2028-04-12 | 5796 |  | 1932
T4-L02-M | T4 | L02 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 283 | 288 | 433 | 438 | 150 | 2027-09-28 | 2027-10-02 | 12204.27 |  | 2440.854
T4-L02-P | T4 | L02 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 291 | 297 | 441 | 447 | 150 | 2027-10-07 | 2027-10-13 | 15067 |  | 2511.1667
T4-L02-S | T4 | L02 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 299 | 302 | 449 | 452 | 150 | 2027-10-16 | 2027-10-19 | 9048 |  | 3016
T4-L02-T | T4 | L02 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 437 | 443 | 466 | 472 | 29 | 2028-03-25 | 2028-03-31 | 24012 |  | 4002
T4-L02-A | T4 | L02 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 445 | 450 | 474 | 479 | 29 | 2028-04-04 | 2028-04-08 | 10245.56 |  | 2049.112
T4-L02-D | T4 | L02 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 450 | 453 | 479 | 482 | 29 | 2028-04-10 | 2028-04-12 | 5796 |  | 1932
T4-L03-M | T4 | L03 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 301 | 306 | 433 | 438 | 132 | 2027-10-19 | 2027-10-23 | 12204.27 |  | 2440.854
T4-L03-P | T4 | L03 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 309 | 315 | 441 | 447 | 132 | 2027-10-28 | 2027-11-03 | 15067 |  | 2511.1667
T4-L03-S | T4 | L03 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 317 | 320 | 449 | 452 | 132 | 2027-11-06 | 2027-11-09 | 9048 |  | 3016
T4-L03-T | T4 | L03 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 437 | 443 | 466 | 472 | 29 | 2028-03-25 | 2028-03-31 | 24012 |  | 4002
T4-L03-A | T4 | L03 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 445 | 450 | 474 | 479 | 29 | 2028-04-04 | 2028-04-08 | 10245.56 |  | 2049.112
T4-L03-D | T4 | L03 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 450 | 453 | 479 | 482 | 29 | 2028-04-10 | 2028-04-12 | 5796 |  | 1932
T4-L04-M | T4 | L04 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 319 | 324 | 433 | 438 | 114 | 2027-11-09 | 2027-11-13 | 12204.27 |  | 2440.854
T4-L04-P | T4 | L04 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 327 | 333 | 441 | 447 | 114 | 2027-11-18 | 2027-11-24 | 15067 |  | 2511.1667
T4-L04-S | T4 | L04 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 335 | 338 | 449 | 452 | 114 | 2027-11-27 | 2027-11-30 | 9048 |  | 3016
T4-L04-T | T4 | L04 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 437 | 443 | 466 | 472 | 29 | 2028-03-25 | 2028-03-31 | 24012 |  | 4002
T4-L04-A | T4 | L04 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 445 | 450 | 474 | 479 | 29 | 2028-04-04 | 2028-04-08 | 10245.56 |  | 2049.112
T4-L04-D | T4 | L04 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 450 | 453 | 479 | 482 | 29 | 2028-04-10 | 2028-04-12 | 5796 |  | 1932
T4-L05-M | T4 | L05 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 337 | 342 | 433 | 438 | 96 | 2027-11-30 | 2027-12-04 | 12204.27 |  | 2440.854
T4-L05-P | T4 | L05 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 345 | 351 | 441 | 447 | 96 | 2027-12-09 | 2027-12-15 | 15067 |  | 2511.1667
T4-L05-S | T4 | L05 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 353 | 356 | 449 | 452 | 96 | 2027-12-18 | 2027-12-21 | 9048 |  | 3016
T4-L05-T | T4 | L05 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 437 | 443 | 466 | 472 | 29 | 2028-03-25 | 2028-03-31 | 24012 |  | 4002
T4-L05-A | T4 | L05 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 445 | 450 | 474 | 479 | 29 | 2028-04-04 | 2028-04-08 | 10245.56 |  | 2049.112
T4-L05-D | T4 | L05 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 450 | 453 | 479 | 482 | 29 | 2028-04-10 | 2028-04-12 | 5796 |  | 1932
T4-L06-M | T4 | L06 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 355 | 360 | 433 | 438 | 78 | 2027-12-21 | 2027-12-25 | 12204.27 |  | 2440.854
T4-L06-P | T4 | L06 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 363 | 369 | 441 | 447 | 78 | 2027-12-30 | 2028-01-05 | 15067 |  | 2511.1667
T4-L06-S | T4 | L06 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 371 | 374 | 449 | 452 | 78 | 2028-01-08 | 2028-01-11 | 9048 |  | 3016
T4-L06-T | T4 | L06 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 437 | 443 | 466 | 472 | 29 | 2028-03-25 | 2028-03-31 | 24012 |  | 4002
T4-L06-A | T4 | L06 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 445 | 450 | 474 | 479 | 29 | 2028-04-04 | 2028-04-08 | 10245.56 |  | 2049.112
T4-L06-D | T4 | L06 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 450 | 453 | 479 | 482 | 29 | 2028-04-10 | 2028-04-12 | 5796 |  | 1932
T4-L07-M | T4 | L07 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 373 | 378 | 433 | 438 | 60 | 2028-01-11 | 2028-01-15 | 12204.27 |  | 2440.854
T4-L07-P | T4 | L07 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 381 | 387 | 441 | 447 | 60 | 2028-01-20 | 2028-01-26 | 15067 |  | 2511.1667
T4-L07-S | T4 | L07 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 389 | 392 | 449 | 452 | 60 | 2028-01-29 | 2028-02-01 | 9048 |  | 3016
T4-L07-T | T4 | L07 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 437 | 443 | 466 | 472 | 29 | 2028-03-25 | 2028-03-31 | 24012 |  | 4002
T4-L07-A | T4 | L07 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 445 | 450 | 474 | 479 | 29 | 2028-04-04 | 2028-04-08 | 10245.56 |  | 2049.112
T4-L07-D | T4 | L07 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 450 | 453 | 479 | 482 | 29 | 2028-04-10 | 2028-04-12 | 5796 |  | 1932
T4-L08-M | T4 | L08 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 391 | 396 | 433 | 438 | 42 | 2028-02-01 | 2028-02-05 | 12204.27 |  | 2440.854
T4-L08-P | T4 | L08 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 399 | 405 | 441 | 447 | 42 | 2028-02-10 | 2028-02-16 | 15067 |  | 2511.1667
T4-L08-S | T4 | L08 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 407 | 410 | 449 | 452 | 42 | 2028-02-19 | 2028-02-22 | 9048 |  | 3016
T4-L08-T | T4 | L08 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 437 | 443 | 466 | 472 | 29 | 2028-03-25 | 2028-03-31 | 24012 |  | 4002
T4-L08-A | T4 | L08 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 445 | 450 | 474 | 479 | 29 | 2028-04-04 | 2028-04-08 | 10245.56 |  | 2049.112
T4-L08-D | T4 | L08 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 450 | 453 | 479 | 482 | 29 | 2028-04-10 | 2028-04-12 | 5796 |  | 1932
T4-L09-M | T4 | L09 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 409 | 414 | 433 | 438 | 24 | 2028-02-22 | 2028-02-26 | 12204.27 |  | 2440.854
T4-L09-P | T4 | L09 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 417 | 423 | 441 | 447 | 24 | 2028-03-02 | 2028-03-08 | 15067 |  | 2511.1667
T4-L09-S | T4 | L09 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 425 | 428 | 449 | 452 | 24 | 2028-03-11 | 2028-03-14 | 9048 |  | 3016
T4-L09-T | T4 | L09 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 442 | 448 | 466 | 472 | 24 | 2028-03-31 | 2028-04-06 | 24012 |  | 4002
T4-L09-A | T4 | L09 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 450 | 455 | 474 | 479 | 24 | 2028-04-10 | 2028-04-14 | 10245.56 |  | 2049.112
T4-L09-D | T4 | L09 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 455 | 458 | 479 | 482 | 24 | 2028-04-15 | 2028-04-18 | 5796 |  | 1932
T4-L10-M | T4 | L10 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 409 | 414 | 433 | 438 | 24 | 2028-02-22 | 2028-02-26 | 12204.27 |  | 2440.854
T4-L10-P | T4 | L10 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 417 | 423 | 441 | 447 | 24 | 2028-03-02 | 2028-03-08 | 15067 |  | 2511.1667
T4-L10-S | T4 | L10 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 425 | 428 | 449 | 452 | 24 | 2028-03-11 | 2028-03-14 | 9048 |  | 3016
T4-L10-T | T4 | L10 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 442 | 448 | 466 | 472 | 24 | 2028-03-31 | 2028-04-06 | 24012 |  | 4002
T4-L10-A | T4 | L10 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 450 | 455 | 474 | 479 | 24 | 2028-04-10 | 2028-04-14 | 10245.56 |  | 2049.112
T4-L10-D | T4 | L10 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 455 | 458 | 479 | 482 | 24 | 2028-04-15 | 2028-04-18 | 5796 |  | 1932
T4-L11-M | T4 | L11 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 409 | 414 | 433 | 438 | 24 | 2028-02-22 | 2028-02-26 | 12204.27 |  | 2440.854
T4-L11-P | T4 | L11 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 417 | 423 | 441 | 447 | 24 | 2028-03-02 | 2028-03-08 | 15067 |  | 2511.1667
T4-L11-S | T4 | L11 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 425 | 428 | 449 | 452 | 24 | 2028-03-11 | 2028-03-14 | 9048 |  | 3016
T4-L11-T | T4 | L11 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 442 | 448 | 466 | 472 | 24 | 2028-03-31 | 2028-04-06 | 24012 |  | 4002
T4-L11-A | T4 | L11 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 450 | 455 | 474 | 479 | 24 | 2028-04-10 | 2028-04-14 | 10245.56 |  | 2049.112
T4-L11-D | T4 | L11 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 455 | 458 | 479 | 482 | 24 | 2028-04-15 | 2028-04-18 | 5796 |  | 1932
T4-L12-M | T4 | L12 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 409 | 414 | 433 | 438 | 24 | 2028-02-22 | 2028-02-26 | 12204.27 |  | 2440.854
T4-L12-P | T4 | L12 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 417 | 423 | 441 | 447 | 24 | 2028-03-02 | 2028-03-08 | 15067 |  | 2511.1667
T4-L12-S | T4 | L12 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 425 | 428 | 449 | 452 | 24 | 2028-03-11 | 2028-03-14 | 9048 |  | 3016
T4-L12-T | T4 | L12 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 442 | 448 | 466 | 472 | 24 | 2028-03-31 | 2028-04-06 | 24012 |  | 4002
T4-L12-A | T4 | L12 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 450 | 455 | 474 | 479 | 24 | 2028-04-10 | 2028-04-14 | 10245.56 |  | 2049.112
T4-L12-D | T4 | L12 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 455 | 458 | 479 | 482 | 24 | 2028-04-15 | 2028-04-18 | 5796 |  | 1932
T5-L00-F | T5 | L00 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 182 | 188 | 194 | 200 | 12 | 2027-06-02 | 2027-06-08 | 29364.32 |  | 4894.0533
T5-L00-R | T5 | L00 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 188 | 193 | 200 | 205 | 12 | 2027-06-09 | 2027-06-14 | 25795.5172 |  | 5159.1034
T5-L00-C | T5 | L00 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 193 | 195 | 205 | 207 | 12 | 2027-06-15 | 2027-06-16 | 33527.397 |  | 16763.6985
T5-L00-H | T5 | L00 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 195 | 200 | 207 | 212 | 12 | 2027-06-17 | 2027-06-22 | 0 | 5 | 0
T5-L01-F | T5 | L01 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 200 | 206 | 212 | 218 | 12 | 2027-06-23 | 2027-06-29 | 29364.32 |  | 4894.0533
T5-L01-R | T5 | L01 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 206 | 211 | 218 | 223 | 12 | 2027-06-30 | 2027-07-05 | 25795.5172 |  | 5159.1034
T5-L01-C | T5 | L01 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 211 | 213 | 223 | 225 | 12 | 2027-07-06 | 2027-07-07 | 33527.397 |  | 16763.6985
T5-L01-H | T5 | L01 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 213 | 218 | 225 | 230 | 12 | 2027-07-08 | 2027-07-13 | 0 | 5 | 0
T5-L02-F | T5 | L02 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 218 | 224 | 230 | 236 | 12 | 2027-07-14 | 2027-07-20 | 29364.32 |  | 4894.0533
T5-L02-R | T5 | L02 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 224 | 229 | 236 | 241 | 12 | 2027-07-21 | 2027-07-26 | 25795.5172 |  | 5159.1034
T5-L02-C | T5 | L02 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 229 | 231 | 241 | 243 | 12 | 2027-07-27 | 2027-07-28 | 33527.397 |  | 16763.6985
T5-L02-H | T5 | L02 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 231 | 236 | 243 | 248 | 12 | 2027-07-29 | 2027-08-03 | 0 | 5 | 0
T5-L03-F | T5 | L03 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 236 | 242 | 248 | 254 | 12 | 2027-08-04 | 2027-08-10 | 29364.32 |  | 4894.0533
T5-L03-R | T5 | L03 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 242 | 247 | 254 | 259 | 12 | 2027-08-11 | 2027-08-16 | 25795.5172 |  | 5159.1034
T5-L03-C | T5 | L03 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 247 | 249 | 259 | 261 | 12 | 2027-08-17 | 2027-08-18 | 33527.397 |  | 16763.6985
T5-L03-H | T5 | L03 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 249 | 254 | 261 | 266 | 12 | 2027-08-19 | 2027-08-24 | 0 | 5 | 0
T5-L04-F | T5 | L04 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 254 | 260 | 266 | 272 | 12 | 2027-08-25 | 2027-08-31 | 29364.32 |  | 4894.0533
T5-L04-R | T5 | L04 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 260 | 265 | 272 | 277 | 12 | 2027-09-01 | 2027-09-06 | 25795.5172 |  | 5159.1034
T5-L04-C | T5 | L04 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 265 | 267 | 277 | 279 | 12 | 2027-09-07 | 2027-09-08 | 33527.397 |  | 16763.6985
T5-L04-H | T5 | L04 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 267 | 272 | 279 | 284 | 12 | 2027-09-09 | 2027-09-14 | 0 | 5 | 0
T5-L05-F | T5 | L05 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 272 | 278 | 284 | 290 | 12 | 2027-09-15 | 2027-09-21 | 29364.32 |  | 4894.0533
T5-L05-R | T5 | L05 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 278 | 283 | 290 | 295 | 12 | 2027-09-22 | 2027-09-27 | 25795.5172 |  | 5159.1034
T5-L05-C | T5 | L05 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 283 | 285 | 295 | 297 | 12 | 2027-09-28 | 2027-09-29 | 33527.397 |  | 16763.6985
T5-L05-H | T5 | L05 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 285 | 290 | 297 | 302 | 12 | 2027-09-30 | 2027-10-05 | 0 | 5 | 0
T5-L06-F | T5 | L06 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 290 | 296 | 302 | 308 | 12 | 2027-10-06 | 2027-10-12 | 29364.32 |  | 4894.0533
T5-L06-R | T5 | L06 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 296 | 301 | 308 | 313 | 12 | 2027-10-13 | 2027-10-18 | 25795.5172 |  | 5159.1034
T5-L06-C | T5 | L06 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 301 | 303 | 313 | 315 | 12 | 2027-10-19 | 2027-10-20 | 33527.397 |  | 16763.6985
T5-L06-H | T5 | L06 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 303 | 308 | 315 | 320 | 12 | 2027-10-21 | 2027-10-26 | 0 | 5 | 0
T5-L07-F | T5 | L07 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 308 | 314 | 320 | 326 | 12 | 2027-10-27 | 2027-11-02 | 29364.32 |  | 4894.0533
T5-L07-R | T5 | L07 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 314 | 319 | 326 | 331 | 12 | 2027-11-03 | 2027-11-08 | 25795.5172 |  | 5159.1034
T5-L07-C | T5 | L07 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 319 | 321 | 331 | 333 | 12 | 2027-11-09 | 2027-11-10 | 33527.397 |  | 16763.6985
T5-L07-H | T5 | L07 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 321 | 326 | 333 | 338 | 12 | 2027-11-11 | 2027-11-16 | 0 | 5 | 0
T5-L08-F | T5 | L08 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 326 | 332 | 338 | 344 | 12 | 2027-11-17 | 2027-11-23 | 29364.32 |  | 4894.0533
T5-L08-R | T5 | L08 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 332 | 337 | 344 | 349 | 12 | 2027-11-24 | 2027-11-29 | 25795.5172 |  | 5159.1034
T5-L08-C | T5 | L08 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 337 | 339 | 349 | 351 | 12 | 2027-11-30 | 2027-12-01 | 33527.397 |  | 16763.6985
T5-L08-H | T5 | L08 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 339 | 344 | 351 | 356 | 12 | 2027-12-02 | 2027-12-07 | 0 | 5 | 0
T5-L09-F | T5 | L09 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 344 | 350 | 356 | 362 | 12 | 2027-12-08 | 2027-12-14 | 29364.32 |  | 4894.0533
T5-L09-R | T5 | L09 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 350 | 355 | 362 | 367 | 12 | 2027-12-15 | 2027-12-20 | 25795.5172 |  | 5159.1034
T5-L09-C | T5 | L09 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 355 | 357 | 367 | 369 | 12 | 2027-12-21 | 2027-12-22 | 33527.397 |  | 16763.6985
T5-L09-H | T5 | L09 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 357 | 362 | 369 | 374 | 12 | 2027-12-23 | 2027-12-28 | 0 | 5 | 0
T5-L10-F | T5 | L10 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 362 | 368 | 374 | 380 | 12 | 2027-12-29 | 2028-01-04 | 29364.32 |  | 4894.0533
T5-L10-R | T5 | L10 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 368 | 373 | 380 | 385 | 12 | 2028-01-05 | 2028-01-10 | 25795.5172 |  | 5159.1034
T5-L10-C | T5 | L10 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 373 | 375 | 385 | 387 | 12 | 2028-01-11 | 2028-01-12 | 33527.397 |  | 16763.6985
T5-L10-H | T5 | L10 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 375 | 380 | 387 | 392 | 12 | 2028-01-13 | 2028-01-18 | 0 | 5 | 0
T5-L11-F | T5 | L11 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 380 | 386 | 392 | 398 | 12 | 2028-01-19 | 2028-01-25 | 29364.32 |  | 4894.0533
T5-L11-R | T5 | L11 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 386 | 391 | 398 | 403 | 12 | 2028-01-26 | 2028-01-31 | 25795.5172 |  | 5159.1034
T5-L11-C | T5 | L11 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 391 | 393 | 403 | 405 | 12 | 2028-02-01 | 2028-02-02 | 33527.397 |  | 16763.6985
T5-L11-H | T5 | L11 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 393 | 398 | 405 | 410 | 12 | 2028-02-03 | 2028-02-08 | 0 | 5 | 0
T5-L12-F | T5 | L12 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 398 | 404 | 410 | 416 | 12 | 2028-02-09 | 2028-02-15 | 29364.32 |  | 4894.0533
T5-L12-R | T5 | L12 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 404 | 409 | 416 | 421 | 12 | 2028-02-16 | 2028-02-21 | 25795.5172 |  | 5159.1034
T5-L12-C | T5 | L12 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 409 | 411 | 421 | 423 | 12 | 2028-02-22 | 2028-02-23 | 33527.397 |  | 16763.6985
T5-L12-H | T5 | L12 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 411 | 416 | 423 | 428 | 12 | 2028-02-24 | 2028-02-29 | 0 | 5 | 0
T5-RF | T5 | ROOF | Roof membrane and weatherproofing | Envelope | 2400 | m2 | 180 | 10 | 14 | 421 | 435 | 438 | 452 | 17 | 2028-03-07 | 2028-03-22 | 48000 |  | 3428.5714
T5-FA | T5 | ALL | Insulated facade installation | Envelope | 3234.816 | m2 | 150 | 16 | 22 | 354 | 376 | 430 | 452 | 76 | 2027-12-20 | 2028-01-13 | 271724.544 |  | 12351.1156
T5-GL | T5 | ALL | Glazing and frame installation | Envelope | 1257.984 | m2 | 90 | 12 | 14 | 435 | 449 | 452 | 466 | 17 | 2028-03-23 | 2028-04-07 | 276756.48 |  | 19768.32
T5-L00-M | T5 | L00 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 259 | 264 | 433 | 438 | 174 | 2027-08-31 | 2027-09-04 | 12204.27 |  | 2440.854
T5-L00-P | T5 | L00 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 267 | 273 | 441 | 447 | 174 | 2027-09-09 | 2027-09-15 | 15067 |  | 2511.1667
T5-L00-S | T5 | L00 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 275 | 278 | 449 | 452 | 174 | 2027-09-18 | 2027-09-21 | 9048 |  | 3016
T5-L00-T | T5 | L00 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 449 | 455 | 466 | 472 | 17 | 2028-04-08 | 2028-04-14 | 24012 |  | 4002
T5-L00-A | T5 | L00 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 457 | 462 | 474 | 479 | 17 | 2028-04-18 | 2028-04-22 | 10245.56 |  | 2049.112
T5-L00-D | T5 | L00 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 462 | 465 | 479 | 482 | 17 | 2028-04-24 | 2028-04-26 | 5796 |  | 1932
T5-L01-M | T5 | L01 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 277 | 282 | 433 | 438 | 156 | 2027-09-21 | 2027-09-25 | 12204.27 |  | 2440.854
T5-L01-P | T5 | L01 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 285 | 291 | 441 | 447 | 156 | 2027-09-30 | 2027-10-06 | 15067 |  | 2511.1667
T5-L01-S | T5 | L01 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 293 | 296 | 449 | 452 | 156 | 2027-10-09 | 2027-10-12 | 9048 |  | 3016
T5-L01-T | T5 | L01 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 449 | 455 | 466 | 472 | 17 | 2028-04-08 | 2028-04-14 | 24012 |  | 4002
T5-L01-A | T5 | L01 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 457 | 462 | 474 | 479 | 17 | 2028-04-18 | 2028-04-22 | 10245.56 |  | 2049.112
T5-L01-D | T5 | L01 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 462 | 465 | 479 | 482 | 17 | 2028-04-24 | 2028-04-26 | 5796 |  | 1932
T5-L02-M | T5 | L02 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 295 | 300 | 433 | 438 | 138 | 2027-10-12 | 2027-10-16 | 12204.27 |  | 2440.854
T5-L02-P | T5 | L02 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 303 | 309 | 441 | 447 | 138 | 2027-10-21 | 2027-10-27 | 15067 |  | 2511.1667
T5-L02-S | T5 | L02 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 311 | 314 | 449 | 452 | 138 | 2027-10-30 | 2027-11-02 | 9048 |  | 3016
T5-L02-T | T5 | L02 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 449 | 455 | 466 | 472 | 17 | 2028-04-08 | 2028-04-14 | 24012 |  | 4002
T5-L02-A | T5 | L02 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 457 | 462 | 474 | 479 | 17 | 2028-04-18 | 2028-04-22 | 10245.56 |  | 2049.112
T5-L02-D | T5 | L02 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 462 | 465 | 479 | 482 | 17 | 2028-04-24 | 2028-04-26 | 5796 |  | 1932
T5-L03-M | T5 | L03 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 313 | 318 | 433 | 438 | 120 | 2027-11-02 | 2027-11-06 | 12204.27 |  | 2440.854
T5-L03-P | T5 | L03 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 321 | 327 | 441 | 447 | 120 | 2027-11-11 | 2027-11-17 | 15067 |  | 2511.1667
T5-L03-S | T5 | L03 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 329 | 332 | 449 | 452 | 120 | 2027-11-20 | 2027-11-23 | 9048 |  | 3016
T5-L03-T | T5 | L03 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 449 | 455 | 466 | 472 | 17 | 2028-04-08 | 2028-04-14 | 24012 |  | 4002
T5-L03-A | T5 | L03 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 457 | 462 | 474 | 479 | 17 | 2028-04-18 | 2028-04-22 | 10245.56 |  | 2049.112
T5-L03-D | T5 | L03 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 462 | 465 | 479 | 482 | 17 | 2028-04-24 | 2028-04-26 | 5796 |  | 1932
T5-L04-M | T5 | L04 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 331 | 336 | 433 | 438 | 102 | 2027-11-23 | 2027-11-27 | 12204.27 |  | 2440.854
T5-L04-P | T5 | L04 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 339 | 345 | 441 | 447 | 102 | 2027-12-02 | 2027-12-08 | 15067 |  | 2511.1667
T5-L04-S | T5 | L04 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 347 | 350 | 449 | 452 | 102 | 2027-12-11 | 2027-12-14 | 9048 |  | 3016
T5-L04-T | T5 | L04 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 449 | 455 | 466 | 472 | 17 | 2028-04-08 | 2028-04-14 | 24012 |  | 4002
T5-L04-A | T5 | L04 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 457 | 462 | 474 | 479 | 17 | 2028-04-18 | 2028-04-22 | 10245.56 |  | 2049.112
T5-L04-D | T5 | L04 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 462 | 465 | 479 | 482 | 17 | 2028-04-24 | 2028-04-26 | 5796 |  | 1932
T5-L05-M | T5 | L05 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 349 | 354 | 433 | 438 | 84 | 2027-12-14 | 2027-12-18 | 12204.27 |  | 2440.854
T5-L05-P | T5 | L05 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 357 | 363 | 441 | 447 | 84 | 2027-12-23 | 2027-12-29 | 15067 |  | 2511.1667
T5-L05-S | T5 | L05 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 365 | 368 | 449 | 452 | 84 | 2028-01-01 | 2028-01-04 | 9048 |  | 3016
T5-L05-T | T5 | L05 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 449 | 455 | 466 | 472 | 17 | 2028-04-08 | 2028-04-14 | 24012 |  | 4002
T5-L05-A | T5 | L05 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 457 | 462 | 474 | 479 | 17 | 2028-04-18 | 2028-04-22 | 10245.56 |  | 2049.112
T5-L05-D | T5 | L05 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 462 | 465 | 479 | 482 | 17 | 2028-04-24 | 2028-04-26 | 5796 |  | 1932
T5-L06-M | T5 | L06 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 367 | 372 | 433 | 438 | 66 | 2028-01-04 | 2028-01-08 | 12204.27 |  | 2440.854
T5-L06-P | T5 | L06 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 375 | 381 | 441 | 447 | 66 | 2028-01-13 | 2028-01-19 | 15067 |  | 2511.1667
T5-L06-S | T5 | L06 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 383 | 386 | 449 | 452 | 66 | 2028-01-22 | 2028-01-25 | 9048 |  | 3016
T5-L06-T | T5 | L06 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 449 | 455 | 466 | 472 | 17 | 2028-04-08 | 2028-04-14 | 24012 |  | 4002
T5-L06-A | T5 | L06 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 457 | 462 | 474 | 479 | 17 | 2028-04-18 | 2028-04-22 | 10245.56 |  | 2049.112
T5-L06-D | T5 | L06 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 462 | 465 | 479 | 482 | 17 | 2028-04-24 | 2028-04-26 | 5796 |  | 1932
T5-L07-M | T5 | L07 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 385 | 390 | 433 | 438 | 48 | 2028-01-25 | 2028-01-29 | 12204.27 |  | 2440.854
T5-L07-P | T5 | L07 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 393 | 399 | 441 | 447 | 48 | 2028-02-03 | 2028-02-09 | 15067 |  | 2511.1667
T5-L07-S | T5 | L07 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 401 | 404 | 449 | 452 | 48 | 2028-02-12 | 2028-02-15 | 9048 |  | 3016
T5-L07-T | T5 | L07 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 449 | 455 | 466 | 472 | 17 | 2028-04-08 | 2028-04-14 | 24012 |  | 4002
T5-L07-A | T5 | L07 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 457 | 462 | 474 | 479 | 17 | 2028-04-18 | 2028-04-22 | 10245.56 |  | 2049.112
T5-L07-D | T5 | L07 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 462 | 465 | 479 | 482 | 17 | 2028-04-24 | 2028-04-26 | 5796 |  | 1932
T5-L08-M | T5 | L08 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 403 | 408 | 433 | 438 | 30 | 2028-02-15 | 2028-02-19 | 12204.27 |  | 2440.854
T5-L08-P | T5 | L08 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 411 | 417 | 441 | 447 | 30 | 2028-02-24 | 2028-03-01 | 15067 |  | 2511.1667
T5-L08-S | T5 | L08 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 419 | 422 | 449 | 452 | 30 | 2028-03-04 | 2028-03-07 | 9048 |  | 3016
T5-L08-T | T5 | L08 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 449 | 455 | 466 | 472 | 17 | 2028-04-08 | 2028-04-14 | 24012 |  | 4002
T5-L08-A | T5 | L08 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 457 | 462 | 474 | 479 | 17 | 2028-04-18 | 2028-04-22 | 10245.56 |  | 2049.112
T5-L08-D | T5 | L08 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 462 | 465 | 479 | 482 | 17 | 2028-04-24 | 2028-04-26 | 5796 |  | 1932
T5-L09-M | T5 | L09 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 421 | 426 | 433 | 438 | 12 | 2028-03-07 | 2028-03-11 | 12204.27 |  | 2440.854
T5-L09-P | T5 | L09 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 429 | 435 | 441 | 447 | 12 | 2028-03-16 | 2028-03-22 | 15067 |  | 2511.1667
T5-L09-S | T5 | L09 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 437 | 440 | 449 | 452 | 12 | 2028-03-25 | 2028-03-28 | 9048 |  | 3016
T5-L09-T | T5 | L09 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 454 | 460 | 466 | 472 | 12 | 2028-04-14 | 2028-04-20 | 24012 |  | 4002
T5-L09-A | T5 | L09 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 462 | 467 | 474 | 479 | 12 | 2028-04-24 | 2028-04-28 | 10245.56 |  | 2049.112
T5-L09-D | T5 | L09 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 467 | 470 | 479 | 482 | 12 | 2028-04-29 | 2028-05-02 | 5796 |  | 1932
T5-L10-M | T5 | L10 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 421 | 426 | 433 | 438 | 12 | 2028-03-07 | 2028-03-11 | 12204.27 |  | 2440.854
T5-L10-P | T5 | L10 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 429 | 435 | 441 | 447 | 12 | 2028-03-16 | 2028-03-22 | 15067 |  | 2511.1667
T5-L10-S | T5 | L10 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 437 | 440 | 449 | 452 | 12 | 2028-03-25 | 2028-03-28 | 9048 |  | 3016
T5-L10-T | T5 | L10 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 454 | 460 | 466 | 472 | 12 | 2028-04-14 | 2028-04-20 | 24012 |  | 4002
T5-L10-A | T5 | L10 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 462 | 467 | 474 | 479 | 12 | 2028-04-24 | 2028-04-28 | 10245.56 |  | 2049.112
T5-L10-D | T5 | L10 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 467 | 470 | 479 | 482 | 12 | 2028-04-29 | 2028-05-02 | 5796 |  | 1932
T5-L11-M | T5 | L11 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 421 | 426 | 433 | 438 | 12 | 2028-03-07 | 2028-03-11 | 12204.27 |  | 2440.854
T5-L11-P | T5 | L11 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 429 | 435 | 441 | 447 | 12 | 2028-03-16 | 2028-03-22 | 15067 |  | 2511.1667
T5-L11-S | T5 | L11 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 437 | 440 | 449 | 452 | 12 | 2028-03-25 | 2028-03-28 | 9048 |  | 3016
T5-L11-T | T5 | L11 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 454 | 460 | 466 | 472 | 12 | 2028-04-14 | 2028-04-20 | 24012 |  | 4002
T5-L11-A | T5 | L11 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 462 | 467 | 474 | 479 | 12 | 2028-04-24 | 2028-04-28 | 10245.56 |  | 2049.112
T5-L11-D | T5 | L11 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 467 | 470 | 479 | 482 | 12 | 2028-04-29 | 2028-05-02 | 5796 |  | 1932
T5-L12-M | T5 | L12 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 421 | 426 | 433 | 438 | 12 | 2028-03-07 | 2028-03-11 | 12204.27 |  | 2440.854
T5-L12-P | T5 | L12 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 429 | 435 | 441 | 447 | 12 | 2028-03-16 | 2028-03-22 | 15067 |  | 2511.1667
T5-L12-S | T5 | L12 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 437 | 440 | 449 | 452 | 12 | 2028-03-25 | 2028-03-28 | 9048 |  | 3016
T5-L12-T | T5 | L12 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 454 | 460 | 466 | 472 | 12 | 2028-04-14 | 2028-04-20 | 24012 |  | 4002
T5-L12-A | T5 | L12 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 462 | 467 | 474 | 479 | 12 | 2028-04-24 | 2028-04-28 | 10245.56 |  | 2049.112
T5-L12-D | T5 | L12 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 467 | 470 | 479 | 482 | 12 | 2028-04-29 | 2028-05-02 | 5796 |  | 1932
T6-L00-F | T6 | L00 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 194 | 200 | 194 | 200 | 0 | 2027-06-16 | 2027-06-22 | 29364.32 |  | 4894.0533
T6-L00-R | T6 | L00 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 200 | 205 | 200 | 205 | 0 | 2027-06-23 | 2027-06-28 | 25795.5172 |  | 5159.1034
T6-L00-C | T6 | L00 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 205 | 207 | 205 | 207 | 0 | 2027-06-29 | 2027-06-30 | 33527.397 |  | 16763.6985
T6-L00-H | T6 | L00 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 207 | 212 | 207 | 212 | 0 | 2027-07-01 | 2027-07-06 | 0 | 5 | 0
T6-L01-F | T6 | L01 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 212 | 218 | 212 | 218 | 0 | 2027-07-07 | 2027-07-13 | 29364.32 |  | 4894.0533
T6-L01-R | T6 | L01 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 218 | 223 | 218 | 223 | 0 | 2027-07-14 | 2027-07-19 | 25795.5172 |  | 5159.1034
T6-L01-C | T6 | L01 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 223 | 225 | 223 | 225 | 0 | 2027-07-20 | 2027-07-21 | 33527.397 |  | 16763.6985
T6-L01-H | T6 | L01 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 225 | 230 | 225 | 230 | 0 | 2027-07-22 | 2027-07-27 | 0 | 5 | 0
T6-L02-F | T6 | L02 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 230 | 236 | 230 | 236 | 0 | 2027-07-28 | 2027-08-03 | 29364.32 |  | 4894.0533
T6-L02-R | T6 | L02 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 236 | 241 | 236 | 241 | 0 | 2027-08-04 | 2027-08-09 | 25795.5172 |  | 5159.1034
T6-L02-C | T6 | L02 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 241 | 243 | 241 | 243 | 0 | 2027-08-10 | 2027-08-11 | 33527.397 |  | 16763.6985
T6-L02-H | T6 | L02 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 243 | 248 | 243 | 248 | 0 | 2027-08-12 | 2027-08-17 | 0 | 5 | 0
T6-L03-F | T6 | L03 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 248 | 254 | 248 | 254 | 0 | 2027-08-18 | 2027-08-24 | 29364.32 |  | 4894.0533
T6-L03-R | T6 | L03 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 254 | 259 | 254 | 259 | 0 | 2027-08-25 | 2027-08-30 | 25795.5172 |  | 5159.1034
T6-L03-C | T6 | L03 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 259 | 261 | 259 | 261 | 0 | 2027-08-31 | 2027-09-01 | 33527.397 |  | 16763.6985
T6-L03-H | T6 | L03 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 261 | 266 | 261 | 266 | 0 | 2027-09-02 | 2027-09-07 | 0 | 5 | 0
T6-L04-F | T6 | L04 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 266 | 272 | 266 | 272 | 0 | 2027-09-08 | 2027-09-14 | 29364.32 |  | 4894.0533
T6-L04-R | T6 | L04 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 272 | 277 | 272 | 277 | 0 | 2027-09-15 | 2027-09-20 | 25795.5172 |  | 5159.1034
T6-L04-C | T6 | L04 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 277 | 279 | 277 | 279 | 0 | 2027-09-21 | 2027-09-22 | 33527.397 |  | 16763.6985
T6-L04-H | T6 | L04 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 279 | 284 | 279 | 284 | 0 | 2027-09-23 | 2027-09-28 | 0 | 5 | 0
T6-L05-F | T6 | L05 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 284 | 290 | 284 | 290 | 0 | 2027-09-29 | 2027-10-05 | 29364.32 |  | 4894.0533
T6-L05-R | T6 | L05 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 290 | 295 | 290 | 295 | 0 | 2027-10-06 | 2027-10-11 | 25795.5172 |  | 5159.1034
T6-L05-C | T6 | L05 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 295 | 297 | 295 | 297 | 0 | 2027-10-12 | 2027-10-13 | 33527.397 |  | 16763.6985
T6-L05-H | T6 | L05 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 297 | 302 | 297 | 302 | 0 | 2027-10-14 | 2027-10-19 | 0 | 5 | 0
T6-L06-F | T6 | L06 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 302 | 308 | 302 | 308 | 0 | 2027-10-20 | 2027-10-26 | 29364.32 |  | 4894.0533
T6-L06-R | T6 | L06 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 308 | 313 | 308 | 313 | 0 | 2027-10-27 | 2027-11-01 | 25795.5172 |  | 5159.1034
T6-L06-C | T6 | L06 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 313 | 315 | 313 | 315 | 0 | 2027-11-02 | 2027-11-03 | 33527.397 |  | 16763.6985
T6-L06-H | T6 | L06 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 315 | 320 | 315 | 320 | 0 | 2027-11-04 | 2027-11-09 | 0 | 5 | 0
T6-L07-F | T6 | L07 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 320 | 326 | 320 | 326 | 0 | 2027-11-10 | 2027-11-16 | 29364.32 |  | 4894.0533
T6-L07-R | T6 | L07 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 326 | 331 | 326 | 331 | 0 | 2027-11-17 | 2027-11-22 | 25795.5172 |  | 5159.1034
T6-L07-C | T6 | L07 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 331 | 333 | 331 | 333 | 0 | 2027-11-23 | 2027-11-24 | 33527.397 |  | 16763.6985
T6-L07-H | T6 | L07 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 333 | 338 | 333 | 338 | 0 | 2027-11-25 | 2027-11-30 | 0 | 5 | 0
T6-L08-F | T6 | L08 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 338 | 344 | 338 | 344 | 0 | 2027-12-01 | 2027-12-07 | 29364.32 |  | 4894.0533
T6-L08-R | T6 | L08 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 344 | 349 | 344 | 349 | 0 | 2027-12-08 | 2027-12-13 | 25795.5172 |  | 5159.1034
T6-L08-C | T6 | L08 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 349 | 351 | 349 | 351 | 0 | 2027-12-14 | 2027-12-15 | 33527.397 |  | 16763.6985
T6-L08-H | T6 | L08 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 351 | 356 | 351 | 356 | 0 | 2027-12-16 | 2027-12-21 | 0 | 5 | 0
T6-L09-F | T6 | L09 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 356 | 362 | 356 | 362 | 0 | 2027-12-22 | 2027-12-28 | 29364.32 |  | 4894.0533
T6-L09-R | T6 | L09 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 362 | 367 | 362 | 367 | 0 | 2027-12-29 | 2028-01-03 | 25795.5172 |  | 5159.1034
T6-L09-C | T6 | L09 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 367 | 369 | 367 | 369 | 0 | 2028-01-04 | 2028-01-05 | 33527.397 |  | 16763.6985
T6-L09-H | T6 | L09 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 369 | 374 | 369 | 374 | 0 | 2028-01-06 | 2028-01-11 | 0 | 5 | 0
T6-L10-F | T6 | L10 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 374 | 380 | 374 | 380 | 0 | 2028-01-12 | 2028-01-18 | 29364.32 |  | 4894.0533
T6-L10-R | T6 | L10 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 380 | 385 | 380 | 385 | 0 | 2028-01-19 | 2028-01-24 | 25795.5172 |  | 5159.1034
T6-L10-C | T6 | L10 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 385 | 387 | 385 | 387 | 0 | 2028-01-25 | 2028-01-26 | 33527.397 |  | 16763.6985
T6-L10-H | T6 | L10 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 387 | 392 | 387 | 392 | 0 | 2028-01-27 | 2028-02-01 | 0 | 5 | 0
T6-L11-F | T6 | L11 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 392 | 398 | 392 | 398 | 0 | 2028-02-02 | 2028-02-08 | 29364.32 |  | 4894.0533
T6-L11-R | T6 | L11 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 398 | 403 | 398 | 403 | 0 | 2028-02-09 | 2028-02-14 | 25795.5172 |  | 5159.1034
T6-L11-C | T6 | L11 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 403 | 405 | 403 | 405 | 0 | 2028-02-15 | 2028-02-16 | 33527.397 |  | 16763.6985
T6-L11-H | T6 | L11 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 405 | 410 | 405 | 410 | 0 | 2028-02-17 | 2028-02-22 | 0 | 5 | 0
T6-L12-F | T6 | L12 | Columns, core and deck formwork | Formwork | 1222.66 | m2 | 220 | 18 | 6 | 410 | 416 | 410 | 416 | 0 | 2028-02-23 | 2028-02-29 | 29364.32 |  | 4894.0533
T6-L12-R | T6 | L12 | Column, wall, beam and slab reinforcement | Rebar | 29.6841 | t | 7 | 14 | 5 | 416 | 421 | 416 | 421 | 0 | 2028-03-01 | 2028-03-06 | 25795.5172 |  | 5159.1034
T6-L12-C | T6 | L12 | Concrete placement and finishing | Concrete | 226.7082 | m3 | 170 | 12 | 2 | 421 | 423 | 421 | 423 | 0 | 2028-03-07 | 2028-03-08 | 33527.397 |  | 16763.6985
T6-L12-H | T6 | L12 | Curing and release hold point | Site | 1 | hold | 1 | 0 | 5 | 423 | 428 | 423 | 428 | 0 | 2028-03-09 | 2028-03-14 | 0 | 5 | 0
T6-RF | T6 | ROOF | Roof membrane and weatherproofing | Envelope | 2400 | m2 | 180 | 10 | 14 | 433 | 447 | 438 | 452 | 5 | 2028-03-21 | 2028-04-05 | 48000 |  | 3428.5714
T6-FA | T6 | ALL | Insulated facade installation | Envelope | 3234.816 | m2 | 150 | 16 | 22 | 366 | 388 | 430 | 452 | 64 | 2028-01-03 | 2028-01-27 | 271724.544 |  | 12351.1156
T6-GL | T6 | ALL | Glazing and frame installation | Envelope | 1257.984 | m2 | 90 | 12 | 14 | 447 | 461 | 452 | 466 | 5 | 2028-04-06 | 2028-04-21 | 276756.48 |  | 19768.32
T6-L00-M | T6 | L00 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 271 | 276 | 433 | 438 | 162 | 2027-09-14 | 2027-09-18 | 12204.27 |  | 2440.854
T6-L00-P | T6 | L00 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 279 | 285 | 441 | 447 | 162 | 2027-09-23 | 2027-09-29 | 15067 |  | 2511.1667
T6-L00-S | T6 | L00 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 287 | 290 | 449 | 452 | 162 | 2027-10-02 | 2027-10-05 | 9048 |  | 3016
T6-L00-T | T6 | L00 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 461 | 467 | 466 | 472 | 5 | 2028-04-22 | 2028-04-28 | 24012 |  | 4002
T6-L00-A | T6 | L00 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 469 | 474 | 474 | 479 | 5 | 2028-05-02 | 2028-05-06 | 10245.56 |  | 2049.112
T6-L00-D | T6 | L00 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 474 | 477 | 479 | 482 | 5 | 2028-05-08 | 2028-05-10 | 5796 |  | 1932
T6-L01-M | T6 | L01 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 289 | 294 | 433 | 438 | 144 | 2027-10-05 | 2027-10-09 | 12204.27 |  | 2440.854
T6-L01-P | T6 | L01 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 297 | 303 | 441 | 447 | 144 | 2027-10-14 | 2027-10-20 | 15067 |  | 2511.1667
T6-L01-S | T6 | L01 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 305 | 308 | 449 | 452 | 144 | 2027-10-23 | 2027-10-26 | 9048 |  | 3016
T6-L01-T | T6 | L01 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 461 | 467 | 466 | 472 | 5 | 2028-04-22 | 2028-04-28 | 24012 |  | 4002
T6-L01-A | T6 | L01 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 469 | 474 | 474 | 479 | 5 | 2028-05-02 | 2028-05-06 | 10245.56 |  | 2049.112
T6-L01-D | T6 | L01 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 474 | 477 | 479 | 482 | 5 | 2028-05-08 | 2028-05-10 | 5796 |  | 1932
T6-L02-M | T6 | L02 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 307 | 312 | 433 | 438 | 126 | 2027-10-26 | 2027-10-30 | 12204.27 |  | 2440.854
T6-L02-P | T6 | L02 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 315 | 321 | 441 | 447 | 126 | 2027-11-04 | 2027-11-10 | 15067 |  | 2511.1667
T6-L02-S | T6 | L02 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 323 | 326 | 449 | 452 | 126 | 2027-11-13 | 2027-11-16 | 9048 |  | 3016
T6-L02-T | T6 | L02 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 461 | 467 | 466 | 472 | 5 | 2028-04-22 | 2028-04-28 | 24012 |  | 4002
T6-L02-A | T6 | L02 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 469 | 474 | 474 | 479 | 5 | 2028-05-02 | 2028-05-06 | 10245.56 |  | 2049.112
T6-L02-D | T6 | L02 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 474 | 477 | 479 | 482 | 5 | 2028-05-08 | 2028-05-10 | 5796 |  | 1932
T6-L03-M | T6 | L03 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 325 | 330 | 433 | 438 | 108 | 2027-11-16 | 2027-11-20 | 12204.27 |  | 2440.854
T6-L03-P | T6 | L03 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 333 | 339 | 441 | 447 | 108 | 2027-11-25 | 2027-12-01 | 15067 |  | 2511.1667
T6-L03-S | T6 | L03 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 341 | 344 | 449 | 452 | 108 | 2027-12-04 | 2027-12-07 | 9048 |  | 3016
T6-L03-T | T6 | L03 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 461 | 467 | 466 | 472 | 5 | 2028-04-22 | 2028-04-28 | 24012 |  | 4002
T6-L03-A | T6 | L03 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 469 | 474 | 474 | 479 | 5 | 2028-05-02 | 2028-05-06 | 10245.56 |  | 2049.112
T6-L03-D | T6 | L03 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 474 | 477 | 479 | 482 | 5 | 2028-05-08 | 2028-05-10 | 5796 |  | 1932
T6-L04-M | T6 | L04 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 343 | 348 | 433 | 438 | 90 | 2027-12-07 | 2027-12-11 | 12204.27 |  | 2440.854
T6-L04-P | T6 | L04 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 351 | 357 | 441 | 447 | 90 | 2027-12-16 | 2027-12-22 | 15067 |  | 2511.1667
T6-L04-S | T6 | L04 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 359 | 362 | 449 | 452 | 90 | 2027-12-25 | 2027-12-28 | 9048 |  | 3016
T6-L04-T | T6 | L04 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 461 | 467 | 466 | 472 | 5 | 2028-04-22 | 2028-04-28 | 24012 |  | 4002
T6-L04-A | T6 | L04 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 469 | 474 | 474 | 479 | 5 | 2028-05-02 | 2028-05-06 | 10245.56 |  | 2049.112
T6-L04-D | T6 | L04 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 474 | 477 | 479 | 482 | 5 | 2028-05-08 | 2028-05-10 | 5796 |  | 1932
T6-L05-M | T6 | L05 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 361 | 366 | 433 | 438 | 72 | 2027-12-28 | 2028-01-01 | 12204.27 |  | 2440.854
T6-L05-P | T6 | L05 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 369 | 375 | 441 | 447 | 72 | 2028-01-06 | 2028-01-12 | 15067 |  | 2511.1667
T6-L05-S | T6 | L05 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 377 | 380 | 449 | 452 | 72 | 2028-01-15 | 2028-01-18 | 9048 |  | 3016
T6-L05-T | T6 | L05 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 461 | 467 | 466 | 472 | 5 | 2028-04-22 | 2028-04-28 | 24012 |  | 4002
T6-L05-A | T6 | L05 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 469 | 474 | 474 | 479 | 5 | 2028-05-02 | 2028-05-06 | 10245.56 |  | 2049.112
T6-L05-D | T6 | L05 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 474 | 477 | 479 | 482 | 5 | 2028-05-08 | 2028-05-10 | 5796 |  | 1932
T6-L06-M | T6 | L06 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 379 | 384 | 433 | 438 | 54 | 2028-01-18 | 2028-01-22 | 12204.27 |  | 2440.854
T6-L06-P | T6 | L06 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 387 | 393 | 441 | 447 | 54 | 2028-01-27 | 2028-02-02 | 15067 |  | 2511.1667
T6-L06-S | T6 | L06 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 395 | 398 | 449 | 452 | 54 | 2028-02-05 | 2028-02-08 | 9048 |  | 3016
T6-L06-T | T6 | L06 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 461 | 467 | 466 | 472 | 5 | 2028-04-22 | 2028-04-28 | 24012 |  | 4002
T6-L06-A | T6 | L06 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 469 | 474 | 474 | 479 | 5 | 2028-05-02 | 2028-05-06 | 10245.56 |  | 2049.112
T6-L06-D | T6 | L06 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 474 | 477 | 479 | 482 | 5 | 2028-05-08 | 2028-05-10 | 5796 |  | 1932
T6-L07-M | T6 | L07 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 397 | 402 | 433 | 438 | 36 | 2028-02-08 | 2028-02-12 | 12204.27 |  | 2440.854
T6-L07-P | T6 | L07 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 405 | 411 | 441 | 447 | 36 | 2028-02-17 | 2028-02-23 | 15067 |  | 2511.1667
T6-L07-S | T6 | L07 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 413 | 416 | 449 | 452 | 36 | 2028-02-26 | 2028-02-29 | 9048 |  | 3016
T6-L07-T | T6 | L07 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 461 | 467 | 466 | 472 | 5 | 2028-04-22 | 2028-04-28 | 24012 |  | 4002
T6-L07-A | T6 | L07 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 469 | 474 | 474 | 479 | 5 | 2028-05-02 | 2028-05-06 | 10245.56 |  | 2049.112
T6-L07-D | T6 | L07 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 474 | 477 | 479 | 482 | 5 | 2028-05-08 | 2028-05-10 | 5796 |  | 1932
T6-L08-M | T6 | L08 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 415 | 420 | 433 | 438 | 18 | 2028-02-29 | 2028-03-04 | 12204.27 |  | 2440.854
T6-L08-P | T6 | L08 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 423 | 429 | 441 | 447 | 18 | 2028-03-09 | 2028-03-15 | 15067 |  | 2511.1667
T6-L08-S | T6 | L08 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 431 | 434 | 449 | 452 | 18 | 2028-03-18 | 2028-03-21 | 9048 |  | 3016
T6-L08-T | T6 | L08 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 461 | 467 | 466 | 472 | 5 | 2028-04-22 | 2028-04-28 | 24012 |  | 4002
T6-L08-A | T6 | L08 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 469 | 474 | 474 | 479 | 5 | 2028-05-02 | 2028-05-06 | 10245.56 |  | 2049.112
T6-L08-D | T6 | L08 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 474 | 477 | 479 | 482 | 5 | 2028-05-08 | 2028-05-10 | 5796 |  | 1932
T6-L09-M | T6 | L09 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 433 | 438 | 433 | 438 | 0 | 2028-03-21 | 2028-03-25 | 12204.27 |  | 2440.854
T6-L09-P | T6 | L09 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 441 | 447 | 441 | 447 | 0 | 2028-03-30 | 2028-04-05 | 15067 |  | 2511.1667
T6-L09-S | T6 | L09 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 449 | 452 | 449 | 452 | 0 | 2028-04-08 | 2028-04-11 | 9048 |  | 3016
T6-L09-T | T6 | L09 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 466 | 472 | 466 | 472 | 0 | 2028-04-28 | 2028-05-04 | 24012 |  | 4002
T6-L09-A | T6 | L09 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 474 | 479 | 474 | 479 | 0 | 2028-05-08 | 2028-05-12 | 10245.56 |  | 2049.112
T6-L09-D | T6 | L09 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 479 | 482 | 479 | 482 | 0 | 2028-05-13 | 2028-05-16 | 5796 |  | 1932
T6-L10-M | T6 | L10 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 433 | 438 | 433 | 438 | 0 | 2028-03-21 | 2028-03-25 | 12204.27 |  | 2440.854
T6-L10-P | T6 | L10 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 441 | 447 | 441 | 447 | 0 | 2028-03-30 | 2028-04-05 | 15067 |  | 2511.1667
T6-L10-S | T6 | L10 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 449 | 452 | 449 | 452 | 0 | 2028-04-08 | 2028-04-11 | 9048 |  | 3016
T6-L10-T | T6 | L10 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 466 | 472 | 466 | 472 | 0 | 2028-04-28 | 2028-05-04 | 24012 |  | 4002
T6-L10-A | T6 | L10 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 474 | 479 | 474 | 479 | 0 | 2028-05-08 | 2028-05-12 | 10245.56 |  | 2049.112
T6-L10-D | T6 | L10 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 479 | 482 | 479 | 482 | 0 | 2028-05-13 | 2028-05-16 | 5796 |  | 1932
T6-L11-M | T6 | L11 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 433 | 438 | 433 | 438 | 0 | 2028-03-21 | 2028-03-25 | 12204.27 |  | 2440.854
T6-L11-P | T6 | L11 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 441 | 447 | 441 | 447 | 0 | 2028-03-30 | 2028-04-05 | 15067 |  | 2511.1667
T6-L11-S | T6 | L11 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 449 | 452 | 449 | 452 | 0 | 2028-04-08 | 2028-04-11 | 9048 |  | 3016
T6-L11-T | T6 | L11 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 466 | 472 | 466 | 472 | 0 | 2028-04-28 | 2028-05-04 | 24012 |  | 4002
T6-L11-A | T6 | L11 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 474 | 479 | 474 | 479 | 0 | 2028-05-08 | 2028-05-12 | 10245.56 |  | 2049.112
T6-L11-D | T6 | L11 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 479 | 482 | 479 | 482 | 0 | 2028-05-13 | 2028-05-16 | 5796 |  | 1932
T6-L12-M | T6 | L12 | Partition masonry | Masonry | 90.402 | m3 | 22 | 10 | 5 | 433 | 438 | 433 | 438 | 0 | 2028-03-21 | 2028-03-25 | 12204.27 |  | 2440.854
T6-L12-P | T6 | L12 | Internal plaster | Finishes | 1205.36 | m2 | 220 | 10 | 6 | 441 | 447 | 441 | 447 | 0 | 2028-03-30 | 2028-04-05 | 15067 |  | 2511.1667
T6-L12-S | T6 | L12 | Screed and substrate preparation | Finishes | 696 | m2 | 240 | 8 | 3 | 449 | 452 | 449 | 452 | 0 | 2028-04-08 | 2028-04-11 | 9048 |  | 3016
T6-L12-T | T6 | L12 | Floor finishes and skirtings | Finishes | 696 | m2 | 130 | 8 | 6 | 466 | 472 | 466 | 472 | 0 | 2028-04-28 | 2028-05-04 | 24012 |  | 4002
T6-L12-A | T6 | L12 | Paint and final decorations | Finishes | 1205.36 | m2 | 270 | 8 | 5 | 474 | 479 | 474 | 479 | 0 | 2028-05-08 | 2028-05-12 | 10245.56 |  | 2049.112
T6-L12-D | T6 | L12 | Door sets and ironmongery | Finishes | 28 | nr | 10 | 4 | 3 | 479 | 482 | 479 | 482 | 0 | 2028-05-13 | 2028-05-16 | 5796 |  | 1932
X-010 | SITE | EXT | Stormwater pipes and chambers | External | 960 | m | 55 | 12 | 18 | 163 | 181 | 441 | 459 | 278 | 2027-05-11 | 2027-05-31 | 76800 |  | 4266.6667
X-020 | SITE | EXT | External paving and final levels | External | 4500 | m2 | 200 | 16 | 23 | 428 | 451 | 459 | 482 | 31 | 2028-03-15 | 2028-04-10 | 171000 |  | 7434.7826
PC-001 | PROJECT | ALL | Inspection, snagging and handover | Site | 1 | lot | 1 | 24 | 20 | 482 | 502 | 482 | 502 | 0 | 2028-05-17 | 2028-06-08 | 0 | 20 | 0
Formulas:
Start date = INDEX('Calendar'!$C8:C907,[ES offset]+1)
Finish date = INDEX('Calendar'!$C8:C907,MAX([ES offset]+1,[EF offset]))

## Logic register
Predecessor and successor register
Each link is checked against the recalculated forward pass.
Predecessor | Successor | Type | Lag wd | Pred finish | Succ start | Logic gap wd | Basis
P-001 | P-010 | FS | 0 | 18 | 18 | 0 | Explicit working-day lag
P-010 | P-020 | FS | 0 | 57 | 57 | 0 | Explicit working-day lag
P-020 | P-030 | FS | 0 | 66 | 66 | 0 | Explicit working-day lag
P-030 | P-040 | FS | 0 | 109 | 109 | 0 | Explicit working-day lag
P-040 | P-050 | FS | 7 | 127 | 134 | 0 | Explicit working-day lag
P-050 | P-060 | FS | 0 | 147 | 147 | 0 | Explicit working-day lag
P-050 | P-070 | FS | 7 | 147 | 154 | 0 | Explicit working-day lag
P-040 | T1-L00-F | FS | 7 | 127 | 134 | 0 | Explicit working-day lag
T1-L00-F | T1-L00-R | FS | 0 | 140 | 140 | 0 | Explicit working-day lag
T1-L00-R | T1-L00-C | FS | 0 | 145 | 145 | 0 | Explicit working-day lag
T1-L00-C | T1-L00-H | FS | 0 | 147 | 147 | 0 | Explicit working-day lag
T1-L00-H | T1-L01-F | FS | 0 | 152 | 152 | 0 | Explicit working-day lag
T1-L01-F | T1-L01-R | FS | 0 | 158 | 158 | 0 | Explicit working-day lag
T1-L01-R | T1-L01-C | FS | 0 | 163 | 163 | 0 | Explicit working-day lag
T1-L01-C | T1-L01-H | FS | 0 | 165 | 165 | 0 | Explicit working-day lag
T1-L01-H | T1-L02-F | FS | 0 | 170 | 170 | 0 | Explicit working-day lag
T1-L02-F | T1-L02-R | FS | 0 | 176 | 176 | 0 | Explicit working-day lag
T1-L02-R | T1-L02-C | FS | 0 | 181 | 181 | 0 | Explicit working-day lag
T1-L02-C | T1-L02-H | FS | 0 | 183 | 183 | 0 | Explicit working-day lag
T1-L02-H | T1-L03-F | FS | 0 | 188 | 188 | 0 | Explicit working-day lag
T1-L03-F | T1-L03-R | FS | 0 | 194 | 194 | 0 | Explicit working-day lag
T1-L03-R | T1-L03-C | FS | 0 | 199 | 199 | 0 | Explicit working-day lag
T1-L03-C | T1-L03-H | FS | 0 | 201 | 201 | 0 | Explicit working-day lag
T1-L03-H | T1-L04-F | FS | 0 | 206 | 206 | 0 | Explicit working-day lag
T1-L04-F | T1-L04-R | FS | 0 | 212 | 212 | 0 | Explicit working-day lag
T1-L04-R | T1-L04-C | FS | 0 | 217 | 217 | 0 | Explicit working-day lag
T1-L04-C | T1-L04-H | FS | 0 | 219 | 219 | 0 | Explicit working-day lag
T1-L04-H | T1-L05-F | FS | 0 | 224 | 224 | 0 | Explicit working-day lag
T1-L05-F | T1-L05-R | FS | 0 | 230 | 230 | 0 | Explicit working-day lag
T1-L05-R | T1-L05-C | FS | 0 | 235 | 235 | 0 | Explicit working-day lag
T1-L05-C | T1-L05-H | FS | 0 | 237 | 237 | 0 | Explicit working-day lag
T1-L05-H | T1-L06-F | FS | 0 | 242 | 242 | 0 | Explicit working-day lag
T1-L06-F | T1-L06-R | FS | 0 | 248 | 248 | 0 | Explicit working-day lag
T1-L06-R | T1-L06-C | FS | 0 | 253 | 253 | 0 | Explicit working-day lag
T1-L06-C | T1-L06-H | FS | 0 | 255 | 255 | 0 | Explicit working-day lag
T1-L06-H | T1-L07-F | FS | 0 | 260 | 260 | 0 | Explicit working-day lag
T1-L07-F | T1-L07-R | FS | 0 | 266 | 266 | 0 | Explicit working-day lag
T1-L07-R | T1-L07-C | FS | 0 | 271 | 271 | 0 | Explicit working-day lag
T1-L07-C | T1-L07-H | FS | 0 | 273 | 273 | 0 | Explicit working-day lag
T1-L07-H | T1-L08-F | FS | 0 | 278 | 278 | 0 | Explicit working-day lag
T1-L08-F | T1-L08-R | FS | 0 | 284 | 284 | 0 | Explicit working-day lag
T1-L08-R | T1-L08-C | FS | 0 | 289 | 289 | 0 | Explicit working-day lag
T1-L08-C | T1-L08-H | FS | 0 | 291 | 291 | 0 | Explicit working-day lag
T1-L08-H | T1-L09-F | FS | 0 | 296 | 296 | 0 | Explicit working-day lag
T1-L09-F | T1-L09-R | FS | 0 | 302 | 302 | 0 | Explicit working-day lag
T1-L09-R | T1-L09-C | FS | 0 | 307 | 307 | 0 | Explicit working-day lag
T1-L09-C | T1-L09-H | FS | 0 | 309 | 309 | 0 | Explicit working-day lag
T1-L09-H | T1-L10-F | FS | 0 | 314 | 314 | 0 | Explicit working-day lag
T1-L10-F | T1-L10-R | FS | 0 | 320 | 320 | 0 | Explicit working-day lag
T1-L10-R | T1-L10-C | FS | 0 | 325 | 325 | 0 | Explicit working-day lag
T1-L10-C | T1-L10-H | FS | 0 | 327 | 327 | 0 | Explicit working-day lag
T1-L10-H | T1-L11-F | FS | 0 | 332 | 332 | 0 | Explicit working-day lag
T1-L11-F | T1-L11-R | FS | 0 | 338 | 338 | 0 | Explicit working-day lag
T1-L11-R | T1-L11-C | FS | 0 | 343 | 343 | 0 | Explicit working-day lag
T1-L11-C | T1-L11-H | FS | 0 | 345 | 345 | 0 | Explicit working-day lag
T1-L11-H | T1-L12-F | FS | 0 | 350 | 350 | 0 | Explicit working-day lag
T1-L12-F | T1-L12-R | FS | 0 | 356 | 356 | 0 | Explicit working-day lag
T1-L12-R | T1-L12-C | FS | 0 | 361 | 361 | 0 | Explicit working-day lag
T1-L12-C | T1-L12-H | FS | 0 | 363 | 363 | 0 | Explicit working-day lag
T1-L12-H | T1-RF | FS | 5 | 368 | 373 | 0 | Explicit working-day lag
T1-L08-H | T1-FA | FS | 10 | 296 | 306 | 0 | Explicit working-day lag
T1-FA | T1-GL | FS | 0 | 328 | 387 | 59 | Explicit working-day lag
T1-RF | T1-GL | FS | 0 | 387 | 387 | 0 | Explicit working-day lag
T1-L03-H | T1-L00-M | FS | 5 | 206 | 211 | 0 | Explicit working-day lag
T1-L00-M | T1-L00-P | FS | 3 | 216 | 219 | 0 | Explicit working-day lag
T1-L00-P | T1-L00-S | FS | 2 | 225 | 227 | 0 | Explicit working-day lag
T1-L00-S | T1-L00-T | FS | 14 | 230 | 401 | 157 | Explicit working-day lag
T1-GL | T1-L00-T | FS | 0 | 401 | 401 | 0 | Explicit working-day lag
T1-L00-T | T1-L00-A | FS | 2 | 407 | 409 | 0 | Explicit working-day lag
T1-L00-A | T1-L00-D | FS | 0 | 414 | 414 | 0 | Explicit working-day lag
T1-L04-H | T1-L01-M | FS | 5 | 224 | 229 | 0 | Explicit working-day lag
T1-L01-M | T1-L01-P | FS | 3 | 234 | 237 | 0 | Explicit working-day lag
T1-L01-P | T1-L01-S | FS | 2 | 243 | 245 | 0 | Explicit working-day lag
T1-L01-S | T1-L01-T | FS | 14 | 248 | 401 | 139 | Explicit working-day lag
T1-GL | T1-L01-T | FS | 0 | 401 | 401 | 0 | Explicit working-day lag
T1-L01-T | T1-L01-A | FS | 2 | 407 | 409 | 0 | Explicit working-day lag
T1-L01-A | T1-L01-D | FS | 0 | 414 | 414 | 0 | Explicit working-day lag
T1-L05-H | T1-L02-M | FS | 5 | 242 | 247 | 0 | Explicit working-day lag
T1-L02-M | T1-L02-P | FS | 3 | 252 | 255 | 0 | Explicit working-day lag
T1-L02-P | T1-L02-S | FS | 2 | 261 | 263 | 0 | Explicit working-day lag
T1-L02-S | T1-L02-T | FS | 14 | 266 | 401 | 121 | Explicit working-day lag
T1-GL | T1-L02-T | FS | 0 | 401 | 401 | 0 | Explicit working-day lag
T1-L02-T | T1-L02-A | FS | 2 | 407 | 409 | 0 | Explicit working-day lag
T1-L02-A | T1-L02-D | FS | 0 | 414 | 414 | 0 | Explicit working-day lag
T1-L06-H | T1-L03-M | FS | 5 | 260 | 265 | 0 | Explicit working-day lag
T1-L03-M | T1-L03-P | FS | 3 | 270 | 273 | 0 | Explicit working-day lag
T1-L03-P | T1-L03-S | FS | 2 | 279 | 281 | 0 | Explicit working-day lag
T1-L03-S | T1-L03-T | FS | 14 | 284 | 401 | 103 | Explicit working-day lag
T1-GL | T1-L03-T | FS | 0 | 401 | 401 | 0 | Explicit working-day lag
T1-L03-T | T1-L03-A | FS | 2 | 407 | 409 | 0 | Explicit working-day lag
T1-L03-A | T1-L03-D | FS | 0 | 414 | 414 | 0 | Explicit working-day lag
T1-L07-H | T1-L04-M | FS | 5 | 278 | 283 | 0 | Explicit working-day lag
T1-L04-M | T1-L04-P | FS | 3 | 288 | 291 | 0 | Explicit working-day lag
T1-L04-P | T1-L04-S | FS | 2 | 297 | 299 | 0 | Explicit working-day lag
T1-L04-S | T1-L04-T | FS | 14 | 302 | 401 | 85 | Explicit working-day lag
T1-GL | T1-L04-T | FS | 0 | 401 | 401 | 0 | Explicit working-day lag
T1-L04-T | T1-L04-A | FS | 2 | 407 | 409 | 0 | Explicit working-day lag
T1-L04-A | T1-L04-D | FS | 0 | 414 | 414 | 0 | Explicit working-day lag
T1-L08-H | T1-L05-M | FS | 5 | 296 | 301 | 0 | Explicit working-day lag
T1-L05-M | T1-L05-P | FS | 3 | 306 | 309 | 0 | Explicit working-day lag
T1-L05-P | T1-L05-S | FS | 2 | 315 | 317 | 0 | Explicit working-day lag
T1-L05-S | T1-L05-T | FS | 14 | 320 | 401 | 67 | Explicit working-day lag
T1-GL | T1-L05-T | FS | 0 | 401 | 401 | 0 | Explicit working-day lag
T1-L05-T | T1-L05-A | FS | 2 | 407 | 409 | 0 | Explicit working-day lag
T1-L05-A | T1-L05-D | FS | 0 | 414 | 414 | 0 | Explicit working-day lag
T1-L09-H | T1-L06-M | FS | 5 | 314 | 319 | 0 | Explicit working-day lag
T1-L06-M | T1-L06-P | FS | 3 | 324 | 327 | 0 | Explicit working-day lag
T1-L06-P | T1-L06-S | FS | 2 | 333 | 335 | 0 | Explicit working-day lag
T1-L06-S | T1-L06-T | FS | 14 | 338 | 401 | 49 | Explicit working-day lag
T1-GL | T1-L06-T | FS | 0 | 401 | 401 | 0 | Explicit working-day lag
T1-L06-T | T1-L06-A | FS | 2 | 407 | 409 | 0 | Explicit working-day lag
T1-L06-A | T1-L06-D | FS | 0 | 414 | 414 | 0 | Explicit working-day lag
T1-L10-H | T1-L07-M | FS | 5 | 332 | 337 | 0 | Explicit working-day lag
T1-L07-M | T1-L07-P | FS | 3 | 342 | 345 | 0 | Explicit working-day lag
T1-L07-P | T1-L07-S | FS | 2 | 351 | 353 | 0 | Explicit working-day lag
T1-L07-S | T1-L07-T | FS | 14 | 356 | 401 | 31 | Explicit working-day lag
T1-GL | T1-L07-T | FS | 0 | 401 | 401 | 0 | Explicit working-day lag
T1-L07-T | T1-L07-A | FS | 2 | 407 | 409 | 0 | Explicit working-day lag
T1-L07-A | T1-L07-D | FS | 0 | 414 | 414 | 0 | Explicit working-day lag
T1-L11-H | T1-L08-M | FS | 5 | 350 | 355 | 0 | Explicit working-day lag
T1-L08-M | T1-L08-P | FS | 3 | 360 | 363 | 0 | Explicit working-day lag
T1-L08-P | T1-L08-S | FS | 2 | 369 | 371 | 0 | Explicit working-day lag
T1-L08-S | T1-L08-T | FS | 14 | 374 | 401 | 13 | Explicit working-day lag
T1-GL | T1-L08-T | FS | 0 | 401 | 401 | 0 | Explicit working-day lag
T1-L08-T | T1-L08-A | FS | 2 | 407 | 409 | 0 | Explicit working-day lag
T1-L08-A | T1-L08-D | FS | 0 | 414 | 414 | 0 | Explicit working-day lag
T1-L12-H | T1-L09-M | FS | 5 | 368 | 373 | 0 | Explicit working-day lag
T1-L09-M | T1-L09-P | FS | 3 | 378 | 381 | 0 | Explicit working-day lag
T1-L09-P | T1-L09-S | FS | 2 | 387 | 389 | 0 | Explicit working-day lag
T1-L09-S | T1-L09-T | FS | 14 | 392 | 406 | 0 | Explicit working-day lag
T1-GL | T1-L09-T | FS | 0 | 401 | 406 | 5 | Explicit working-day lag
T1-L09-T | T1-L09-A | FS | 2 | 412 | 414 | 0 | Explicit working-day lag
T1-L09-A | T1-L09-D | FS | 0 | 419 | 419 | 0 | Explicit working-day lag
T1-L12-H | T1-L10-M | FS | 5 | 368 | 373 | 0 | Explicit working-day lag
T1-L10-M | T1-L10-P | FS | 3 | 378 | 381 | 0 | Explicit working-day lag
T1-L10-P | T1-L10-S | FS | 2 | 387 | 389 | 0 | Explicit working-day lag
T1-L10-S | T1-L10-T | FS | 14 | 392 | 406 | 0 | Explicit working-day lag
T1-GL | T1-L10-T | FS | 0 | 401 | 406 | 5 | Explicit working-day lag
T1-L10-T | T1-L10-A | FS | 2 | 412 | 414 | 0 | Explicit working-day lag
T1-L10-A | T1-L10-D | FS | 0 | 419 | 419 | 0 | Explicit working-day lag
T1-L12-H | T1-L11-M | FS | 5 | 368 | 373 | 0 | Explicit working-day lag
T1-L11-M | T1-L11-P | FS | 3 | 378 | 381 | 0 | Explicit working-day lag
T1-L11-P | T1-L11-S | FS | 2 | 387 | 389 | 0 | Explicit working-day lag
T1-L11-S | T1-L11-T | FS | 14 | 392 | 406 | 0 | Explicit working-day lag
T1-GL | T1-L11-T | FS | 0 | 401 | 406 | 5 | Explicit working-day lag
T1-L11-T | T1-L11-A | FS | 2 | 412 | 414 | 0 | Explicit working-day lag
T1-L11-A | T1-L11-D | FS | 0 | 419 | 419 | 0 | Explicit working-day lag
T1-L12-H | T1-L12-M | FS | 5 | 368 | 373 | 0 | Explicit working-day lag
T1-L12-M | T1-L12-P | FS | 3 | 378 | 381 | 0 | Explicit working-day lag
T1-L12-P | T1-L12-S | FS | 2 | 387 | 389 | 0 | Explicit working-day lag
T1-L12-S | T1-L12-T | FS | 14 | 392 | 406 | 0 | Explicit working-day lag
T1-GL | T1-L12-T | FS | 0 | 401 | 406 | 5 | Explicit working-day lag
T1-L12-T | T1-L12-A | FS | 2 | 412 | 414 | 0 | Explicit working-day lag
T1-L12-A | T1-L12-D | FS | 0 | 419 | 419 | 0 | Explicit working-day lag
P-040 | T2-L00-F | FS | 19 | 127 | 146 | 0 | Explicit working-day lag
T2-L00-F | T2-L00-R | FS | 0 | 152 | 152 | 0 | Explicit working-day lag
T2-L00-R | T2-L00-C | FS | 0 | 157 | 157 | 0 | Explicit working-day lag
T2-L00-C | T2-L00-H | FS | 0 | 159 | 159 | 0 | Explicit working-day lag
T2-L00-H | T2-L01-F | FS | 0 | 164 | 164 | 0 | Explicit working-day lag
T2-L01-F | T2-L01-R | FS | 0 | 170 | 170 | 0 | Explicit working-day lag
T2-L01-R | T2-L01-C | FS | 0 | 175 | 175 | 0 | Explicit working-day lag
T2-L01-C | T2-L01-H | FS | 0 | 177 | 177 | 0 | Explicit working-day lag
T2-L01-H | T2-L02-F | FS | 0 | 182 | 182 | 0 | Explicit working-day lag
T2-L02-F | T2-L02-R | FS | 0 | 188 | 188 | 0 | Explicit working-day lag
T2-L02-R | T2-L02-C | FS | 0 | 193 | 193 | 0 | Explicit working-day lag
T2-L02-C | T2-L02-H | FS | 0 | 195 | 195 | 0 | Explicit working-day lag
T2-L02-H | T2-L03-F | FS | 0 | 200 | 200 | 0 | Explicit working-day lag
T2-L03-F | T2-L03-R | FS | 0 | 206 | 206 | 0 | Explicit working-day lag
T2-L03-R | T2-L03-C | FS | 0 | 211 | 211 | 0 | Explicit working-day lag
T2-L03-C | T2-L03-H | FS | 0 | 213 | 213 | 0 | Explicit working-day lag
T2-L03-H | T2-L04-F | FS | 0 | 218 | 218 | 0 | Explicit working-day lag
T2-L04-F | T2-L04-R | FS | 0 | 224 | 224 | 0 | Explicit working-day lag
T2-L04-R | T2-L04-C | FS | 0 | 229 | 229 | 0 | Explicit working-day lag
T2-L04-C | T2-L04-H | FS | 0 | 231 | 231 | 0 | Explicit working-day lag
T2-L04-H | T2-L05-F | FS | 0 | 236 | 236 | 0 | Explicit working-day lag
T2-L05-F | T2-L05-R | FS | 0 | 242 | 242 | 0 | Explicit working-day lag
T2-L05-R | T2-L05-C | FS | 0 | 247 | 247 | 0 | Explicit working-day lag
T2-L05-C | T2-L05-H | FS | 0 | 249 | 249 | 0 | Explicit working-day lag
T2-L05-H | T2-L06-F | FS | 0 | 254 | 254 | 0 | Explicit working-day lag
T2-L06-F | T2-L06-R | FS | 0 | 260 | 260 | 0 | Explicit working-day lag
T2-L06-R | T2-L06-C | FS | 0 | 265 | 265 | 0 | Explicit working-day lag
T2-L06-C | T2-L06-H | FS | 0 | 267 | 267 | 0 | Explicit working-day lag
T2-L06-H | T2-L07-F | FS | 0 | 272 | 272 | 0 | Explicit working-day lag
T2-L07-F | T2-L07-R | FS | 0 | 278 | 278 | 0 | Explicit working-day lag
T2-L07-R | T2-L07-C | FS | 0 | 283 | 283 | 0 | Explicit working-day lag
T2-L07-C | T2-L07-H | FS | 0 | 285 | 285 | 0 | Explicit working-day lag
T2-L07-H | T2-L08-F | FS | 0 | 290 | 290 | 0 | Explicit working-day lag
T2-L08-F | T2-L08-R | FS | 0 | 296 | 296 | 0 | Explicit working-day lag
T2-L08-R | T2-L08-C | FS | 0 | 301 | 301 | 0 | Explicit working-day lag
T2-L08-C | T2-L08-H | FS | 0 | 303 | 303 | 0 | Explicit working-day lag
T2-L08-H | T2-L09-F | FS | 0 | 308 | 308 | 0 | Explicit working-day lag
T2-L09-F | T2-L09-R | FS | 0 | 314 | 314 | 0 | Explicit working-day lag
T2-L09-R | T2-L09-C | FS | 0 | 319 | 319 | 0 | Explicit working-day lag
T2-L09-C | T2-L09-H | FS | 0 | 321 | 321 | 0 | Explicit working-day lag
T2-L09-H | T2-L10-F | FS | 0 | 326 | 326 | 0 | Explicit working-day lag
T2-L10-F | T2-L10-R | FS | 0 | 332 | 332 | 0 | Explicit working-day lag
T2-L10-R | T2-L10-C | FS | 0 | 337 | 337 | 0 | Explicit working-day lag
T2-L10-C | T2-L10-H | FS | 0 | 339 | 339 | 0 | Explicit working-day lag
T2-L10-H | T2-L11-F | FS | 0 | 344 | 344 | 0 | Explicit working-day lag
T2-L11-F | T2-L11-R | FS | 0 | 350 | 350 | 0 | Explicit working-day lag
T2-L11-R | T2-L11-C | FS | 0 | 355 | 355 | 0 | Explicit working-day lag
T2-L11-C | T2-L11-H | FS | 0 | 357 | 357 | 0 | Explicit working-day lag
T2-L11-H | T2-L12-F | FS | 0 | 362 | 362 | 0 | Explicit working-day lag
T2-L12-F | T2-L12-R | FS | 0 | 368 | 368 | 0 | Explicit working-day lag
T2-L12-R | T2-L12-C | FS | 0 | 373 | 373 | 0 | Explicit working-day lag
T2-L12-C | T2-L12-H | FS | 0 | 375 | 375 | 0 | Explicit working-day lag
T2-L12-H | T2-RF | FS | 5 | 380 | 385 | 0 | Explicit working-day lag
T2-L08-H | T2-FA | FS | 10 | 308 | 318 | 0 | Explicit working-day lag
T2-FA | T2-GL | FS | 0 | 340 | 399 | 59 | Explicit working-day lag
T2-RF | T2-GL | FS | 0 | 399 | 399 | 0 | Explicit working-day lag
T2-L03-H | T2-L00-M | FS | 5 | 218 | 223 | 0 | Explicit working-day lag
T2-L00-M | T2-L00-P | FS | 3 | 228 | 231 | 0 | Explicit working-day lag
T2-L00-P | T2-L00-S | FS | 2 | 237 | 239 | 0 | Explicit working-day lag
T2-L00-S | T2-L00-T | FS | 14 | 242 | 413 | 157 | Explicit working-day lag
T2-GL | T2-L00-T | FS | 0 | 413 | 413 | 0 | Explicit working-day lag
T2-L00-T | T2-L00-A | FS | 2 | 419 | 421 | 0 | Explicit working-day lag
T2-L00-A | T2-L00-D | FS | 0 | 426 | 426 | 0 | Explicit working-day lag
T2-L04-H | T2-L01-M | FS | 5 | 236 | 241 | 0 | Explicit working-day lag
T2-L01-M | T2-L01-P | FS | 3 | 246 | 249 | 0 | Explicit working-day lag
T2-L01-P | T2-L01-S | FS | 2 | 255 | 257 | 0 | Explicit working-day lag
T2-L01-S | T2-L01-T | FS | 14 | 260 | 413 | 139 | Explicit working-day lag
T2-GL | T2-L01-T | FS | 0 | 413 | 413 | 0 | Explicit working-day lag
T2-L01-T | T2-L01-A | FS | 2 | 419 | 421 | 0 | Explicit working-day lag
T2-L01-A | T2-L01-D | FS | 0 | 426 | 426 | 0 | Explicit working-day lag
T2-L05-H | T2-L02-M | FS | 5 | 254 | 259 | 0 | Explicit working-day lag
T2-L02-M | T2-L02-P | FS | 3 | 264 | 267 | 0 | Explicit working-day lag
T2-L02-P | T2-L02-S | FS | 2 | 273 | 275 | 0 | Explicit working-day lag
T2-L02-S | T2-L02-T | FS | 14 | 278 | 413 | 121 | Explicit working-day lag
T2-GL | T2-L02-T | FS | 0 | 413 | 413 | 0 | Explicit working-day lag
T2-L02-T | T2-L02-A | FS | 2 | 419 | 421 | 0 | Explicit working-day lag
T2-L02-A | T2-L02-D | FS | 0 | 426 | 426 | 0 | Explicit working-day lag
T2-L06-H | T2-L03-M | FS | 5 | 272 | 277 | 0 | Explicit working-day lag
T2-L03-M | T2-L03-P | FS | 3 | 282 | 285 | 0 | Explicit working-day lag
T2-L03-P | T2-L03-S | FS | 2 | 291 | 293 | 0 | Explicit working-day lag
T2-L03-S | T2-L03-T | FS | 14 | 296 | 413 | 103 | Explicit working-day lag
T2-GL | T2-L03-T | FS | 0 | 413 | 413 | 0 | Explicit working-day lag
T2-L03-T | T2-L03-A | FS | 2 | 419 | 421 | 0 | Explicit working-day lag
T2-L03-A | T2-L03-D | FS | 0 | 426 | 426 | 0 | Explicit working-day lag
T2-L07-H | T2-L04-M | FS | 5 | 290 | 295 | 0 | Explicit working-day lag
T2-L04-M | T2-L04-P | FS | 3 | 300 | 303 | 0 | Explicit working-day lag
T2-L04-P | T2-L04-S | FS | 2 | 309 | 311 | 0 | Explicit working-day lag
T2-L04-S | T2-L04-T | FS | 14 | 314 | 413 | 85 | Explicit working-day lag
T2-GL | T2-L04-T | FS | 0 | 413 | 413 | 0 | Explicit working-day lag
T2-L04-T | T2-L04-A | FS | 2 | 419 | 421 | 0 | Explicit working-day lag
T2-L04-A | T2-L04-D | FS | 0 | 426 | 426 | 0 | Explicit working-day lag
T2-L08-H | T2-L05-M | FS | 5 | 308 | 313 | 0 | Explicit working-day lag
T2-L05-M | T2-L05-P | FS | 3 | 318 | 321 | 0 | Explicit working-day lag
T2-L05-P | T2-L05-S | FS | 2 | 327 | 329 | 0 | Explicit working-day lag
T2-L05-S | T2-L05-T | FS | 14 | 332 | 413 | 67 | Explicit working-day lag
T2-GL | T2-L05-T | FS | 0 | 413 | 413 | 0 | Explicit working-day lag
T2-L05-T | T2-L05-A | FS | 2 | 419 | 421 | 0 | Explicit working-day lag
T2-L05-A | T2-L05-D | FS | 0 | 426 | 426 | 0 | Explicit working-day lag
T2-L09-H | T2-L06-M | FS | 5 | 326 | 331 | 0 | Explicit working-day lag
T2-L06-M | T2-L06-P | FS | 3 | 336 | 339 | 0 | Explicit working-day lag
T2-L06-P | T2-L06-S | FS | 2 | 345 | 347 | 0 | Explicit working-day lag
T2-L06-S | T2-L06-T | FS | 14 | 350 | 413 | 49 | Explicit working-day lag
T2-GL | T2-L06-T | FS | 0 | 413 | 413 | 0 | Explicit working-day lag
T2-L06-T | T2-L06-A | FS | 2 | 419 | 421 | 0 | Explicit working-day lag
T2-L06-A | T2-L06-D | FS | 0 | 426 | 426 | 0 | Explicit working-day lag
T2-L10-H | T2-L07-M | FS | 5 | 344 | 349 | 0 | Explicit working-day lag
T2-L07-M | T2-L07-P | FS | 3 | 354 | 357 | 0 | Explicit working-day lag
T2-L07-P | T2-L07-S | FS | 2 | 363 | 365 | 0 | Explicit working-day lag
T2-L07-S | T2-L07-T | FS | 14 | 368 | 413 | 31 | Explicit working-day lag
T2-GL | T2-L07-T | FS | 0 | 413 | 413 | 0 | Explicit working-day lag
T2-L07-T | T2-L07-A | FS | 2 | 419 | 421 | 0 | Explicit working-day lag
T2-L07-A | T2-L07-D | FS | 0 | 426 | 426 | 0 | Explicit working-day lag
T2-L11-H | T2-L08-M | FS | 5 | 362 | 367 | 0 | Explicit working-day lag
T2-L08-M | T2-L08-P | FS | 3 | 372 | 375 | 0 | Explicit working-day lag
T2-L08-P | T2-L08-S | FS | 2 | 381 | 383 | 0 | Explicit working-day lag
T2-L08-S | T2-L08-T | FS | 14 | 386 | 413 | 13 | Explicit working-day lag
T2-GL | T2-L08-T | FS | 0 | 413 | 413 | 0 | Explicit working-day lag
T2-L08-T | T2-L08-A | FS | 2 | 419 | 421 | 0 | Explicit working-day lag
T2-L08-A | T2-L08-D | FS | 0 | 426 | 426 | 0 | Explicit working-day lag
T2-L12-H | T2-L09-M | FS | 5 | 380 | 385 | 0 | Explicit working-day lag
T2-L09-M | T2-L09-P | FS | 3 | 390 | 393 | 0 | Explicit working-day lag
T2-L09-P | T2-L09-S | FS | 2 | 399 | 401 | 0 | Explicit working-day lag
T2-L09-S | T2-L09-T | FS | 14 | 404 | 418 | 0 | Explicit working-day lag
T2-GL | T2-L09-T | FS | 0 | 413 | 418 | 5 | Explicit working-day lag
T2-L09-T | T2-L09-A | FS | 2 | 424 | 426 | 0 | Explicit working-day lag
T2-L09-A | T2-L09-D | FS | 0 | 431 | 431 | 0 | Explicit working-day lag
T2-L12-H | T2-L10-M | FS | 5 | 380 | 385 | 0 | Explicit working-day lag
T2-L10-M | T2-L10-P | FS | 3 | 390 | 393 | 0 | Explicit working-day lag
T2-L10-P | T2-L10-S | FS | 2 | 399 | 401 | 0 | Explicit working-day lag
T2-L10-S | T2-L10-T | FS | 14 | 404 | 418 | 0 | Explicit working-day lag
T2-GL | T2-L10-T | FS | 0 | 413 | 418 | 5 | Explicit working-day lag
T2-L10-T | T2-L10-A | FS | 2 | 424 | 426 | 0 | Explicit working-day lag
T2-L10-A | T2-L10-D | FS | 0 | 431 | 431 | 0 | Explicit working-day lag
T2-L12-H | T2-L11-M | FS | 5 | 380 | 385 | 0 | Explicit working-day lag
T2-L11-M | T2-L11-P | FS | 3 | 390 | 393 | 0 | Explicit working-day lag
T2-L11-P | T2-L11-S | FS | 2 | 399 | 401 | 0 | Explicit working-day lag
T2-L11-S | T2-L11-T | FS | 14 | 404 | 418 | 0 | Explicit working-day lag
T2-GL | T2-L11-T | FS | 0 | 413 | 418 | 5 | Explicit working-day lag
T2-L11-T | T2-L11-A | FS | 2 | 424 | 426 | 0 | Explicit working-day lag
T2-L11-A | T2-L11-D | FS | 0 | 431 | 431 | 0 | Explicit working-day lag
T2-L12-H | T2-L12-M | FS | 5 | 380 | 385 | 0 | Explicit working-day lag
T2-L12-M | T2-L12-P | FS | 3 | 390 | 393 | 0 | Explicit working-day lag
T2-L12-P | T2-L12-S | FS | 2 | 399 | 401 | 0 | Explicit working-day lag
T2-L12-S | T2-L12-T | FS | 14 | 404 | 418 | 0 | Explicit working-day lag
T2-GL | T2-L12-T | FS | 0 | 413 | 418 | 5 | Explicit working-day lag
T2-L12-T | T2-L12-A | FS | 2 | 424 | 426 | 0 | Explicit working-day lag
T2-L12-A | T2-L12-D | FS | 0 | 431 | 431 | 0 | Explicit working-day lag
P-040 | T3-L00-F | FS | 31 | 127 | 158 | 0 | Explicit working-day lag
T3-L00-F | T3-L00-R | FS | 0 | 164 | 164 | 0 | Explicit working-day lag
T3-L00-R | T3-L00-C | FS | 0 | 169 | 169 | 0 | Explicit working-day lag
T3-L00-C | T3-L00-H | FS | 0 | 171 | 171 | 0 | Explicit working-day lag
T3-L00-H | T3-L01-F | FS | 0 | 176 | 176 | 0 | Explicit working-day lag
T3-L01-F | T3-L01-R | FS | 0 | 182 | 182 | 0 | Explicit working-day lag
T3-L01-R | T3-L01-C | FS | 0 | 187 | 187 | 0 | Explicit working-day lag
T3-L01-C | T3-L01-H | FS | 0 | 189 | 189 | 0 | Explicit working-day lag
T3-L01-H | T3-L02-F | FS | 0 | 194 | 194 | 0 | Explicit working-day lag
T3-L02-F | T3-L02-R | FS | 0 | 200 | 200 | 0 | Explicit working-day lag
T3-L02-R | T3-L02-C | FS | 0 | 205 | 205 | 0 | Explicit working-day lag
T3-L02-C | T3-L02-H | FS | 0 | 207 | 207 | 0 | Explicit working-day lag
T3-L02-H | T3-L03-F | FS | 0 | 212 | 212 | 0 | Explicit working-day lag
T3-L03-F | T3-L03-R | FS | 0 | 218 | 218 | 0 | Explicit working-day lag
T3-L03-R | T3-L03-C | FS | 0 | 223 | 223 | 0 | Explicit working-day lag
T3-L03-C | T3-L03-H | FS | 0 | 225 | 225 | 0 | Explicit working-day lag
T3-L03-H | T3-L04-F | FS | 0 | 230 | 230 | 0 | Explicit working-day lag
T3-L04-F | T3-L04-R | FS | 0 | 236 | 236 | 0 | Explicit working-day lag
T3-L04-R | T3-L04-C | FS | 0 | 241 | 241 | 0 | Explicit working-day lag
T3-L04-C | T3-L04-H | FS | 0 | 243 | 243 | 0 | Explicit working-day lag
T3-L04-H | T3-L05-F | FS | 0 | 248 | 248 | 0 | Explicit working-day lag
T3-L05-F | T3-L05-R | FS | 0 | 254 | 254 | 0 | Explicit working-day lag
T3-L05-R | T3-L05-C | FS | 0 | 259 | 259 | 0 | Explicit working-day lag
T3-L05-C | T3-L05-H | FS | 0 | 261 | 261 | 0 | Explicit working-day lag
T3-L05-H | T3-L06-F | FS | 0 | 266 | 266 | 0 | Explicit working-day lag
T3-L06-F | T3-L06-R | FS | 0 | 272 | 272 | 0 | Explicit working-day lag
T3-L06-R | T3-L06-C | FS | 0 | 277 | 277 | 0 | Explicit working-day lag
T3-L06-C | T3-L06-H | FS | 0 | 279 | 279 | 0 | Explicit working-day lag
T3-L06-H | T3-L07-F | FS | 0 | 284 | 284 | 0 | Explicit working-day lag
T3-L07-F | T3-L07-R | FS | 0 | 290 | 290 | 0 | Explicit working-day lag
T3-L07-R | T3-L07-C | FS | 0 | 295 | 295 | 0 | Explicit working-day lag
T3-L07-C | T3-L07-H | FS | 0 | 297 | 297 | 0 | Explicit working-day lag
T3-L07-H | T3-L08-F | FS | 0 | 302 | 302 | 0 | Explicit working-day lag
T3-L08-F | T3-L08-R | FS | 0 | 308 | 308 | 0 | Explicit working-day lag
T3-L08-R | T3-L08-C | FS | 0 | 313 | 313 | 0 | Explicit working-day lag
T3-L08-C | T3-L08-H | FS | 0 | 315 | 315 | 0 | Explicit working-day lag
T3-L08-H | T3-L09-F | FS | 0 | 320 | 320 | 0 | Explicit working-day lag
T3-L09-F | T3-L09-R | FS | 0 | 326 | 326 | 0 | Explicit working-day lag
T3-L09-R | T3-L09-C | FS | 0 | 331 | 331 | 0 | Explicit working-day lag
T3-L09-C | T3-L09-H | FS | 0 | 333 | 333 | 0 | Explicit working-day lag
T3-L09-H | T3-L10-F | FS | 0 | 338 | 338 | 0 | Explicit working-day lag
T3-L10-F | T3-L10-R | FS | 0 | 344 | 344 | 0 | Explicit working-day lag
T3-L10-R | T3-L10-C | FS | 0 | 349 | 349 | 0 | Explicit working-day lag
T3-L10-C | T3-L10-H | FS | 0 | 351 | 351 | 0 | Explicit working-day lag
T3-L10-H | T3-L11-F | FS | 0 | 356 | 356 | 0 | Explicit working-day lag
T3-L11-F | T3-L11-R | FS | 0 | 362 | 362 | 0 | Explicit working-day lag
T3-L11-R | T3-L11-C | FS | 0 | 367 | 367 | 0 | Explicit working-day lag
T3-L11-C | T3-L11-H | FS | 0 | 369 | 369 | 0 | Explicit working-day lag
T3-L11-H | T3-L12-F | FS | 0 | 374 | 374 | 0 | Explicit working-day lag
T3-L12-F | T3-L12-R | FS | 0 | 380 | 380 | 0 | Explicit working-day lag
T3-L12-R | T3-L12-C | FS | 0 | 385 | 385 | 0 | Explicit working-day lag
T3-L12-C | T3-L12-H | FS | 0 | 387 | 387 | 0 | Explicit working-day lag
T3-L12-H | T3-RF | FS | 5 | 392 | 397 | 0 | Explicit working-day lag
T3-L08-H | T3-FA | FS | 10 | 320 | 330 | 0 | Explicit working-day lag
T3-FA | T3-GL | FS | 0 | 352 | 411 | 59 | Explicit working-day lag
T3-RF | T3-GL | FS | 0 | 411 | 411 | 0 | Explicit working-day lag
T3-L03-H | T3-L00-M | FS | 5 | 230 | 235 | 0 | Explicit working-day lag
T3-L00-M | T3-L00-P | FS | 3 | 240 | 243 | 0 | Explicit working-day lag
T3-L00-P | T3-L00-S | FS | 2 | 249 | 251 | 0 | Explicit working-day lag
T3-L00-S | T3-L00-T | FS | 14 | 254 | 425 | 157 | Explicit working-day lag
T3-GL | T3-L00-T | FS | 0 | 425 | 425 | 0 | Explicit working-day lag
T3-L00-T | T3-L00-A | FS | 2 | 431 | 433 | 0 | Explicit working-day lag
T3-L00-A | T3-L00-D | FS | 0 | 438 | 438 | 0 | Explicit working-day lag
T3-L04-H | T3-L01-M | FS | 5 | 248 | 253 | 0 | Explicit working-day lag
T3-L01-M | T3-L01-P | FS | 3 | 258 | 261 | 0 | Explicit working-day lag
T3-L01-P | T3-L01-S | FS | 2 | 267 | 269 | 0 | Explicit working-day lag
T3-L01-S | T3-L01-T | FS | 14 | 272 | 425 | 139 | Explicit working-day lag
T3-GL | T3-L01-T | FS | 0 | 425 | 425 | 0 | Explicit working-day lag
T3-L01-T | T3-L01-A | FS | 2 | 431 | 433 | 0 | Explicit working-day lag
T3-L01-A | T3-L01-D | FS | 0 | 438 | 438 | 0 | Explicit working-day lag
T3-L05-H | T3-L02-M | FS | 5 | 266 | 271 | 0 | Explicit working-day lag
T3-L02-M | T3-L02-P | FS | 3 | 276 | 279 | 0 | Explicit working-day lag
T3-L02-P | T3-L02-S | FS | 2 | 285 | 287 | 0 | Explicit working-day lag
T3-L02-S | T3-L02-T | FS | 14 | 290 | 425 | 121 | Explicit working-day lag
T3-GL | T3-L02-T | FS | 0 | 425 | 425 | 0 | Explicit working-day lag
T3-L02-T | T3-L02-A | FS | 2 | 431 | 433 | 0 | Explicit working-day lag
T3-L02-A | T3-L02-D | FS | 0 | 438 | 438 | 0 | Explicit working-day lag
T3-L06-H | T3-L03-M | FS | 5 | 284 | 289 | 0 | Explicit working-day lag
T3-L03-M | T3-L03-P | FS | 3 | 294 | 297 | 0 | Explicit working-day lag
T3-L03-P | T3-L03-S | FS | 2 | 303 | 305 | 0 | Explicit working-day lag
T3-L03-S | T3-L03-T | FS | 14 | 308 | 425 | 103 | Explicit working-day lag
T3-GL | T3-L03-T | FS | 0 | 425 | 425 | 0 | Explicit working-day lag
T3-L03-T | T3-L03-A | FS | 2 | 431 | 433 | 0 | Explicit working-day lag
T3-L03-A | T3-L03-D | FS | 0 | 438 | 438 | 0 | Explicit working-day lag
T3-L07-H | T3-L04-M | FS | 5 | 302 | 307 | 0 | Explicit working-day lag
T3-L04-M | T3-L04-P | FS | 3 | 312 | 315 | 0 | Explicit working-day lag
T3-L04-P | T3-L04-S | FS | 2 | 321 | 323 | 0 | Explicit working-day lag
T3-L04-S | T3-L04-T | FS | 14 | 326 | 425 | 85 | Explicit working-day lag
T3-GL | T3-L04-T | FS | 0 | 425 | 425 | 0 | Explicit working-day lag
T3-L04-T | T3-L04-A | FS | 2 | 431 | 433 | 0 | Explicit working-day lag
T3-L04-A | T3-L04-D | FS | 0 | 438 | 438 | 0 | Explicit working-day lag
T3-L08-H | T3-L05-M | FS | 5 | 320 | 325 | 0 | Explicit working-day lag
T3-L05-M | T3-L05-P | FS | 3 | 330 | 333 | 0 | Explicit working-day lag
T3-L05-P | T3-L05-S | FS | 2 | 339 | 341 | 0 | Explicit working-day lag
T3-L05-S | T3-L05-T | FS | 14 | 344 | 425 | 67 | Explicit working-day lag
T3-GL | T3-L05-T | FS | 0 | 425 | 425 | 0 | Explicit working-day lag
T3-L05-T | T3-L05-A | FS | 2 | 431 | 433 | 0 | Explicit working-day lag
T3-L05-A | T3-L05-D | FS | 0 | 438 | 438 | 0 | Explicit working-day lag
T3-L09-H | T3-L06-M | FS | 5 | 338 | 343 | 0 | Explicit working-day lag
T3-L06-M | T3-L06-P | FS | 3 | 348 | 351 | 0 | Explicit working-day lag
T3-L06-P | T3-L06-S | FS | 2 | 357 | 359 | 0 | Explicit working-day lag
T3-L06-S | T3-L06-T | FS | 14 | 362 | 425 | 49 | Explicit working-day lag
T3-GL | T3-L06-T | FS | 0 | 425 | 425 | 0 | Explicit working-day lag
T3-L06-T | T3-L06-A | FS | 2 | 431 | 433 | 0 | Explicit working-day lag
T3-L06-A | T3-L06-D | FS | 0 | 438 | 438 | 0 | Explicit working-day lag
T3-L10-H | T3-L07-M | FS | 5 | 356 | 361 | 0 | Explicit working-day lag
T3-L07-M | T3-L07-P | FS | 3 | 366 | 369 | 0 | Explicit working-day lag
T3-L07-P | T3-L07-S | FS | 2 | 375 | 377 | 0 | Explicit working-day lag
T3-L07-S | T3-L07-T | FS | 14 | 380 | 425 | 31 | Explicit working-day lag
T3-GL | T3-L07-T | FS | 0 | 425 | 425 | 0 | Explicit working-day lag
T3-L07-T | T3-L07-A | FS | 2 | 431 | 433 | 0 | Explicit working-day lag
T3-L07-A | T3-L07-D | FS | 0 | 438 | 438 | 0 | Explicit working-day lag
T3-L11-H | T3-L08-M | FS | 5 | 374 | 379 | 0 | Explicit working-day lag
T3-L08-M | T3-L08-P | FS | 3 | 384 | 387 | 0 | Explicit working-day lag
T3-L08-P | T3-L08-S | FS | 2 | 393 | 395 | 0 | Explicit working-day lag
T3-L08-S | T3-L08-T | FS | 14 | 398 | 425 | 13 | Explicit working-day lag
T3-GL | T3-L08-T | FS | 0 | 425 | 425 | 0 | Explicit working-day lag
T3-L08-T | T3-L08-A | FS | 2 | 431 | 433 | 0 | Explicit working-day lag
T3-L08-A | T3-L08-D | FS | 0 | 438 | 438 | 0 | Explicit working-day lag
T3-L12-H | T3-L09-M | FS | 5 | 392 | 397 | 0 | Explicit working-day lag
T3-L09-M | T3-L09-P | FS | 3 | 402 | 405 | 0 | Explicit working-day lag
T3-L09-P | T3-L09-S | FS | 2 | 411 | 413 | 0 | Explicit working-day lag
T3-L09-S | T3-L09-T | FS | 14 | 416 | 430 | 0 | Explicit working-day lag
T3-GL | T3-L09-T | FS | 0 | 425 | 430 | 5 | Explicit working-day lag
T3-L09-T | T3-L09-A | FS | 2 | 436 | 438 | 0 | Explicit working-day lag
T3-L09-A | T3-L09-D | FS | 0 | 443 | 443 | 0 | Explicit working-day lag
T3-L12-H | T3-L10-M | FS | 5 | 392 | 397 | 0 | Explicit working-day lag
T3-L10-M | T3-L10-P | FS | 3 | 402 | 405 | 0 | Explicit working-day lag
T3-L10-P | T3-L10-S | FS | 2 | 411 | 413 | 0 | Explicit working-day lag
T3-L10-S | T3-L10-T | FS | 14 | 416 | 430 | 0 | Explicit working-day lag
T3-GL | T3-L10-T | FS | 0 | 425 | 430 | 5 | Explicit working-day lag
T3-L10-T | T3-L10-A | FS | 2 | 436 | 438 | 0 | Explicit working-day lag
T3-L10-A | T3-L10-D | FS | 0 | 443 | 443 | 0 | Explicit working-day lag
T3-L12-H | T3-L11-M | FS | 5 | 392 | 397 | 0 | Explicit working-day lag
T3-L11-M | T3-L11-P | FS | 3 | 402 | 405 | 0 | Explicit working-day lag
T3-L11-P | T3-L11-S | FS | 2 | 411 | 413 | 0 | Explicit working-day lag
T3-L11-S | T3-L11-T | FS | 14 | 416 | 430 | 0 | Explicit working-day lag
T3-GL | T3-L11-T | FS | 0 | 425 | 430 | 5 | Explicit working-day lag
T3-L11-T | T3-L11-A | FS | 2 | 436 | 438 | 0 | Explicit working-day lag
T3-L11-A | T3-L11-D | FS | 0 | 443 | 443 | 0 | Explicit working-day lag
T3-L12-H | T3-L12-M | FS | 5 | 392 | 397 | 0 | Explicit working-day lag
T3-L12-M | T3-L12-P | FS | 3 | 402 | 405 | 0 | Explicit working-day lag
T3-L12-P | T3-L12-S | FS | 2 | 411 | 413 | 0 | Explicit working-day lag
T3-L12-S | T3-L12-T | FS | 14 | 416 | 430 | 0 | Explicit working-day lag
T3-GL | T3-L12-T | FS | 0 | 425 | 430 | 5 | Explicit working-day lag
T3-L12-T | T3-L12-A | FS | 2 | 436 | 438 | 0 | Explicit working-day lag
T3-L12-A | T3-L12-D | FS | 0 | 443 | 443 | 0 | Explicit working-day lag
P-040 | T4-L00-F | FS | 43 | 127 | 170 | 0 | Explicit working-day lag
T4-L00-F | T4-L00-R | FS | 0 | 176 | 176 | 0 | Explicit working-day lag
T4-L00-R | T4-L00-C | FS | 0 | 181 | 181 | 0 | Explicit working-day lag
T4-L00-C | T4-L00-H | FS | 0 | 183 | 183 | 0 | Explicit working-day lag
T4-L00-H | T4-L01-F | FS | 0 | 188 | 188 | 0 | Explicit working-day lag
T4-L01-F | T4-L01-R | FS | 0 | 194 | 194 | 0 | Explicit working-day lag
T4-L01-R | T4-L01-C | FS | 0 | 199 | 199 | 0 | Explicit working-day lag
T4-L01-C | T4-L01-H | FS | 0 | 201 | 201 | 0 | Explicit working-day lag
T4-L01-H | T4-L02-F | FS | 0 | 206 | 206 | 0 | Explicit working-day lag
T4-L02-F | T4-L02-R | FS | 0 | 212 | 212 | 0 | Explicit working-day lag
T4-L02-R | T4-L02-C | FS | 0 | 217 | 217 | 0 | Explicit working-day lag
T4-L02-C | T4-L02-H | FS | 0 | 219 | 219 | 0 | Explicit working-day lag
T4-L02-H | T4-L03-F | FS | 0 | 224 | 224 | 0 | Explicit working-day lag
T4-L03-F | T4-L03-R | FS | 0 | 230 | 230 | 0 | Explicit working-day lag
T4-L03-R | T4-L03-C | FS | 0 | 235 | 235 | 0 | Explicit working-day lag
T4-L03-C | T4-L03-H | FS | 0 | 237 | 237 | 0 | Explicit working-day lag
T4-L03-H | T4-L04-F | FS | 0 | 242 | 242 | 0 | Explicit working-day lag
T4-L04-F | T4-L04-R | FS | 0 | 248 | 248 | 0 | Explicit working-day lag
T4-L04-R | T4-L04-C | FS | 0 | 253 | 253 | 0 | Explicit working-day lag
T4-L04-C | T4-L04-H | FS | 0 | 255 | 255 | 0 | Explicit working-day lag
T4-L04-H | T4-L05-F | FS | 0 | 260 | 260 | 0 | Explicit working-day lag
T4-L05-F | T4-L05-R | FS | 0 | 266 | 266 | 0 | Explicit working-day lag
T4-L05-R | T4-L05-C | FS | 0 | 271 | 271 | 0 | Explicit working-day lag
T4-L05-C | T4-L05-H | FS | 0 | 273 | 273 | 0 | Explicit working-day lag
T4-L05-H | T4-L06-F | FS | 0 | 278 | 278 | 0 | Explicit working-day lag
T4-L06-F | T4-L06-R | FS | 0 | 284 | 284 | 0 | Explicit working-day lag
T4-L06-R | T4-L06-C | FS | 0 | 289 | 289 | 0 | Explicit working-day lag
T4-L06-C | T4-L06-H | FS | 0 | 291 | 291 | 0 | Explicit working-day lag
T4-L06-H | T4-L07-F | FS | 0 | 296 | 296 | 0 | Explicit working-day lag
T4-L07-F | T4-L07-R | FS | 0 | 302 | 302 | 0 | Explicit working-day lag
T4-L07-R | T4-L07-C | FS | 0 | 307 | 307 | 0 | Explicit working-day lag
T4-L07-C | T4-L07-H | FS | 0 | 309 | 309 | 0 | Explicit working-day lag
T4-L07-H | T4-L08-F | FS | 0 | 314 | 314 | 0 | Explicit working-day lag
T4-L08-F | T4-L08-R | FS | 0 | 320 | 320 | 0 | Explicit working-day lag
T4-L08-R | T4-L08-C | FS | 0 | 325 | 325 | 0 | Explicit working-day lag
T4-L08-C | T4-L08-H | FS | 0 | 327 | 327 | 0 | Explicit working-day lag
T4-L08-H | T4-L09-F | FS | 0 | 332 | 332 | 0 | Explicit working-day lag
T4-L09-F | T4-L09-R | FS | 0 | 338 | 338 | 0 | Explicit working-day lag
T4-L09-R | T4-L09-C | FS | 0 | 343 | 343 | 0 | Explicit working-day lag
T4-L09-C | T4-L09-H | FS | 0 | 345 | 345 | 0 | Explicit working-day lag
T4-L09-H | T4-L10-F | FS | 0 | 350 | 350 | 0 | Explicit working-day lag
T4-L10-F | T4-L10-R | FS | 0 | 356 | 356 | 0 | Explicit working-day lag
T4-L10-R | T4-L10-C | FS | 0 | 361 | 361 | 0 | Explicit working-day lag
T4-L10-C | T4-L10-H | FS | 0 | 363 | 363 | 0 | Explicit working-day lag
T4-L10-H | T4-L11-F | FS | 0 | 368 | 368 | 0 | Explicit working-day lag
T4-L11-F | T4-L11-R | FS | 0 | 374 | 374 | 0 | Explicit working-day lag
T4-L11-R | T4-L11-C | FS | 0 | 379 | 379 | 0 | Explicit working-day lag
T4-L11-C | T4-L11-H | FS | 0 | 381 | 381 | 0 | Explicit working-day lag
T4-L11-H | T4-L12-F | FS | 0 | 386 | 386 | 0 | Explicit working-day lag
T4-L12-F | T4-L12-R | FS | 0 | 392 | 392 | 0 | Explicit working-day lag
T4-L12-R | T4-L12-C | FS | 0 | 397 | 397 | 0 | Explicit working-day lag
T4-L12-C | T4-L12-H | FS | 0 | 399 | 399 | 0 | Explicit working-day lag
T4-L12-H | T4-RF | FS | 5 | 404 | 409 | 0 | Explicit working-day lag
T4-L08-H | T4-FA | FS | 10 | 332 | 342 | 0 | Explicit working-day lag
T4-FA | T4-GL | FS | 0 | 364 | 423 | 59 | Explicit working-day lag
T4-RF | T4-GL | FS | 0 | 423 | 423 | 0 | Explicit working-day lag
T4-L03-H | T4-L00-M | FS | 5 | 242 | 247 | 0 | Explicit working-day lag
T4-L00-M | T4-L00-P | FS | 3 | 252 | 255 | 0 | Explicit working-day lag
T4-L00-P | T4-L00-S | FS | 2 | 261 | 263 | 0 | Explicit working-day lag
T4-L00-S | T4-L00-T | FS | 14 | 266 | 437 | 157 | Explicit working-day lag
T4-GL | T4-L00-T | FS | 0 | 437 | 437 | 0 | Explicit working-day lag
T4-L00-T | T4-L00-A | FS | 2 | 443 | 445 | 0 | Explicit working-day lag
T4-L00-A | T4-L00-D | FS | 0 | 450 | 450 | 0 | Explicit working-day lag
T4-L04-H | T4-L01-M | FS | 5 | 260 | 265 | 0 | Explicit working-day lag
T4-L01-M | T4-L01-P | FS | 3 | 270 | 273 | 0 | Explicit working-day lag
T4-L01-P | T4-L01-S | FS | 2 | 279 | 281 | 0 | Explicit working-day lag
T4-L01-S | T4-L01-T | FS | 14 | 284 | 437 | 139 | Explicit working-day lag
T4-GL | T4-L01-T | FS | 0 | 437 | 437 | 0 | Explicit working-day lag
T4-L01-T | T4-L01-A | FS | 2 | 443 | 445 | 0 | Explicit working-day lag
T4-L01-A | T4-L01-D | FS | 0 | 450 | 450 | 0 | Explicit working-day lag
T4-L05-H | T4-L02-M | FS | 5 | 278 | 283 | 0 | Explicit working-day lag
T4-L02-M | T4-L02-P | FS | 3 | 288 | 291 | 0 | Explicit working-day lag
T4-L02-P | T4-L02-S | FS | 2 | 297 | 299 | 0 | Explicit working-day lag
T4-L02-S | T4-L02-T | FS | 14 | 302 | 437 | 121 | Explicit working-day lag
T4-GL | T4-L02-T | FS | 0 | 437 | 437 | 0 | Explicit working-day lag
T4-L02-T | T4-L02-A | FS | 2 | 443 | 445 | 0 | Explicit working-day lag
T4-L02-A | T4-L02-D | FS | 0 | 450 | 450 | 0 | Explicit working-day lag
T4-L06-H | T4-L03-M | FS | 5 | 296 | 301 | 0 | Explicit working-day lag
T4-L03-M | T4-L03-P | FS | 3 | 306 | 309 | 0 | Explicit working-day lag
T4-L03-P | T4-L03-S | FS | 2 | 315 | 317 | 0 | Explicit working-day lag
T4-L03-S | T4-L03-T | FS | 14 | 320 | 437 | 103 | Explicit working-day lag
T4-GL | T4-L03-T | FS | 0 | 437 | 437 | 0 | Explicit working-day lag
T4-L03-T | T4-L03-A | FS | 2 | 443 | 445 | 0 | Explicit working-day lag
T4-L03-A | T4-L03-D | FS | 0 | 450 | 450 | 0 | Explicit working-day lag
T4-L07-H | T4-L04-M | FS | 5 | 314 | 319 | 0 | Explicit working-day lag
T4-L04-M | T4-L04-P | FS | 3 | 324 | 327 | 0 | Explicit working-day lag
T4-L04-P | T4-L04-S | FS | 2 | 333 | 335 | 0 | Explicit working-day lag
T4-L04-S | T4-L04-T | FS | 14 | 338 | 437 | 85 | Explicit working-day lag
T4-GL | T4-L04-T | FS | 0 | 437 | 437 | 0 | Explicit working-day lag
T4-L04-T | T4-L04-A | FS | 2 | 443 | 445 | 0 | Explicit working-day lag
T4-L04-A | T4-L04-D | FS | 0 | 450 | 450 | 0 | Explicit working-day lag
T4-L08-H | T4-L05-M | FS | 5 | 332 | 337 | 0 | Explicit working-day lag
T4-L05-M | T4-L05-P | FS | 3 | 342 | 345 | 0 | Explicit working-day lag
T4-L05-P | T4-L05-S | FS | 2 | 351 | 353 | 0 | Explicit working-day lag
T4-L05-S | T4-L05-T | FS | 14 | 356 | 437 | 67 | Explicit working-day lag
T4-GL | T4-L05-T | FS | 0 | 437 | 437 | 0 | Explicit working-day lag
T4-L05-T | T4-L05-A | FS | 2 | 443 | 445 | 0 | Explicit working-day lag
T4-L05-A | T4-L05-D | FS | 0 | 450 | 450 | 0 | Explicit working-day lag
T4-L09-H | T4-L06-M | FS | 5 | 350 | 355 | 0 | Explicit working-day lag
T4-L06-M | T4-L06-P | FS | 3 | 360 | 363 | 0 | Explicit working-day lag
T4-L06-P | T4-L06-S | FS | 2 | 369 | 371 | 0 | Explicit working-day lag
T4-L06-S | T4-L06-T | FS | 14 | 374 | 437 | 49 | Explicit working-day lag
T4-GL | T4-L06-T | FS | 0 | 437 | 437 | 0 | Explicit working-day lag
T4-L06-T | T4-L06-A | FS | 2 | 443 | 445 | 0 | Explicit working-day lag
T4-L06-A | T4-L06-D | FS | 0 | 450 | 450 | 0 | Explicit working-day lag
T4-L10-H | T4-L07-M | FS | 5 | 368 | 373 | 0 | Explicit working-day lag
T4-L07-M | T4-L07-P | FS | 3 | 378 | 381 | 0 | Explicit working-day lag
T4-L07-P | T4-L07-S | FS | 2 | 387 | 389 | 0 | Explicit working-day lag
T4-L07-S | T4-L07-T | FS | 14 | 392 | 437 | 31 | Explicit working-day lag
T4-GL | T4-L07-T | FS | 0 | 437 | 437 | 0 | Explicit working-day lag
T4-L07-T | T4-L07-A | FS | 2 | 443 | 445 | 0 | Explicit working-day lag
T4-L07-A | T4-L07-D | FS | 0 | 450 | 450 | 0 | Explicit working-day lag
T4-L11-H | T4-L08-M | FS | 5 | 386 | 391 | 0 | Explicit working-day lag
T4-L08-M | T4-L08-P | FS | 3 | 396 | 399 | 0 | Explicit working-day lag
T4-L08-P | T4-L08-S | FS | 2 | 405 | 407 | 0 | Explicit working-day lag
T4-L08-S | T4-L08-T | FS | 14 | 410 | 437 | 13 | Explicit working-day lag
T4-GL | T4-L08-T | FS | 0 | 437 | 437 | 0 | Explicit working-day lag
T4-L08-T | T4-L08-A | FS | 2 | 443 | 445 | 0 | Explicit working-day lag
T4-L08-A | T4-L08-D | FS | 0 | 450 | 450 | 0 | Explicit working-day lag
T4-L12-H | T4-L09-M | FS | 5 | 404 | 409 | 0 | Explicit working-day lag
T4-L09-M | T4-L09-P | FS | 3 | 414 | 417 | 0 | Explicit working-day lag
T4-L09-P | T4-L09-S | FS | 2 | 423 | 425 | 0 | Explicit working-day lag
T4-L09-S | T4-L09-T | FS | 14 | 428 | 442 | 0 | Explicit working-day lag
T4-GL | T4-L09-T | FS | 0 | 437 | 442 | 5 | Explicit working-day lag
T4-L09-T | T4-L09-A | FS | 2 | 448 | 450 | 0 | Explicit working-day lag
T4-L09-A | T4-L09-D | FS | 0 | 455 | 455 | 0 | Explicit working-day lag
T4-L12-H | T4-L10-M | FS | 5 | 404 | 409 | 0 | Explicit working-day lag
T4-L10-M | T4-L10-P | FS | 3 | 414 | 417 | 0 | Explicit working-day lag
T4-L10-P | T4-L10-S | FS | 2 | 423 | 425 | 0 | Explicit working-day lag
T4-L10-S | T4-L10-T | FS | 14 | 428 | 442 | 0 | Explicit working-day lag
T4-GL | T4-L10-T | FS | 0 | 437 | 442 | 5 | Explicit working-day lag
T4-L10-T | T4-L10-A | FS | 2 | 448 | 450 | 0 | Explicit working-day lag
T4-L10-A | T4-L10-D | FS | 0 | 455 | 455 | 0 | Explicit working-day lag
T4-L12-H | T4-L11-M | FS | 5 | 404 | 409 | 0 | Explicit working-day lag
T4-L11-M | T4-L11-P | FS | 3 | 414 | 417 | 0 | Explicit working-day lag
T4-L11-P | T4-L11-S | FS | 2 | 423 | 425 | 0 | Explicit working-day lag
T4-L11-S | T4-L11-T | FS | 14 | 428 | 442 | 0 | Explicit working-day lag
T4-GL | T4-L11-T | FS | 0 | 437 | 442 | 5 | Explicit working-day lag
T4-L11-T | T4-L11-A | FS | 2 | 448 | 450 | 0 | Explicit working-day lag
T4-L11-A | T4-L11-D | FS | 0 | 455 | 455 | 0 | Explicit working-day lag
T4-L12-H | T4-L12-M | FS | 5 | 404 | 409 | 0 | Explicit working-day lag
T4-L12-M | T4-L12-P | FS | 3 | 414 | 417 | 0 | Explicit working-day lag
T4-L12-P | T4-L12-S | FS | 2 | 423 | 425 | 0 | Explicit working-day lag
T4-L12-S | T4-L12-T | FS | 14 | 428 | 442 | 0 | Explicit working-day lag
T4-GL | T4-L12-T | FS | 0 | 437 | 442 | 5 | Explicit working-day lag
T4-L12-T | T4-L12-A | FS | 2 | 448 | 450 | 0 | Explicit working-day lag
T4-L12-A | T4-L12-D | FS | 0 | 455 | 455 | 0 | Explicit working-day lag
P-040 | T5-L00-F | FS | 55 | 127 | 182 | 0 | Explicit working-day lag
T5-L00-F | T5-L00-R | FS | 0 | 188 | 188 | 0 | Explicit working-day lag
T5-L00-R | T5-L00-C | FS | 0 | 193 | 193 | 0 | Explicit working-day lag
T5-L00-C | T5-L00-H | FS | 0 | 195 | 195 | 0 | Explicit working-day lag
T5-L00-H | T5-L01-F | FS | 0 | 200 | 200 | 0 | Explicit working-day lag
T5-L01-F | T5-L01-R | FS | 0 | 206 | 206 | 0 | Explicit working-day lag
T5-L01-R | T5-L01-C | FS | 0 | 211 | 211 | 0 | Explicit working-day lag
T5-L01-C | T5-L01-H | FS | 0 | 213 | 213 | 0 | Explicit working-day lag
T5-L01-H | T5-L02-F | FS | 0 | 218 | 218 | 0 | Explicit working-day lag
T5-L02-F | T5-L02-R | FS | 0 | 224 | 224 | 0 | Explicit working-day lag
T5-L02-R | T5-L02-C | FS | 0 | 229 | 229 | 0 | Explicit working-day lag
T5-L02-C | T5-L02-H | FS | 0 | 231 | 231 | 0 | Explicit working-day lag
T5-L02-H | T5-L03-F | FS | 0 | 236 | 236 | 0 | Explicit working-day lag
T5-L03-F | T5-L03-R | FS | 0 | 242 | 242 | 0 | Explicit working-day lag
T5-L03-R | T5-L03-C | FS | 0 | 247 | 247 | 0 | Explicit working-day lag
T5-L03-C | T5-L03-H | FS | 0 | 249 | 249 | 0 | Explicit working-day lag
T5-L03-H | T5-L04-F | FS | 0 | 254 | 254 | 0 | Explicit working-day lag
T5-L04-F | T5-L04-R | FS | 0 | 260 | 260 | 0 | Explicit working-day lag
T5-L04-R | T5-L04-C | FS | 0 | 265 | 265 | 0 | Explicit working-day lag
T5-L04-C | T5-L04-H | FS | 0 | 267 | 267 | 0 | Explicit working-day lag
T5-L04-H | T5-L05-F | FS | 0 | 272 | 272 | 0 | Explicit working-day lag
T5-L05-F | T5-L05-R | FS | 0 | 278 | 278 | 0 | Explicit working-day lag
T5-L05-R | T5-L05-C | FS | 0 | 283 | 283 | 0 | Explicit working-day lag
T5-L05-C | T5-L05-H | FS | 0 | 285 | 285 | 0 | Explicit working-day lag
T5-L05-H | T5-L06-F | FS | 0 | 290 | 290 | 0 | Explicit working-day lag
T5-L06-F | T5-L06-R | FS | 0 | 296 | 296 | 0 | Explicit working-day lag
T5-L06-R | T5-L06-C | FS | 0 | 301 | 301 | 0 | Explicit working-day lag
T5-L06-C | T5-L06-H | FS | 0 | 303 | 303 | 0 | Explicit working-day lag
T5-L06-H | T5-L07-F | FS | 0 | 308 | 308 | 0 | Explicit working-day lag
T5-L07-F | T5-L07-R | FS | 0 | 314 | 314 | 0 | Explicit working-day lag
T5-L07-R | T5-L07-C | FS | 0 | 319 | 319 | 0 | Explicit working-day lag
T5-L07-C | T5-L07-H | FS | 0 | 321 | 321 | 0 | Explicit working-day lag
T5-L07-H | T5-L08-F | FS | 0 | 326 | 326 | 0 | Explicit working-day lag
T5-L08-F | T5-L08-R | FS | 0 | 332 | 332 | 0 | Explicit working-day lag
T5-L08-R | T5-L08-C | FS | 0 | 337 | 337 | 0 | Explicit working-day lag
T5-L08-C | T5-L08-H | FS | 0 | 339 | 339 | 0 | Explicit working-day lag
T5-L08-H | T5-L09-F | FS | 0 | 344 | 344 | 0 | Explicit working-day lag
T5-L09-F | T5-L09-R | FS | 0 | 350 | 350 | 0 | Explicit working-day lag
T5-L09-R | T5-L09-C | FS | 0 | 355 | 355 | 0 | Explicit working-day lag
T5-L09-C | T5-L09-H | FS | 0 | 357 | 357 | 0 | Explicit working-day lag
T5-L09-H | T5-L10-F | FS | 0 | 362 | 362 | 0 | Explicit working-day lag
T5-L10-F | T5-L10-R | FS | 0 | 368 | 368 | 0 | Explicit working-day lag
T5-L10-R | T5-L10-C | FS | 0 | 373 | 373 | 0 | Explicit working-day lag
T5-L10-C | T5-L10-H | FS | 0 | 375 | 375 | 0 | Explicit working-day lag
T5-L10-H | T5-L11-F | FS | 0 | 380 | 380 | 0 | Explicit working-day lag
T5-L11-F | T5-L11-R | FS | 0 | 386 | 386 | 0 | Explicit working-day lag
T5-L11-R | T5-L11-C | FS | 0 | 391 | 391 | 0 | Explicit working-day lag
T5-L11-C | T5-L11-H | FS | 0 | 393 | 393 | 0 | Explicit working-day lag
T5-L11-H | T5-L12-F | FS | 0 | 398 | 398 | 0 | Explicit working-day lag
T5-L12-F | T5-L12-R | FS | 0 | 404 | 404 | 0 | Explicit working-day lag
T5-L12-R | T5-L12-C | FS | 0 | 409 | 409 | 0 | Explicit working-day lag
T5-L12-C | T5-L12-H | FS | 0 | 411 | 411 | 0 | Explicit working-day lag
T5-L12-H | T5-RF | FS | 5 | 416 | 421 | 0 | Explicit working-day lag
T5-L08-H | T5-FA | FS | 10 | 344 | 354 | 0 | Explicit working-day lag
T5-FA | T5-GL | FS | 0 | 376 | 435 | 59 | Explicit working-day lag
T5-RF | T5-GL | FS | 0 | 435 | 435 | 0 | Explicit working-day lag
T5-L03-H | T5-L00-M | FS | 5 | 254 | 259 | 0 | Explicit working-day lag
T5-L00-M | T5-L00-P | FS | 3 | 264 | 267 | 0 | Explicit working-day lag
T5-L00-P | T5-L00-S | FS | 2 | 273 | 275 | 0 | Explicit working-day lag
T5-L00-S | T5-L00-T | FS | 14 | 278 | 449 | 157 | Explicit working-day lag
T5-GL | T5-L00-T | FS | 0 | 449 | 449 | 0 | Explicit working-day lag
T5-L00-T | T5-L00-A | FS | 2 | 455 | 457 | 0 | Explicit working-day lag
T5-L00-A | T5-L00-D | FS | 0 | 462 | 462 | 0 | Explicit working-day lag
T5-L04-H | T5-L01-M | FS | 5 | 272 | 277 | 0 | Explicit working-day lag
T5-L01-M | T5-L01-P | FS | 3 | 282 | 285 | 0 | Explicit working-day lag
T5-L01-P | T5-L01-S | FS | 2 | 291 | 293 | 0 | Explicit working-day lag
T5-L01-S | T5-L01-T | FS | 14 | 296 | 449 | 139 | Explicit working-day lag
T5-GL | T5-L01-T | FS | 0 | 449 | 449 | 0 | Explicit working-day lag
T5-L01-T | T5-L01-A | FS | 2 | 455 | 457 | 0 | Explicit working-day lag
T5-L01-A | T5-L01-D | FS | 0 | 462 | 462 | 0 | Explicit working-day lag
T5-L05-H | T5-L02-M | FS | 5 | 290 | 295 | 0 | Explicit working-day lag
T5-L02-M | T5-L02-P | FS | 3 | 300 | 303 | 0 | Explicit working-day lag
T5-L02-P | T5-L02-S | FS | 2 | 309 | 311 | 0 | Explicit working-day lag
T5-L02-S | T5-L02-T | FS | 14 | 314 | 449 | 121 | Explicit working-day lag
T5-GL | T5-L02-T | FS | 0 | 449 | 449 | 0 | Explicit working-day lag
T5-L02-T | T5-L02-A | FS | 2 | 455 | 457 | 0 | Explicit working-day lag
T5-L02-A | T5-L02-D | FS | 0 | 462 | 462 | 0 | Explicit working-day lag
T5-L06-H | T5-L03-M | FS | 5 | 308 | 313 | 0 | Explicit working-day lag
T5-L03-M | T5-L03-P | FS | 3 | 318 | 321 | 0 | Explicit working-day lag
T5-L03-P | T5-L03-S | FS | 2 | 327 | 329 | 0 | Explicit working-day lag
T5-L03-S | T5-L03-T | FS | 14 | 332 | 449 | 103 | Explicit working-day lag
T5-GL | T5-L03-T | FS | 0 | 449 | 449 | 0 | Explicit working-day lag
T5-L03-T | T5-L03-A | FS | 2 | 455 | 457 | 0 | Explicit working-day lag
T5-L03-A | T5-L03-D | FS | 0 | 462 | 462 | 0 | Explicit working-day lag
T5-L07-H | T5-L04-M | FS | 5 | 326 | 331 | 0 | Explicit working-day lag
T5-L04-M | T5-L04-P | FS | 3 | 336 | 339 | 0 | Explicit working-day lag
T5-L04-P | T5-L04-S | FS | 2 | 345 | 347 | 0 | Explicit working-day lag
T5-L04-S | T5-L04-T | FS | 14 | 350 | 449 | 85 | Explicit working-day lag
T5-GL | T5-L04-T | FS | 0 | 449 | 449 | 0 | Explicit working-day lag
T5-L04-T | T5-L04-A | FS | 2 | 455 | 457 | 0 | Explicit working-day lag
T5-L04-A | T5-L04-D | FS | 0 | 462 | 462 | 0 | Explicit working-day lag
T5-L08-H | T5-L05-M | FS | 5 | 344 | 349 | 0 | Explicit working-day lag
T5-L05-M | T5-L05-P | FS | 3 | 354 | 357 | 0 | Explicit working-day lag
T5-L05-P | T5-L05-S | FS | 2 | 363 | 365 | 0 | Explicit working-day lag
T5-L05-S | T5-L05-T | FS | 14 | 368 | 449 | 67 | Explicit working-day lag
T5-GL | T5-L05-T | FS | 0 | 449 | 449 | 0 | Explicit working-day lag
T5-L05-T | T5-L05-A | FS | 2 | 455 | 457 | 0 | Explicit working-day lag
T5-L05-A | T5-L05-D | FS | 0 | 462 | 462 | 0 | Explicit working-day lag
T5-L09-H | T5-L06-M | FS | 5 | 362 | 367 | 0 | Explicit working-day lag
T5-L06-M | T5-L06-P | FS | 3 | 372 | 375 | 0 | Explicit working-day lag
T5-L06-P | T5-L06-S | FS | 2 | 381 | 383 | 0 | Explicit working-day lag
T5-L06-S | T5-L06-T | FS | 14 | 386 | 449 | 49 | Explicit working-day lag
T5-GL | T5-L06-T | FS | 0 | 449 | 449 | 0 | Explicit working-day lag
T5-L06-T | T5-L06-A | FS | 2 | 455 | 457 | 0 | Explicit working-day lag
T5-L06-A | T5-L06-D | FS | 0 | 462 | 462 | 0 | Explicit working-day lag
T5-L10-H | T5-L07-M | FS | 5 | 380 | 385 | 0 | Explicit working-day lag
T5-L07-M | T5-L07-P | FS | 3 | 390 | 393 | 0 | Explicit working-day lag
T5-L07-P | T5-L07-S | FS | 2 | 399 | 401 | 0 | Explicit working-day lag
T5-L07-S | T5-L07-T | FS | 14 | 404 | 449 | 31 | Explicit working-day lag
T5-GL | T5-L07-T | FS | 0 | 449 | 449 | 0 | Explicit working-day lag
T5-L07-T | T5-L07-A | FS | 2 | 455 | 457 | 0 | Explicit working-day lag
T5-L07-A | T5-L07-D | FS | 0 | 462 | 462 | 0 | Explicit working-day lag
T5-L11-H | T5-L08-M | FS | 5 | 398 | 403 | 0 | Explicit working-day lag
T5-L08-M | T5-L08-P | FS | 3 | 408 | 411 | 0 | Explicit working-day lag
T5-L08-P | T5-L08-S | FS | 2 | 417 | 419 | 0 | Explicit working-day lag
T5-L08-S | T5-L08-T | FS | 14 | 422 | 449 | 13 | Explicit working-day lag
T5-GL | T5-L08-T | FS | 0 | 449 | 449 | 0 | Explicit working-day lag
T5-L08-T | T5-L08-A | FS | 2 | 455 | 457 | 0 | Explicit working-day lag
T5-L08-A | T5-L08-D | FS | 0 | 462 | 462 | 0 | Explicit working-day lag
T5-L12-H | T5-L09-M | FS | 5 | 416 | 421 | 0 | Explicit working-day lag
T5-L09-M | T5-L09-P | FS | 3 | 426 | 429 | 0 | Explicit working-day lag
T5-L09-P | T5-L09-S | FS | 2 | 435 | 437 | 0 | Explicit working-day lag
T5-L09-S | T5-L09-T | FS | 14 | 440 | 454 | 0 | Explicit working-day lag
T5-GL | T5-L09-T | FS | 0 | 449 | 454 | 5 | Explicit working-day lag
T5-L09-T | T5-L09-A | FS | 2 | 460 | 462 | 0 | Explicit working-day lag
T5-L09-A | T5-L09-D | FS | 0 | 467 | 467 | 0 | Explicit working-day lag
T5-L12-H | T5-L10-M | FS | 5 | 416 | 421 | 0 | Explicit working-day lag
T5-L10-M | T5-L10-P | FS | 3 | 426 | 429 | 0 | Explicit working-day lag
T5-L10-P | T5-L10-S | FS | 2 | 435 | 437 | 0 | Explicit working-day lag
T5-L10-S | T5-L10-T | FS | 14 | 440 | 454 | 0 | Explicit working-day lag
T5-GL | T5-L10-T | FS | 0 | 449 | 454 | 5 | Explicit working-day lag
T5-L10-T | T5-L10-A | FS | 2 | 460 | 462 | 0 | Explicit working-day lag
T5-L10-A | T5-L10-D | FS | 0 | 467 | 467 | 0 | Explicit working-day lag
T5-L12-H | T5-L11-M | FS | 5 | 416 | 421 | 0 | Explicit working-day lag
T5-L11-M | T5-L11-P | FS | 3 | 426 | 429 | 0 | Explicit working-day lag
T5-L11-P | T5-L11-S | FS | 2 | 435 | 437 | 0 | Explicit working-day lag
T5-L11-S | T5-L11-T | FS | 14 | 440 | 454 | 0 | Explicit working-day lag
T5-GL | T5-L11-T | FS | 0 | 449 | 454 | 5 | Explicit working-day lag
T5-L11-T | T5-L11-A | FS | 2 | 460 | 462 | 0 | Explicit working-day lag
T5-L11-A | T5-L11-D | FS | 0 | 467 | 467 | 0 | Explicit working-day lag
T5-L12-H | T5-L12-M | FS | 5 | 416 | 421 | 0 | Explicit working-day lag
T5-L12-M | T5-L12-P | FS | 3 | 426 | 429 | 0 | Explicit working-day lag
T5-L12-P | T5-L12-S | FS | 2 | 435 | 437 | 0 | Explicit working-day lag
T5-L12-S | T5-L12-T | FS | 14 | 440 | 454 | 0 | Explicit working-day lag
T5-GL | T5-L12-T | FS | 0 | 449 | 454 | 5 | Explicit working-day lag
T5-L12-T | T5-L12-A | FS | 2 | 460 | 462 | 0 | Explicit working-day lag
T5-L12-A | T5-L12-D | FS | 0 | 467 | 467 | 0 | Explicit working-day lag
P-040 | T6-L00-F | FS | 67 | 127 | 194 | 0 | Explicit working-day lag
T6-L00-F | T6-L00-R | FS | 0 | 200 | 200 | 0 | Explicit working-day lag
T6-L00-R | T6-L00-C | FS | 0 | 205 | 205 | 0 | Explicit working-day lag
T6-L00-C | T6-L00-H | FS | 0 | 207 | 207 | 0 | Explicit working-day lag
T6-L00-H | T6-L01-F | FS | 0 | 212 | 212 | 0 | Explicit working-day lag
T6-L01-F | T6-L01-R | FS | 0 | 218 | 218 | 0 | Explicit working-day lag
T6-L01-R | T6-L01-C | FS | 0 | 223 | 223 | 0 | Explicit working-day lag
T6-L01-C | T6-L01-H | FS | 0 | 225 | 225 | 0 | Explicit working-day lag
T6-L01-H | T6-L02-F | FS | 0 | 230 | 230 | 0 | Explicit working-day lag
T6-L02-F | T6-L02-R | FS | 0 | 236 | 236 | 0 | Explicit working-day lag
T6-L02-R | T6-L02-C | FS | 0 | 241 | 241 | 0 | Explicit working-day lag
T6-L02-C | T6-L02-H | FS | 0 | 243 | 243 | 0 | Explicit working-day lag
T6-L02-H | T6-L03-F | FS | 0 | 248 | 248 | 0 | Explicit working-day lag
T6-L03-F | T6-L03-R | FS | 0 | 254 | 254 | 0 | Explicit working-day lag
T6-L03-R | T6-L03-C | FS | 0 | 259 | 259 | 0 | Explicit working-day lag
T6-L03-C | T6-L03-H | FS | 0 | 261 | 261 | 0 | Explicit working-day lag
T6-L03-H | T6-L04-F | FS | 0 | 266 | 266 | 0 | Explicit working-day lag
T6-L04-F | T6-L04-R | FS | 0 | 272 | 272 | 0 | Explicit working-day lag
T6-L04-R | T6-L04-C | FS | 0 | 277 | 277 | 0 | Explicit working-day lag
T6-L04-C | T6-L04-H | FS | 0 | 279 | 279 | 0 | Explicit working-day lag
T6-L04-H | T6-L05-F | FS | 0 | 284 | 284 | 0 | Explicit working-day lag
T6-L05-F | T6-L05-R | FS | 0 | 290 | 290 | 0 | Explicit working-day lag
T6-L05-R | T6-L05-C | FS | 0 | 295 | 295 | 0 | Explicit working-day lag
T6-L05-C | T6-L05-H | FS | 0 | 297 | 297 | 0 | Explicit working-day lag
T6-L05-H | T6-L06-F | FS | 0 | 302 | 302 | 0 | Explicit working-day lag
T6-L06-F | T6-L06-R | FS | 0 | 308 | 308 | 0 | Explicit working-day lag
T6-L06-R | T6-L06-C | FS | 0 | 313 | 313 | 0 | Explicit working-day lag
T6-L06-C | T6-L06-H | FS | 0 | 315 | 315 | 0 | Explicit working-day lag
T6-L06-H | T6-L07-F | FS | 0 | 320 | 320 | 0 | Explicit working-day lag
T6-L07-F | T6-L07-R | FS | 0 | 326 | 326 | 0 | Explicit working-day lag
T6-L07-R | T6-L07-C | FS | 0 | 331 | 331 | 0 | Explicit working-day lag
T6-L07-C | T6-L07-H | FS | 0 | 333 | 333 | 0 | Explicit working-day lag
T6-L07-H | T6-L08-F | FS | 0 | 338 | 338 | 0 | Explicit working-day lag
T6-L08-F | T6-L08-R | FS | 0 | 344 | 344 | 0 | Explicit working-day lag
T6-L08-R | T6-L08-C | FS | 0 | 349 | 349 | 0 | Explicit working-day lag
T6-L08-C | T6-L08-H | FS | 0 | 351 | 351 | 0 | Explicit working-day lag
T6-L08-H | T6-L09-F | FS | 0 | 356 | 356 | 0 | Explicit working-day lag
T6-L09-F | T6-L09-R | FS | 0 | 362 | 362 | 0 | Explicit working-day lag
T6-L09-R | T6-L09-C | FS | 0 | 367 | 367 | 0 | Explicit working-day lag
T6-L09-C | T6-L09-H | FS | 0 | 369 | 369 | 0 | Explicit working-day lag
T6-L09-H | T6-L10-F | FS | 0 | 374 | 374 | 0 | Explicit working-day lag
T6-L10-F | T6-L10-R | FS | 0 | 380 | 380 | 0 | Explicit working-day lag
T6-L10-R | T6-L10-C | FS | 0 | 385 | 385 | 0 | Explicit working-day lag
T6-L10-C | T6-L10-H | FS | 0 | 387 | 387 | 0 | Explicit working-day lag
T6-L10-H | T6-L11-F | FS | 0 | 392 | 392 | 0 | Explicit working-day lag
T6-L11-F | T6-L11-R | FS | 0 | 398 | 398 | 0 | Explicit working-day lag
T6-L11-R | T6-L11-C | FS | 0 | 403 | 403 | 0 | Explicit working-day lag
T6-L11-C | T6-L11-H | FS | 0 | 405 | 405 | 0 | Explicit working-day lag
T6-L11-H | T6-L12-F | FS | 0 | 410 | 410 | 0 | Explicit working-day lag
T6-L12-F | T6-L12-R | FS | 0 | 416 | 416 | 0 | Explicit working-day lag
T6-L12-R | T6-L12-C | FS | 0 | 421 | 421 | 0 | Explicit working-day lag
T6-L12-C | T6-L12-H | FS | 0 | 423 | 423 | 0 | Explicit working-day lag
T6-L12-H | T6-RF | FS | 5 | 428 | 433 | 0 | Explicit working-day lag
T6-L08-H | T6-FA | FS | 10 | 356 | 366 | 0 | Explicit working-day lag
T6-FA | T6-GL | FS | 0 | 388 | 447 | 59 | Explicit working-day lag
T6-RF | T6-GL | FS | 0 | 447 | 447 | 0 | Explicit working-day lag
T6-L03-H | T6-L00-M | FS | 5 | 266 | 271 | 0 | Explicit working-day lag
T6-L00-M | T6-L00-P | FS | 3 | 276 | 279 | 0 | Explicit working-day lag
T6-L00-P | T6-L00-S | FS | 2 | 285 | 287 | 0 | Explicit working-day lag
T6-L00-S | T6-L00-T | FS | 14 | 290 | 461 | 157 | Explicit working-day lag
T6-GL | T6-L00-T | FS | 0 | 461 | 461 | 0 | Explicit working-day lag
T6-L00-T | T6-L00-A | FS | 2 | 467 | 469 | 0 | Explicit working-day lag
T6-L00-A | T6-L00-D | FS | 0 | 474 | 474 | 0 | Explicit working-day lag
T6-L04-H | T6-L01-M | FS | 5 | 284 | 289 | 0 | Explicit working-day lag
T6-L01-M | T6-L01-P | FS | 3 | 294 | 297 | 0 | Explicit working-day lag
T6-L01-P | T6-L01-S | FS | 2 | 303 | 305 | 0 | Explicit working-day lag
T6-L01-S | T6-L01-T | FS | 14 | 308 | 461 | 139 | Explicit working-day lag
T6-GL | T6-L01-T | FS | 0 | 461 | 461 | 0 | Explicit working-day lag
T6-L01-T | T6-L01-A | FS | 2 | 467 | 469 | 0 | Explicit working-day lag
T6-L01-A | T6-L01-D | FS | 0 | 474 | 474 | 0 | Explicit working-day lag
T6-L05-H | T6-L02-M | FS | 5 | 302 | 307 | 0 | Explicit working-day lag
T6-L02-M | T6-L02-P | FS | 3 | 312 | 315 | 0 | Explicit working-day lag
T6-L02-P | T6-L02-S | FS | 2 | 321 | 323 | 0 | Explicit working-day lag
T6-L02-S | T6-L02-T | FS | 14 | 326 | 461 | 121 | Explicit working-day lag
T6-GL | T6-L02-T | FS | 0 | 461 | 461 | 0 | Explicit working-day lag
T6-L02-T | T6-L02-A | FS | 2 | 467 | 469 | 0 | Explicit working-day lag
T6-L02-A | T6-L02-D | FS | 0 | 474 | 474 | 0 | Explicit working-day lag
T6-L06-H | T6-L03-M | FS | 5 | 320 | 325 | 0 | Explicit working-day lag
T6-L03-M | T6-L03-P | FS | 3 | 330 | 333 | 0 | Explicit working-day lag
T6-L03-P | T6-L03-S | FS | 2 | 339 | 341 | 0 | Explicit working-day lag
T6-L03-S | T6-L03-T | FS | 14 | 344 | 461 | 103 | Explicit working-day lag
T6-GL | T6-L03-T | FS | 0 | 461 | 461 | 0 | Explicit working-day lag
T6-L03-T | T6-L03-A | FS | 2 | 467 | 469 | 0 | Explicit working-day lag
T6-L03-A | T6-L03-D | FS | 0 | 474 | 474 | 0 | Explicit working-day lag
T6-L07-H | T6-L04-M | FS | 5 | 338 | 343 | 0 | Explicit working-day lag
T6-L04-M | T6-L04-P | FS | 3 | 348 | 351 | 0 | Explicit working-day lag
T6-L04-P | T6-L04-S | FS | 2 | 357 | 359 | 0 | Explicit working-day lag
T6-L04-S | T6-L04-T | FS | 14 | 362 | 461 | 85 | Explicit working-day lag
T6-GL | T6-L04-T | FS | 0 | 461 | 461 | 0 | Explicit working-day lag
T6-L04-T | T6-L04-A | FS | 2 | 467 | 469 | 0 | Explicit working-day lag
T6-L04-A | T6-L04-D | FS | 0 | 474 | 474 | 0 | Explicit working-day lag
T6-L08-H | T6-L05-M | FS | 5 | 356 | 361 | 0 | Explicit working-day lag
T6-L05-M | T6-L05-P | FS | 3 | 366 | 369 | 0 | Explicit working-day lag
T6-L05-P | T6-L05-S | FS | 2 | 375 | 377 | 0 | Explicit working-day lag
T6-L05-S | T6-L05-T | FS | 14 | 380 | 461 | 67 | Explicit working-day lag
T6-GL | T6-L05-T | FS | 0 | 461 | 461 | 0 | Explicit working-day lag
T6-L05-T | T6-L05-A | FS | 2 | 467 | 469 | 0 | Explicit working-day lag
T6-L05-A | T6-L05-D | FS | 0 | 474 | 474 | 0 | Explicit working-day lag
T6-L09-H | T6-L06-M | FS | 5 | 374 | 379 | 0 | Explicit working-day lag
T6-L06-M | T6-L06-P | FS | 3 | 384 | 387 | 0 | Explicit working-day lag
T6-L06-P | T6-L06-S | FS | 2 | 393 | 395 | 0 | Explicit working-day lag
T6-L06-S | T6-L06-T | FS | 14 | 398 | 461 | 49 | Explicit working-day lag
T6-GL | T6-L06-T | FS | 0 | 461 | 461 | 0 | Explicit working-day lag
T6-L06-T | T6-L06-A | FS | 2 | 467 | 469 | 0 | Explicit working-day lag
T6-L06-A | T6-L06-D | FS | 0 | 474 | 474 | 0 | Explicit working-day lag
T6-L10-H | T6-L07-M | FS | 5 | 392 | 397 | 0 | Explicit working-day lag
T6-L07-M | T6-L07-P | FS | 3 | 402 | 405 | 0 | Explicit working-day lag
T6-L07-P | T6-L07-S | FS | 2 | 411 | 413 | 0 | Explicit working-day lag
T6-L07-S | T6-L07-T | FS | 14 | 416 | 461 | 31 | Explicit working-day lag
T6-GL | T6-L07-T | FS | 0 | 461 | 461 | 0 | Explicit working-day lag
T6-L07-T | T6-L07-A | FS | 2 | 467 | 469 | 0 | Explicit working-day lag
T6-L07-A | T6-L07-D | FS | 0 | 474 | 474 | 0 | Explicit working-day lag
T6-L11-H | T6-L08-M | FS | 5 | 410 | 415 | 0 | Explicit working-day lag
T6-L08-M | T6-L08-P | FS | 3 | 420 | 423 | 0 | Explicit working-day lag
T6-L08-P | T6-L08-S | FS | 2 | 429 | 431 | 0 | Explicit working-day lag
T6-L08-S | T6-L08-T | FS | 14 | 434 | 461 | 13 | Explicit working-day lag
T6-GL | T6-L08-T | FS | 0 | 461 | 461 | 0 | Explicit working-day lag
T6-L08-T | T6-L08-A | FS | 2 | 467 | 469 | 0 | Explicit working-day lag
T6-L08-A | T6-L08-D | FS | 0 | 474 | 474 | 0 | Explicit working-day lag
T6-L12-H | T6-L09-M | FS | 5 | 428 | 433 | 0 | Explicit working-day lag
T6-L09-M | T6-L09-P | FS | 3 | 438 | 441 | 0 | Explicit working-day lag
T6-L09-P | T6-L09-S | FS | 2 | 447 | 449 | 0 | Explicit working-day lag
T6-L09-S | T6-L09-T | FS | 14 | 452 | 466 | 0 | Explicit working-day lag
T6-GL | T6-L09-T | FS | 0 | 461 | 466 | 5 | Explicit working-day lag
T6-L09-T | T6-L09-A | FS | 2 | 472 | 474 | 0 | Explicit working-day lag
T6-L09-A | T6-L09-D | FS | 0 | 479 | 479 | 0 | Explicit working-day lag
T6-L12-H | T6-L10-M | FS | 5 | 428 | 433 | 0 | Explicit working-day lag
T6-L10-M | T6-L10-P | FS | 3 | 438 | 441 | 0 | Explicit working-day lag
T6-L10-P | T6-L10-S | FS | 2 | 447 | 449 | 0 | Explicit working-day lag
T6-L10-S | T6-L10-T | FS | 14 | 452 | 466 | 0 | Explicit working-day lag
T6-GL | T6-L10-T | FS | 0 | 461 | 466 | 5 | Explicit working-day lag
T6-L10-T | T6-L10-A | FS | 2 | 472 | 474 | 0 | Explicit working-day lag
T6-L10-A | T6-L10-D | FS | 0 | 479 | 479 | 0 | Explicit working-day lag
T6-L12-H | T6-L11-M | FS | 5 | 428 | 433 | 0 | Explicit working-day lag
T6-L11-M | T6-L11-P | FS | 3 | 438 | 441 | 0 | Explicit working-day lag
T6-L11-P | T6-L11-S | FS | 2 | 447 | 449 | 0 | Explicit working-day lag
T6-L11-S | T6-L11-T | FS | 14 | 452 | 466 | 0 | Explicit working-day lag
T6-GL | T6-L11-T | FS | 0 | 461 | 466 | 5 | Explicit working-day lag
T6-L11-T | T6-L11-A | FS | 2 | 472 | 474 | 0 | Explicit working-day lag
T6-L11-A | T6-L11-D | FS | 0 | 479 | 479 | 0 | Explicit working-day lag
T6-L12-H | T6-L12-M | FS | 5 | 428 | 433 | 0 | Explicit working-day lag
T6-L12-M | T6-L12-P | FS | 3 | 438 | 441 | 0 | Explicit working-day lag
T6-L12-P | T6-L12-S | FS | 2 | 447 | 449 | 0 | Explicit working-day lag
T6-L12-S | T6-L12-T | FS | 14 | 452 | 466 | 0 | Explicit working-day lag
T6-GL | T6-L12-T | FS | 0 | 461 | 466 | 5 | Explicit working-day lag
T6-L12-T | T6-L12-A | FS | 2 | 472 | 474 | 0 | Explicit working-day lag
T6-L12-A | T6-L12-D | FS | 0 | 479 | 479 | 0 | Explicit working-day lag
P-070 | X-010 | FS | 0 | 163 | 163 | 0 | Explicit working-day lag
X-010 | X-020 | FS | 0 | 181 | 428 | 247 | Explicit working-day lag
T6-L12-H | X-020 | FS | 0 | 428 | 428 | 0 | Explicit working-day lag
P-060 | X-020 | FS | 0 | 161 | 428 | 267 | Explicit working-day lag
X-020 | PC-001 | FS | 0 | 451 | 482 | 31 | Explicit working-day lag
T1-L00-D | PC-001 | FS | 0 | 417 | 482 | 65 | Explicit working-day lag
T1-L01-D | PC-001 | FS | 0 | 417 | 482 | 65 | Explicit working-day lag
T1-L02-D | PC-001 | FS | 0 | 417 | 482 | 65 | Explicit working-day lag
T1-L03-D | PC-001 | FS | 0 | 417 | 482 | 65 | Explicit working-day lag
T1-L04-D | PC-001 | FS | 0 | 417 | 482 | 65 | Explicit working-day lag
T1-L05-D | PC-001 | FS | 0 | 417 | 482 | 65 | Explicit working-day lag
T1-L06-D | PC-001 | FS | 0 | 417 | 482 | 65 | Explicit working-day lag
T1-L07-D | PC-001 | FS | 0 | 417 | 482 | 65 | Explicit working-day lag
T1-L08-D | PC-001 | FS | 0 | 417 | 482 | 65 | Explicit working-day lag
T1-L09-D | PC-001 | FS | 0 | 422 | 482 | 60 | Explicit working-day lag
T1-L10-D | PC-001 | FS | 0 | 422 | 482 | 60 | Explicit working-day lag
T1-L11-D | PC-001 | FS | 0 | 422 | 482 | 60 | Explicit working-day lag
T1-L12-D | PC-001 | FS | 0 | 422 | 482 | 60 | Explicit working-day lag
T2-L00-D | PC-001 | FS | 0 | 429 | 482 | 53 | Explicit working-day lag
T2-L01-D | PC-001 | FS | 0 | 429 | 482 | 53 | Explicit working-day lag
T2-L02-D | PC-001 | FS | 0 | 429 | 482 | 53 | Explicit working-day lag
T2-L03-D | PC-001 | FS | 0 | 429 | 482 | 53 | Explicit working-day lag
T2-L04-D | PC-001 | FS | 0 | 429 | 482 | 53 | Explicit working-day lag
T2-L05-D | PC-001 | FS | 0 | 429 | 482 | 53 | Explicit working-day lag
T2-L06-D | PC-001 | FS | 0 | 429 | 482 | 53 | Explicit working-day lag
T2-L07-D | PC-001 | FS | 0 | 429 | 482 | 53 | Explicit working-day lag
T2-L08-D | PC-001 | FS | 0 | 429 | 482 | 53 | Explicit working-day lag
T2-L09-D | PC-001 | FS | 0 | 434 | 482 | 48 | Explicit working-day lag
T2-L10-D | PC-001 | FS | 0 | 434 | 482 | 48 | Explicit working-day lag
T2-L11-D | PC-001 | FS | 0 | 434 | 482 | 48 | Explicit working-day lag
T2-L12-D | PC-001 | FS | 0 | 434 | 482 | 48 | Explicit working-day lag
T3-L00-D | PC-001 | FS | 0 | 441 | 482 | 41 | Explicit working-day lag
T3-L01-D | PC-001 | FS | 0 | 441 | 482 | 41 | Explicit working-day lag
T3-L02-D | PC-001 | FS | 0 | 441 | 482 | 41 | Explicit working-day lag
T3-L03-D | PC-001 | FS | 0 | 441 | 482 | 41 | Explicit working-day lag
T3-L04-D | PC-001 | FS | 0 | 441 | 482 | 41 | Explicit working-day lag
T3-L05-D | PC-001 | FS | 0 | 441 | 482 | 41 | Explicit working-day lag
T3-L06-D | PC-001 | FS | 0 | 441 | 482 | 41 | Explicit working-day lag
T3-L07-D | PC-001 | FS | 0 | 441 | 482 | 41 | Explicit working-day lag
T3-L08-D | PC-001 | FS | 0 | 441 | 482 | 41 | Explicit working-day lag
T3-L09-D | PC-001 | FS | 0 | 446 | 482 | 36 | Explicit working-day lag
T3-L10-D | PC-001 | FS | 0 | 446 | 482 | 36 | Explicit working-day lag
T3-L11-D | PC-001 | FS | 0 | 446 | 482 | 36 | Explicit working-day lag
T3-L12-D | PC-001 | FS | 0 | 446 | 482 | 36 | Explicit working-day lag
T4-L00-D | PC-001 | FS | 0 | 453 | 482 | 29 | Explicit working-day lag
T4-L01-D | PC-001 | FS | 0 | 453 | 482 | 29 | Explicit working-day lag
T4-L02-D | PC-001 | FS | 0 | 453 | 482 | 29 | Explicit working-day lag
T4-L03-D | PC-001 | FS | 0 | 453 | 482 | 29 | Explicit working-day lag
T4-L04-D | PC-001 | FS | 0 | 453 | 482 | 29 | Explicit working-day lag
T4-L05-D | PC-001 | FS | 0 | 453 | 482 | 29 | Explicit working-day lag
T4-L06-D | PC-001 | FS | 0 | 453 | 482 | 29 | Explicit working-day lag
T4-L07-D | PC-001 | FS | 0 | 453 | 482 | 29 | Explicit working-day lag
T4-L08-D | PC-001 | FS | 0 | 453 | 482 | 29 | Explicit working-day lag
T4-L09-D | PC-001 | FS | 0 | 458 | 482 | 24 | Explicit working-day lag
T4-L10-D | PC-001 | FS | 0 | 458 | 482 | 24 | Explicit working-day lag
T4-L11-D | PC-001 | FS | 0 | 458 | 482 | 24 | Explicit working-day lag
T4-L12-D | PC-001 | FS | 0 | 458 | 482 | 24 | Explicit working-day lag
T5-L00-D | PC-001 | FS | 0 | 465 | 482 | 17 | Explicit working-day lag
T5-L01-D | PC-001 | FS | 0 | 465 | 482 | 17 | Explicit working-day lag
T5-L02-D | PC-001 | FS | 0 | 465 | 482 | 17 | Explicit working-day lag
T5-L03-D | PC-001 | FS | 0 | 465 | 482 | 17 | Explicit working-day lag
T5-L04-D | PC-001 | FS | 0 | 465 | 482 | 17 | Explicit working-day lag
T5-L05-D | PC-001 | FS | 0 | 465 | 482 | 17 | Explicit working-day lag
T5-L06-D | PC-001 | FS | 0 | 465 | 482 | 17 | Explicit working-day lag
T5-L07-D | PC-001 | FS | 0 | 465 | 482 | 17 | Explicit working-day lag
T5-L08-D | PC-001 | FS | 0 | 465 | 482 | 17 | Explicit working-day lag
T5-L09-D | PC-001 | FS | 0 | 470 | 482 | 12 | Explicit working-day lag
T5-L10-D | PC-001 | FS | 0 | 470 | 482 | 12 | Explicit working-day lag
T5-L11-D | PC-001 | FS | 0 | 470 | 482 | 12 | Explicit working-day lag
T5-L12-D | PC-001 | FS | 0 | 470 | 482 | 12 | Explicit working-day lag
T6-L00-D | PC-001 | FS | 0 | 477 | 482 | 5 | Explicit working-day lag
T6-L01-D | PC-001 | FS | 0 | 477 | 482 | 5 | Explicit working-day lag
T6-L02-D | PC-001 | FS | 0 | 477 | 482 | 5 | Explicit working-day lag
T6-L03-D | PC-001 | FS | 0 | 477 | 482 | 5 | Explicit working-day lag
T6-L04-D | PC-001 | FS | 0 | 477 | 482 | 5 | Explicit working-day lag
T6-L05-D | PC-001 | FS | 0 | 477 | 482 | 5 | Explicit working-day lag
T6-L06-D | PC-001 | FS | 0 | 477 | 482 | 5 | Explicit working-day lag
T6-L07-D | PC-001 | FS | 0 | 477 | 482 | 5 | Explicit working-day lag
T6-L08-D | PC-001 | FS | 0 | 477 | 482 | 5 | Explicit working-day lag
T6-L09-D | PC-001 | FS | 0 | 482 | 482 | 0 | Explicit working-day lag
T6-L10-D | PC-001 | FS | 0 | 482 | 482 | 0 | Explicit working-day lag
T6-L11-D | PC-001 | FS | 0 | 482 | 482 | 0 | Explicit working-day lag
T6-L12-D | PC-001 | FS | 0 | 482 | 482 | 0 | Explicit working-day lag

## Weekly Gantt
Weekly construction sequence
Values are scheduled working days in each week, not percent complete.
Activity ID | Zone | Activity | Trade | W001 | W002 | W003 | W004 | W005 | W006 | W007 | W008 | W009 | W010 | W011 | W012 | W013 | W014 | W015 | W016 | W017 | W018 | W019 | W020 | W021 | W022 | W023 | W024 | W025 | W026 | W027 | W028 | W029 | W030 | W031 | W032 | W033 | W034 | W035 | W036 | W037 | W038 | W039 | W040 | W041 | W042 | W043 | W044 | W045 | W046 | W047 | W048 | W049 | W050 | W051 | W052 | W053 | W054 | W055 | W056 | W057 | W058 | W059 | W060 | W061 | W062 | W063 | W064 | W065 | W066 | W067 | W068 | W069 | W070 | W071 | W072 | W073 | W074 | W075 | W076 | W077 | W078 | W079 | W080 | W081 | W082 | W083 | W084 | W085 | W086 | W087 | W088 | W089 | W090 | W091 | W092 | W093 | W094 | W095 | W096 | W097 | W098 | W099 | W100 | W101 | W102 | W103 | W104 | W105 | W106
P-001 | SITE | Mobilisation and temporary facilities | Site | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P-010 | POD | Excavation and surplus disposal | Earthworks | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P-020 | POD | Blinding and underslab membrane | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P-030 | POD | Raft reinforcement and preparation | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P-040 | POD | Raft base and tower thickening pours | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P-050 | POD | Basement perimeter walls | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P-060 | POD | Podium roof structural package | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P-070 | SITE | Backfill and perimeter reinstatement | Earthworks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L00-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L00-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L00-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L00-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L01-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L01-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L01-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L01-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L02-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L02-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L02-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L02-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L03-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L03-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L03-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L03-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L04-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L04-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L04-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L04-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L05-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L05-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L05-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L05-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L06-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L06-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L06-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L06-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L07-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L07-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L07-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L07-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L08-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L08-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L08-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L08-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L09-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L09-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L09-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L09-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L10-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L10-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L10-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L10-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L11-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L11-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L11-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L11-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L12-F | T1 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L12-R | T1 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L12-C | T1 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L12-H | T1 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-RF | T1 | Roof membrane and weatherproofing | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-FA | T1 | Insulated facade installation | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-GL | T1 | Glazing and frame installation | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L00-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L00-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L00-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L00-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L00-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L00-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L01-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L01-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L01-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L01-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L01-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L01-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L02-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L02-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L02-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L02-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L02-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L02-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L03-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L03-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L03-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L03-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L03-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L03-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L04-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L04-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L04-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L04-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L04-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L04-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L05-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L05-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L05-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L05-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L05-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L05-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L06-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L06-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L06-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L06-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L06-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L06-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L07-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L07-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L07-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L07-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L07-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L07-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L08-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L08-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L08-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L08-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L08-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L08-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L09-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L09-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L09-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L09-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L09-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L09-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L10-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L10-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L10-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L10-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L10-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L10-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L11-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L11-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L11-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L11-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L11-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L11-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L12-M | T1 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L12-P | T1 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L12-S | T1 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L12-T | T1 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L12-A | T1 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1-L12-D | T1 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L00-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L00-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L00-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L00-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L01-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L01-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L01-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L01-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L02-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L02-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L02-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L02-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L03-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L03-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L03-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L03-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L04-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L04-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L04-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L04-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L05-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L05-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L05-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L05-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L06-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L06-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L06-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L06-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L07-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L07-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L07-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L07-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L08-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L08-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L08-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L08-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L09-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L09-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L09-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L09-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L10-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L10-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L10-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L10-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L11-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L11-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L11-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L11-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L12-F | T2 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L12-R | T2 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L12-C | T2 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L12-H | T2 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-RF | T2 | Roof membrane and weatherproofing | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-FA | T2 | Insulated facade installation | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-GL | T2 | Glazing and frame installation | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L00-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L00-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L00-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L00-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L00-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L00-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L01-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L01-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L01-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L01-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L01-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L01-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L02-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L02-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L02-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L02-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L02-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L02-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L03-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L03-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L03-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L03-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L03-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L03-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L04-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L04-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L04-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L04-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L04-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L04-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L05-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L05-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L05-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L05-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L05-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L05-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L06-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L06-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L06-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L06-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L06-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L06-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L07-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L07-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L07-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L07-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L07-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L07-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L08-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L08-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L08-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L08-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L08-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L08-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L09-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L09-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L09-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L09-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L09-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L09-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L10-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L10-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L10-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L10-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L10-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L10-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L11-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L11-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L11-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L11-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L11-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L11-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L12-M | T2 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L12-P | T2 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L12-S | T2 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L12-T | T2 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L12-A | T2 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-L12-D | T2 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L00-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L00-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L00-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L00-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L01-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L01-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L01-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L01-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L02-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L02-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L02-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L02-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L03-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L03-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L03-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L03-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L04-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L04-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L04-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L04-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L05-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L05-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L05-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L05-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L06-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L06-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L06-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L06-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L07-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L07-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L07-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L07-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L08-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L08-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L08-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L08-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L09-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L09-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L09-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L09-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L10-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L10-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L10-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L10-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L11-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L11-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L11-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L11-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L12-F | T3 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L12-R | T3 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L12-C | T3 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L12-H | T3 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-RF | T3 | Roof membrane and weatherproofing | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-FA | T3 | Insulated facade installation | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-GL | T3 | Glazing and frame installation | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L00-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L00-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L00-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L00-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L00-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L00-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L01-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L01-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L01-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L01-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L01-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L01-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L02-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L02-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L02-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L02-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L02-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L02-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L03-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L03-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L03-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L03-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L03-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L03-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L04-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L04-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L04-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L04-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L04-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L04-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L05-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L05-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L05-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L05-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L05-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L05-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L06-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L06-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L06-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L06-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L06-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L06-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L07-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L07-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L07-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L07-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L07-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L07-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L08-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L08-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L08-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L08-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L08-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L08-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L09-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L09-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L09-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L09-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L09-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L09-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L10-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L10-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L10-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L10-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L10-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L10-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L11-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L11-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L11-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L11-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L11-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L11-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L12-M | T3 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L12-P | T3 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L12-S | T3 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L12-T | T3 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L12-A | T3 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3-L12-D | T3 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L00-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L00-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L00-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L00-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L01-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L01-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L01-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L01-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L02-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L02-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L02-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L02-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L03-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L03-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L03-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L03-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L04-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L04-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L04-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L04-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L05-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L05-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L05-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L05-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L06-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L06-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L06-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L06-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L07-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L07-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L07-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L07-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L08-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L08-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L08-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L08-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L09-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L09-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L09-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L09-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L10-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L10-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L10-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L10-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L11-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L11-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L11-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L11-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L12-F | T4 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L12-R | T4 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L12-C | T4 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L12-H | T4 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-RF | T4 | Roof membrane and weatherproofing | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-FA | T4 | Insulated facade installation | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-GL | T4 | Glazing and frame installation | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L00-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L00-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L00-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L00-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L00-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L00-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L01-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L01-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L01-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L01-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L01-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L01-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L02-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L02-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L02-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L02-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L02-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L02-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L03-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L03-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L03-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L03-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L03-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L03-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L04-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L04-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L04-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L04-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L04-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L04-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L05-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L05-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L05-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L05-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L05-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L05-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L06-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L06-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L06-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L06-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L06-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L06-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L07-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L07-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L07-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L07-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L07-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L07-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L08-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L08-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L08-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L08-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L08-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L08-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L09-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L09-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L09-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L09-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L09-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L09-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L10-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L10-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L10-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L10-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L10-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L10-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L11-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L11-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L11-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L11-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L11-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L11-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L12-M | T4 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L12-P | T4 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L12-S | T4 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L12-T | T4 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L12-A | T4 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4-L12-D | T4 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L00-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L00-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L00-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L00-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L01-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L01-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L01-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L01-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L02-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L02-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L02-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L02-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L03-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L03-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L03-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L03-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L04-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L04-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L04-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L04-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L05-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L05-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L05-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L05-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L06-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L06-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L06-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L06-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L07-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L07-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L07-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L07-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L08-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L08-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L08-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L08-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L09-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L09-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L09-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L09-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L10-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L10-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L10-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L10-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L11-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L11-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L11-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L11-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L12-F | T5 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L12-R | T5 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L12-C | T5 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L12-H | T5 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-RF | T5 | Roof membrane and weatherproofing | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-FA | T5 | Insulated facade installation | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-GL | T5 | Glazing and frame installation | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L00-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L00-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L00-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L00-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L00-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L00-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L01-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L01-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L01-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L01-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L01-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L01-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L02-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L02-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L02-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L02-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L02-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L02-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L03-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L03-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L03-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L03-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L03-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L03-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L04-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L04-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L04-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L04-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L04-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L04-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L05-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L05-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L05-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L05-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L05-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L05-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L06-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L06-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L06-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L06-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L06-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L06-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L07-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L07-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L07-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L07-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L07-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L07-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L08-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L08-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L08-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L08-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L08-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L08-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L09-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L09-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L09-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L09-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L09-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L09-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L10-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L10-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L10-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L10-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L10-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L10-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L11-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L11-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L11-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L11-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L11-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L11-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L12-M | T5 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L12-P | T5 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L12-S | T5 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L12-T | T5 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L12-A | T5 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5-L12-D | T5 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L00-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L00-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L00-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L00-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L01-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L01-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L01-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L01-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L02-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L02-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L02-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L02-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L03-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L03-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L03-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L03-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L04-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L04-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L04-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L04-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L05-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L05-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L05-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L05-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L06-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L06-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L06-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L06-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L07-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L07-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L07-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L07-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L08-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L08-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L08-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L08-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L09-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L09-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L09-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L09-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L10-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L10-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L10-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L10-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L11-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L11-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L11-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L11-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L12-F | T6 | Columns, core and deck formwork | Formwork | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L12-R | T6 | Column, wall, beam and slab reinforcement | Rebar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L12-C | T6 | Concrete placement and finishing | Concrete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L12-H | T6 | Curing and release hold point | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-RF | T6 | Roof membrane and weatherproofing | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-FA | T6 | Insulated facade installation | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-GL | T6 | Glazing and frame installation | Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L00-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L00-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L00-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L00-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L00-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L00-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L01-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L01-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L01-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L01-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L01-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L01-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L02-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L02-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L02-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L02-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L02-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L02-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L03-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L03-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L03-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L03-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L03-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L03-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L04-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L04-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L04-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L04-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L04-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L04-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L05-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L05-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L05-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L05-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L05-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L05-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L06-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L06-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L06-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L06-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L06-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L06-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L07-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L07-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L07-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L07-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L07-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L07-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L08-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L08-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L08-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L08-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L08-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L08-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L09-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L09-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L09-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L09-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L09-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L09-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L10-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L10-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L10-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L10-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L10-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L10-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L11-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L11-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L11-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L11-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L11-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L11-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L12-M | T6 | Partition masonry | Masonry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L12-P | T6 | Internal plaster | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L12-S | T6 | Screed and substrate preparation | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L12-T | T6 | Floor finishes and skirtings | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L12-A | T6 | Paint and final decorations | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6-L12-D | T6 | Door sets and ironmongery | Finishes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X-010 | SITE | Stormwater pipes and chambers | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
X-020 | SITE | External paving and final levels | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 6 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PC-001 | PROJECT | Inspection, snagging and handover | Site | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Workforce
Weekly average workforce demand
Worker-days / six-day week. Baseline is not resource-levelled; thresholds flag crew congestion.
Week | Week start | Earthworks | Formwork | Rebar | Concrete | Masonry | Finishes | Envelope | External | Site | Total avg people | Capacity breaches
1 | 2026-11-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0
2 | 2026-11-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0
3 | 2026-11-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0
4 | 2026-11-23 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0
5 | 2026-11-30 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0
6 | 2026-12-07 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0
7 | 2026-12-14 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0
8 | 2026-12-21 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0
9 | 2026-12-28 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0
10 | 2027-01-04 | 12 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 21 | 0
11 | 2027-01-11 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 18 | 0
12 | 2027-01-18 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0
13 | 2027-01-25 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0
14 | 2027-02-01 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0
15 | 2027-02-08 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0
16 | 2027-02-15 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0
17 | 2027-02-22 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0
18 | 2027-03-01 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0
19 | 2027-03-08 | 0 | 0 | 9.1667 | 23.3333 | 0 | 0 | 0 | 0 | 0 | 32.5 | 0
20 | 2027-03-15 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 28 | 0
21 | 2027-03-22 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 28 | 0
22 | 2027-03-29 | 0 | 0 | 0 | 4.6667 | 0 | 0 | 0 | 0 | 0 | 4.6667 | 0
23 | 2027-04-05 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0
24 | 2027-04-12 | 0 | 30 | 9.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 39.3333 | 0
25 | 2027-04-19 | 0 | 39 | 2.3333 | 4 | 0 | 0 | 0 | 0 | 0 | 45.3333 | 0
26 | 2027-04-26 | 5.3333 | 48 | 9.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 62.6667 | 0
27 | 2027-05-03 | 16 | 43 | 11.6667 | 4 | 0 | 0 | 0 | 0 | 0 | 74.6667 | 0
28 | 2027-05-10 | 2.6667 | 18 | 11.6667 | 4 | 0 | 0 | 0 | 10 | 0 | 46.3333 | 0
29 | 2027-05-17 | 0 | 30 | 11.6667 | 4 | 0 | 0 | 0 | 12 | 0 | 57.6667 | 0
30 | 2027-05-24 | 0 | 24 | 21 | 4 | 0 | 0 | 0 | 12 | 0 | 61 | 0
31 | 2027-05-31 | 0 | 30 | 14 | 8 | 0 | 0 | 0 | 2 | 0 | 54 | 0
32 | 2027-06-07 | 0 | 36 | 21 | 4 | 0 | 0 | 0 | 0 | 0 | 61 | 0
33 | 2027-06-14 | 0 | 36 | 23.3333 | 8 | 0 | 0 | 0 | 0 | 0 | 67.3333 | 0
34 | 2027-06-21 | 0 | 36 | 23.3333 | 8 | 0 | 0 | 0 | 0 | 0 | 67.3333 | 0
35 | 2027-06-28 | 0 | 36 | 23.3333 | 8 | 0 | 0 | 0 | 0 | 0 | 67.3333 | 0
36 | 2027-07-05 | 0 | 36 | 23.3333 | 8 | 8.3333 | 0 | 0 | 0 | 0 | 75.6667 | 0
37 | 2027-07-12 | 0 | 36 | 23.3333 | 8 | 0 | 5 | 0 | 0 | 0 | 72.3333 | 0
38 | 2027-07-19 | 0 | 36 | 23.3333 | 8 | 8.3333 | 6.3333 | 0 | 0 | 0 | 82 | 0
39 | 2027-07-26 | 0 | 36 | 23.3333 | 8 | 8.3333 | 7.6667 | 0 | 0 | 0 | 83.3333 | 0
40 | 2027-08-02 | 0 | 36 | 23.3333 | 8 | 8.3333 | 11.3333 | 0 | 0 | 0 | 87 | 0
41 | 2027-08-09 | 0 | 36 | 23.3333 | 8 | 8.3333 | 14 | 0 | 0 | 0 | 89.6667 | 0
42 | 2027-08-16 | 0 | 36 | 23.3333 | 8 | 16.6667 | 14 | 0 | 0 | 0 | 98 | 0
43 | 2027-08-23 | 0 | 36 | 23.3333 | 8 | 8.3333 | 19 | 0 | 0 | 0 | 94.6667 | 0
44 | 2027-08-30 | 0 | 36 | 23.3333 | 8 | 16.6667 | 20.3333 | 0 | 0 | 0 | 104.3333 | 0
45 | 2027-09-06 | 0 | 36 | 23.3333 | 8 | 16.6667 | 21.6667 | 0 | 0 | 0 | 105.6667 | 0
46 | 2027-09-13 | 0 | 36 | 23.3333 | 8 | 16.6667 | 25.3333 | 0 | 0 | 0 | 109.3333 | 0
47 | 2027-09-20 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 0 | 0 | 0 | 112 | 0
48 | 2027-09-27 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 0 | 0 | 0 | 112 | 0
49 | 2027-10-04 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 0 | 0 | 0 | 112 | 0
50 | 2027-10-11 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 0 | 0 | 0 | 112 | 0
51 | 2027-10-18 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 0 | 0 | 0 | 112 | 0
52 | 2027-10-25 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 16 | 0 | 0 | 128 | 0
53 | 2027-11-01 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 16 | 0 | 0 | 128 | 0
54 | 2027-11-08 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 32 | 0 | 0 | 144 | 0
55 | 2027-11-15 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 26.6667 | 0 | 0 | 138.6667 | 0
56 | 2027-11-22 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 32 | 0 | 0 | 144 | 0
57 | 2027-11-29 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 26.6667 | 0 | 0 | 138.6667 | 0
58 | 2027-12-06 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 32 | 0 | 0 | 144 | 0
59 | 2027-12-13 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 26.6667 | 0 | 0 | 138.6667 | 0
60 | 2027-12-20 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 32 | 0 | 0 | 144 | 0
61 | 2027-12-27 | 0 | 36 | 23.3333 | 8 | 16.6667 | 28 | 26.6667 | 0 | 0 | 138.6667 | 0
62 | 2028-01-03 | 0 | 24 | 23.3333 | 8 | 16.6667 | 28 | 32 | 0 | 0 | 132 | 0
63 | 2028-01-10 | 0 | 30 | 14 | 8 | 41.6667 | 28 | 35 | 0 | 0 | 156.6667 | 0
64 | 2028-01-17 | 0 | 24 | 21 | 4 | 16.6667 | 43 | 26 | 0 | 0 | 134.6667 | 0
65 | 2028-01-24 | 0 | 18 | 14 | 8 | 41.6667 | 47 | 30 | 0 | 0 | 158.6667 | 0
66 | 2028-01-31 | 0 | 18 | 11.6667 | 4 | 8.3333 | 51 | 22 | 0 | 0 | 115 | 0
67 | 2028-02-07 | 0 | 18 | 11.6667 | 4 | 41.6667 | 54 | 29.3333 | 0 | 0 | 158.6667 | 0
68 | 2028-02-14 | 0 | 6 | 11.6667 | 4 | 8.3333 | 115.3333 | 22 | 0 | 0 | 167.3333 | 0
69 | 2028-02-21 | 0 | 12 | 2.3333 | 4 | 33.3333 | 132.6667 | 29.3333 | 0 | 0 | 213.6667 | 0
70 | 2028-02-28 | 0 | 6 | 9.3333 | 0 | 8.3333 | 157.6667 | 22 | 0 | 0 | 203.3333 | 0
71 | 2028-03-06 | 0 | 0 | 2.3333 | 4 | 33.3333 | 131.6667 | 29.3333 | 0 | 0 | 200.6667 | 0
72 | 2028-03-13 | 0 | 0 | 0 | 0 | 0 | 155 | 22 | 10.6667 | 0 | 187.6667 | 0
73 | 2028-03-20 | 0 | 0 | 0 | 0 | 33.3333 | 126.6667 | 29.3333 | 16 | 0 | 205.3333 | 0
74 | 2028-03-27 | 0 | 0 | 0 | 0 | 0 | 148.6667 | 22 | 16 | 0 | 186.6667 | 0
75 | 2028-04-03 | 0 | 0 | 0 | 0 | 0 | 124 | 21 | 16 | 0 | 161 | 0
76 | 2028-04-10 | 0 | 0 | 0 | 0 | 0 | 128.6667 | 12 | 2.6667 | 0 | 143.3333 | 0
77 | 2028-04-17 | 0 | 0 | 0 | 0 | 0 | 98.6667 | 10 | 0 | 0 | 108.6667 | 0
78 | 2028-04-24 | 0 | 0 | 0 | 0 | 0 | 118 | 0 | 0 | 0 | 118 | 0
79 | 2028-05-01 | 0 | 0 | 0 | 0 | 0 | 86.6667 | 0 | 0 | 0 | 86.6667 | 0
80 | 2028-05-08 | 0 | 0 | 0 | 0 | 0 | 47.3333 | 0 | 0 | 0 | 47.3333 | 0
81 | 2028-05-15 | 0 | 0 | 0 | 0 | 0 | 5.3333 | 0 | 0 | 16 | 21.3333 | 0
82 | 2028-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0
83 | 2028-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0
84 | 2028-06-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0
85 | 2028-06-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 2028-06-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 2028-06-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 2028-07-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 2028-07-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 2028-07-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 2028-07-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 2028-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 2028-08-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 2028-08-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 2028-08-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 2028-08-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 2028-09-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 2028-09-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 2028-09-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 2028-09-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 2028-10-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 2028-10-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 2028-10-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 2028-10-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 2028-10-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 2028-11-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Cost curve
Baseline cost and labor loading
Direct BOQ budget only. Equal daily earning within each activity; no actual progress represented.
Week | Week start | Planned direct value USD | Cumulative planned USD | Cumulative % | Labor hours
1 | 2026-11-02 | 0 | 0 | 0% | 960
2 | 2026-11-09 | 0 | 0 | 0% | 960
3 | 2026-11-16 | 0 | 0 | 0% | 960
4 | 2026-11-23 | 155336.1231 | 155336.1231 | 0.6868% | 1152
5 | 2026-11-30 | 155336.1231 | 310672.2462 | 1.374% | 1152
6 | 2026-12-07 | 155336.1231 | 466008.3692 | 2.06% | 1152
7 | 2026-12-14 | 155336.1231 | 621344.4923 | 2.747% | 1152
8 | 2026-12-21 | 155336.1231 | 776680.6154 | 3.434% | 1152
9 | 2026-12-28 | 155336.1231 | 932016.7385 | 4.121% | 1152
10 | 2027-01-04 | 219268.0615 | 1151284.8 | 5.09% | 1008
11 | 2027-01-11 | 283200 | 1434484.8 | 6.343% | 864
12 | 2027-01-18 | 280751.2105 | 1715236.0105 | 7.584% | 2640
13 | 2027-01-25 | 280751.2105 | 1995987.221 | 8.825% | 2640
14 | 2027-02-01 | 280751.2105 | 2276738.4315 | 10.07% | 2640
15 | 2027-02-08 | 280751.2105 | 2557489.642 | 11.31% | 2640
16 | 2027-02-15 | 280751.2105 | 2838240.8525 | 12.55% | 2640
17 | 2027-02-22 | 280751.2105 | 3118992.063 | 13.79% | 2640
18 | 2027-03-01 | 280751.2105 | 3399743.2735 | 15.03% | 2640
19 | 2027-03-08 | 509191.8684 | 3908935.1419 | 17.28% | 1560
20 | 2027-03-15 | 554880 | 4463815.1419 | 19.74% | 1344
21 | 2027-03-22 | 554880 | 5018695.1419 | 22.19% | 1344
22 | 2027-03-29 | 92480 | 5111175.1419 | 22.6% | 224
23 | 2027-04-05 | 67272.0595 | 5178447.2014 | 22.9% | 1344
24 | 2027-04-12 | 101968.2897 | 5280415.4911 | 23.35% | 1888
25 | 2027-04-19 | 218774.5984 | 5499190.0895 | 24.31% | 2176
26 | 2027-04-26 | 314413.5338 | 5813603.6232 | 25.7% | 3008
27 | 2027-05-03 | 341385.6342 | 6154989.2574 | 27.21% | 3584
28 | 2027-05-10 | 117486.9675 | 6272476.225 | 27.73% | 2224
29 | 2027-05-17 | 133863.4475 | 6406339.6725 | 28.33% | 2768
30 | 2027-05-24 | 144711.7546 | 6551051.4271 | 28.97% | 2928
31 | 2027-05-31 | 151216.6146 | 6702268.0418 | 29.63% | 2592
32 | 2027-06-07 | 138687.968 | 6840956.0097 | 30.25% | 2928
33 | 2027-06-14 | 177374.4684 | 7018330.4782 | 31.03% | 3232
34 | 2027-06-21 | 177374.4684 | 7195704.9466 | 31.82% | 3232
35 | 2027-06-28 | 177374.4684 | 7373079.415 | 32.6% | 3232
36 | 2027-07-05 | 189578.7384 | 7562658.1534 | 33.44% | 3632
37 | 2027-07-12 | 184907.9684 | 7747566.1218 | 34.26% | 3472
38 | 2027-07-19 | 200128.2384 | 7947694.3602 | 35.14% | 3936
39 | 2027-07-26 | 203144.2384 | 8150838.5986 | 36.04% | 4000
40 | 2027-08-02 | 207661.7384 | 8358500.337 | 36.96% | 4176
41 | 2027-08-09 | 213693.7384 | 8572194.0754 | 37.9% | 4304
42 | 2027-08-16 | 225898.0084 | 8798092.0838 | 38.9% | 4704
43 | 2027-08-23 | 221227.2384 | 9019319.3222 | 39.88% | 4544
44 | 2027-08-30 | 236447.5084 | 9255766.8306 | 40.92% | 5008
45 | 2027-09-06 | 239463.5084 | 9495230.3391 | 41.98% | 5072
46 | 2027-09-13 | 243981.0084 | 9739211.3475 | 43.06% | 5248
47 | 2027-09-20 | 250013.0084 | 9989224.3559 | 44.17% | 5376
48 | 2027-09-27 | 250013.0084 | 10239237.3643 | 45.27% | 5376
49 | 2027-10-04 | 250013.0084 | 10489250.3727 | 46.38% | 5376
50 | 2027-10-11 | 250013.0084 | 10739263.3811 | 47.48% | 5376
51 | 2027-10-18 | 250013.0084 | 10989276.3895 | 48.59% | 5376
52 | 2027-10-25 | 324119.7022 | 11313396.0917 | 50.02% | 6144
53 | 2027-11-01 | 324119.7022 | 11637515.794 | 51.46% | 6144
54 | 2027-11-08 | 398226.396 | 12035742.19 | 53.22% | 6912
55 | 2027-11-15 | 373524.1648 | 12409266.3548 | 54.87% | 6656
56 | 2027-11-22 | 398226.396 | 12807492.7508 | 56.63% | 6912
57 | 2027-11-29 | 373524.1648 | 13181016.9156 | 58.28% | 6656
58 | 2027-12-06 | 398226.396 | 13579243.3116 | 60.04% | 6912
59 | 2027-12-13 | 373524.1648 | 13952767.4764 | 61.69% | 6656
60 | 2027-12-20 | 398226.396 | 14350993.8725 | 63.45% | 6912
61 | 2027-12-27 | 373524.1648 | 14724518.0372 | 65.1% | 6656
62 | 2028-01-03 | 378650.1827 | 15103168.2199 | 66.78% | 6336
63 | 2028-01-10 | 396855.3115 | 15500023.5314 | 68.53% | 7520
64 | 2028-01-17 | 309028.917 | 15809052.4484 | 69.9% | 6464
65 | 2028-01-24 | 404411.5786 | 16213464.0271 | 71.69% | 7616
66 | 2028-01-31 | 328999.3528 | 16542463.3798 | 73.14% | 5520
67 | 2028-02-07 | 443646.7156 | 16986110.0955 | 75.1% | 7616
68 | 2028-02-14 | 510979.6394 | 17497089.7349 | 77.36% | 8032
69 | 2028-02-21 | 551227.9652 | 18048317.7001 | 79.8% | 10256
70 | 2028-02-28 | 565633.879 | 18613951.5791 | 82.3% | 9760
71 | 2028-03-06 | 536558.2519 | 19150509.831 | 84.67% | 9632
72 | 2028-03-13 | 546712.219 | 19697222.05 | 87.09% | 9008
73 | 2028-03-20 | 534946.9471 | 20232168.9971 | 89.46% | 9856
74 | 2028-03-27 | 551032.2842 | 20783201.2813 | 91.89% | 8960
75 | 2028-04-03 | 462955.0099 | 21246156.2912 | 93.94% | 7728
76 | 2028-04-10 | 463152.9426 | 21709309.2338 | 95.99% | 6880
77 | 2028-04-17 | 306557.64 | 22015866.8738 | 97.34% | 5216
78 | 2028-04-24 | 312980.24 | 22328847.1138 | 98.73% | 5664
79 | 2028-05-01 | 171698.04 | 22500545.1538 | 99.49% | 4160
80 | 2028-05-08 | 100874.24 | 22601419.3938 | 99.93% | 2272
81 | 2028-05-15 | 15456 | 22616875.3938 | 100% | 1024
82 | 2028-05-22 | 0 | 22616875.3938 | 100% | 1152
83 | 2028-05-29 | 0 | 22616875.3938 | 100% | 1152
84 | 2028-06-05 | 0 | 22616875.3938 | 100% | 768
85 | 2028-06-12 | 0 | 22616875.3938 | 100% | 0
86 | 2028-06-19 | 0 | 22616875.3938 | 100% | 0
87 | 2028-06-26 | 0 | 22616875.3938 | 100% | 0
88 | 2028-07-03 | 0 | 22616875.3938 | 100% | 0
89 | 2028-07-10 | 0 | 22616875.3938 | 100% | 0
90 | 2028-07-17 | 0 | 22616875.3938 | 100% | 0
91 | 2028-07-24 | 0 | 22616875.3938 | 100% | 0
92 | 2028-07-31 | 0 | 22616875.3938 | 100% | 0
93 | 2028-08-07 | 0 | 22616875.3938 | 100% | 0
94 | 2028-08-14 | 0 | 22616875.3938 | 100% | 0
95 | 2028-08-21 | 0 | 22616875.3938 | 100% | 0
96 | 2028-08-28 | 0 | 22616875.3938 | 100% | 0
97 | 2028-09-04 | 0 | 22616875.3938 | 100% | 0
98 | 2028-09-11 | 0 | 22616875.3938 | 100% | 0
99 | 2028-09-18 | 0 | 22616875.3938 | 100% | 0
100 | 2028-09-25 | 0 | 22616875.3938 | 100% | 0
101 | 2028-10-02 | 0 | 22616875.3938 | 100% | 0
102 | 2028-10-09 | 0 | 22616875.3938 | 100% | 0
103 | 2028-10-16 | 0 | 22616875.3938 | 100% | 0
104 | 2028-10-23 | 0 | 22616875.3938 | 100% | 0
105 | 2028-10-30 | 0 | 22616875.3938 | 100% | 0
106 | 2028-11-06 | 0 | 22616875.3938 | 100% | 0

## Milestones
Programme milestones
Finish dates are the last planned working day of the activity.
Milestone | Activity | Finish offset | Finish date | Float wd
Excavation complete | P-010 | 57 | 2027-01-06 | 0
Raft complete | P-040 | 127 | 2027-03-29 | 0
Podium roof complete | P-060 | 161 | 2027-05-07 | 298
Tower 1 structure complete | T1-L12-H | 368 | 2028-01-04 | 60
Tower 2 structure complete | T2-L12-H | 380 | 2028-01-18 | 48
Tower 3 structure complete | T3-L12-H | 392 | 2028-02-01 | 36
Tower 4 structure complete | T4-L12-H | 404 | 2028-02-15 | 24
Tower 5 structure complete | T5-L12-H | 416 | 2028-02-29 | 12
Tower 6 structure complete | T6-L12-H | 428 | 2028-03-14 | 0
Tower 1 weatherproofing | T1-RF | 387 | 2028-01-26 | 65
Tower 2 weatherproofing | T2-RF | 399 | 2028-02-09 | 53
Tower 3 weatherproofing | T3-RF | 411 | 2028-02-23 | 41
Tower 4 weatherproofing | T4-RF | 423 | 2028-03-08 | 29
Tower 5 weatherproofing | T5-RF | 435 | 2028-03-22 | 17
Tower 6 weatherproofing | T6-RF | 447 | 2028-04-05 | 5
Practical completion | PC-001 | 502 | 2028-06-08 | 0

## Risk register
Programme interfaces and release risks
Planning actions, not reported site incidents.
ID | Issue | Effect | Owner role | Mitigation / release condition | Status
R01 | Formwork overlap | Concurrent floor cycles increase crew demand | Construction manager | Review Workforce red thresholds and stagger floor starts | Open
R02 | Glazing release | Finishes depend on weather-tightness | Procurement lead | Freeze dimensions and approve samples before production | Open
R03 | Concrete curing | Five workdays is an explicit release hold, not strength evidence | Site engineer | Confirm test results and temporary works release before stripping | Open
R04 | Screed moisture | Fourteen-day waiting allowance may not achieve required moisture | Finishes lead | Test substrate before installation | Open
R05 | Public holidays | Baseline excludes Sundays only | Planner | Apply project-specific holiday and weather calendars | Open
R06 | Podium logistics | Tower crews and podium works may share crane/access zones | Construction manager | Coordinate access, lifting plans and workface allocations | Open
R07 | MEP interfaces | MEP is excluded from priced BOQ but affects finishes | Interface coordinator | Integrate first-fix and inspection gates before field issue | Open
R08 | Budget phasing | Detailed programme redistributes the same BOQ baseline | Cost controller | Rebaseline cash forecast before project use | Open

## Checks
Programme logic and cost reconciliation
Independent forward/backward passes, package allocation and weekly load totals.
Control | Model result | Independent control | Difference | Tolerance | Status | Unit
BOQ allocation total | 22616875.3938 | 22616875.3938 | 0 | 0.01 | OK | USD
Forward pass completion | 502 | 502 | 0 | 0.01 | OK | wd
Backward pass minimum float | 0 | 0 | 0 | 0.01 | OK | wd
Negative logic gaps | 0 | 0 | 0 | 0.01 | OK | links
Weekly cost loading | 22616875.3938 | 22616875.3938 | 0 | 0.01 | OK | USD
Labor loading | 353880 | 353880 | 0 | 0.01 | OK | hours
Calendar days available | 900 | 900 | 0 | 0.01 | OK | wd
Completion inside calendar | 1 | 1 | 0 | 0.01 | OK | flag
BOQ code | Allocated share | Expected | Difference
EW01 | 1 | 1 | 0
EW02 | 1 | 1 | 0
EW03 | 1 | 1 | 0
RC01 | 1 | 1 | 0
RC02 | 1 | 1 | 0
RC03 | 1 | 1 | -1.5543e-15
RC04 | 1 | 1 | -1.5543e-15
RC05 | 1 | 1 | -1.5543e-15
RC06 | 1 | 1 | -1.5543e-15
RC07 | 1 | 1 | -1.5543e-15
RC08 | 1 | 1 | 0
RC09 | 1 | 1 | 0
RB01 | 1 | 1 | -1.7764e-15
FW01 | 1 | 1 | -1.5543e-15
FW02 | 1 | 1 | -1.5543e-15
FW03 | 1 | 1 | -1.5543e-15
FW04 | 1 | 1 | -1.5543e-15
FW05 | 1 | 1 | 0
FW06 | 1 | 1 | 0
EN01 | 1 | 1 | 0
EN02 | 1 | 1 | -1.1102e-16
EN03 | 1 | 1 | -1.1102e-16
EN04 | 1 | 1 | -1.1102e-16
AR01 | 1 | 1 | -1.5543e-15
AR02 | 1 | 1 | -1.5543e-15
AR03 | 1 | 1 | -1.5543e-15
AR04 | 1 | 1 | -1.5543e-15
AR05 | 1 | 1 | -1.5543e-15
AR06 | 1 | 1 | -1.5543e-15
EX01 | 1 | 1 | 0
EX02 | 1 | 1 | 0
EX03 | 1 | 1 | 0

## Calendar
Six-day working calendar
Sunday excluded. No public holidays assumed.
Working day | Calendar offset | Working date | Weekday
1 | 0 | 2026-11-02 | Mon
2 | 1 | 2026-11-03 | Tue
3 | 2 | 2026-11-04 | Wed
4 | 3 | 2026-11-05 | Thu
5 | 4 | 2026-11-06 | Fri
6 | 5 | 2026-11-07 | Sat
7 | 7 | 2026-11-09 | Mon
8 | 8 | 2026-11-10 | Tue
9 | 9 | 2026-11-11 | Wed
10 | 10 | 2026-11-12 | Thu
11 | 11 | 2026-11-13 | Fri
12 | 12 | 2026-11-14 | Sat
13 | 14 | 2026-11-16 | Mon
14 | 15 | 2026-11-17 | Tue
15 | 16 | 2026-11-18 | Wed
16 | 17 | 2026-11-19 | Thu
17 | 18 | 2026-11-20 | Fri
18 | 19 | 2026-11-21 | Sat
19 | 21 | 2026-11-23 | Mon
20 | 22 | 2026-11-24 | Tue
21 | 23 | 2026-11-25 | Wed
22 | 24 | 2026-11-26 | Thu
23 | 25 | 2026-11-27 | Fri
24 | 26 | 2026-11-28 | Sat
25 | 28 | 2026-11-30 | Mon
26 | 29 | 2026-12-01 | Tue
27 | 30 | 2026-12-02 | Wed
28 | 31 | 2026-12-03 | Thu
29 | 32 | 2026-12-04 | Fri
30 | 33 | 2026-12-05 | Sat
31 | 35 | 2026-12-07 | Mon
32 | 36 | 2026-12-08 | Tue
33 | 37 | 2026-12-09 | Wed
34 | 38 | 2026-12-10 | Thu
35 | 39 | 2026-12-11 | Fri
36 | 40 | 2026-12-12 | Sat
37 | 42 | 2026-12-14 | Mon
38 | 43 | 2026-12-15 | Tue
39 | 44 | 2026-12-16 | Wed
40 | 45 | 2026-12-17 | Thu
41 | 46 | 2026-12-18 | Fri
42 | 47 | 2026-12-19 | Sat
43 | 49 | 2026-12-21 | Mon
44 | 50 | 2026-12-22 | Tue
45 | 51 | 2026-12-23 | Wed
46 | 52 | 2026-12-24 | Thu
47 | 53 | 2026-12-25 | Fri
48 | 54 | 2026-12-26 | Sat
49 | 56 | 2026-12-28 | Mon
50 | 57 | 2026-12-29 | Tue
51 | 58 | 2026-12-30 | Wed
52 | 59 | 2026-12-31 | Thu
53 | 60 | 2027-01-01 | Fri
54 | 61 | 2027-01-02 | Sat
55 | 63 | 2027-01-04 | Mon
56 | 64 | 2027-01-05 | Tue
57 | 65 | 2027-01-06 | Wed
58 | 66 | 2027-01-07 | Thu
59 | 67 | 2027-01-08 | Fri
60 | 68 | 2027-01-09 | Sat
61 | 70 | 2027-01-11 | Mon
62 | 71 | 2027-01-12 | Tue
63 | 72 | 2027-01-13 | Wed
64 | 73 | 2027-01-14 | Thu
65 | 74 | 2027-01-15 | Fri
66 | 75 | 2027-01-16 | Sat
67 | 77 | 2027-01-18 | Mon
68 | 78 | 2027-01-19 | Tue
69 | 79 | 2027-01-20 | Wed
70 | 80 | 2027-01-21 | Thu
71 | 81 | 2027-01-22 | Fri
72 | 82 | 2027-01-23 | Sat
73 | 84 | 2027-01-25 | Mon
74 | 85 | 2027-01-26 | Tue
75 | 86 | 2027-01-27 | Wed
76 | 87 | 2027-01-28 | Thu
77 | 88 | 2027-01-29 | Fri
78 | 89 | 2027-01-30 | Sat
79 | 91 | 2027-02-01 | Mon
80 | 92 | 2027-02-02 | Tue
81 | 93 | 2027-02-03 | Wed
82 | 94 | 2027-02-04 | Thu
83 | 95 | 2027-02-05 | Fri
84 | 96 | 2027-02-06 | Sat
85 | 98 | 2027-02-08 | Mon
86 | 99 | 2027-02-09 | Tue
87 | 100 | 2027-02-10 | Wed
88 | 101 | 2027-02-11 | Thu
89 | 102 | 2027-02-12 | Fri
90 | 103 | 2027-02-13 | Sat
91 | 105 | 2027-02-15 | Mon
92 | 106 | 2027-02-16 | Tue
93 | 107 | 2027-02-17 | Wed
94 | 108 | 2027-02-18 | Thu
95 | 109 | 2027-02-19 | Fri
96 | 110 | 2027-02-20 | Sat
97 | 112 | 2027-02-22 | Mon
98 | 113 | 2027-02-23 | Tue
99 | 114 | 2027-02-24 | Wed
100 | 115 | 2027-02-25 | Thu
101 | 116 | 2027-02-26 | Fri
102 | 117 | 2027-02-27 | Sat
103 | 119 | 2027-03-01 | Mon
104 | 120 | 2027-03-02 | Tue
105 | 121 | 2027-03-03 | Wed
106 | 122 | 2027-03-04 | Thu
107 | 123 | 2027-03-05 | Fri
108 | 124 | 2027-03-06 | Sat
109 | 126 | 2027-03-08 | Mon
110 | 127 | 2027-03-09 | Tue
111 | 128 | 2027-03-10 | Wed
112 | 129 | 2027-03-11 | Thu
113 | 130 | 2027-03-12 | Fri
114 | 131 | 2027-03-13 | Sat
115 | 133 | 2027-03-15 | Mon
116 | 134 | 2027-03-16 | Tue
117 | 135 | 2027-03-17 | Wed
118 | 136 | 2027-03-18 | Thu
119 | 137 | 2027-03-19 | Fri
120 | 138 | 2027-03-20 | Sat
121 | 140 | 2027-03-22 | Mon
122 | 141 | 2027-03-23 | Tue
123 | 142 | 2027-03-24 | Wed
124 | 143 | 2027-03-25 | Thu
125 | 144 | 2027-03-26 | Fri
126 | 145 | 2027-03-27 | Sat
127 | 147 | 2027-03-29 | Mon
128 | 148 | 2027-03-30 | Tue
129 | 149 | 2027-03-31 | Wed
130 | 150 | 2027-04-01 | Thu
131 | 151 | 2027-04-02 | Fri
132 | 152 | 2027-04-03 | Sat
133 | 154 | 2027-04-05 | Mon
134 | 155 | 2027-04-06 | Tue
135 | 156 | 2027-04-07 | Wed
136 | 157 | 2027-04-08 | Thu
137 | 158 | 2027-04-09 | Fri
138 | 159 | 2027-04-10 | Sat
139 | 161 | 2027-04-12 | Mon
140 | 162 | 2027-04-13 | Tue
141 | 163 | 2027-04-14 | Wed
142 | 164 | 2027-04-15 | Thu
143 | 165 | 2027-04-16 | Fri
144 | 166 | 2027-04-17 | Sat
145 | 168 | 2027-04-19 | Mon
146 | 169 | 2027-04-20 | Tue
147 | 170 | 2027-04-21 | Wed
148 | 171 | 2027-04-22 | Thu
149 | 172 | 2027-04-23 | Fri
150 | 173 | 2027-04-24 | Sat
151 | 175 | 2027-04-26 | Mon
152 | 176 | 2027-04-27 | Tue
153 | 177 | 2027-04-28 | Wed
154 | 178 | 2027-04-29 | Thu
155 | 179 | 2027-04-30 | Fri
156 | 180 | 2027-05-01 | Sat
157 | 182 | 2027-05-03 | Mon
158 | 183 | 2027-05-04 | Tue
159 | 184 | 2027-05-05 | Wed
160 | 185 | 2027-05-06 | Thu
161 | 186 | 2027-05-07 | Fri
162 | 187 | 2027-05-08 | Sat
163 | 189 | 2027-05-10 | Mon
164 | 190 | 2027-05-11 | Tue
165 | 191 | 2027-05-12 | Wed
166 | 192 | 2027-05-13 | Thu
167 | 193 | 2027-05-14 | Fri
168 | 194 | 2027-05-15 | Sat
169 | 196 | 2027-05-17 | Mon
170 | 197 | 2027-05-18 | Tue
171 | 198 | 2027-05-19 | Wed
172 | 199 | 2027-05-20 | Thu
173 | 200 | 2027-05-21 | Fri
174 | 201 | 2027-05-22 | Sat
175 | 203 | 2027-05-24 | Mon
176 | 204 | 2027-05-25 | Tue
177 | 205 | 2027-05-26 | Wed
178 | 206 | 2027-05-27 | Thu
179 | 207 | 2027-05-28 | Fri
180 | 208 | 2027-05-29 | Sat
181 | 210 | 2027-05-31 | Mon
182 | 211 | 2027-06-01 | Tue
183 | 212 | 2027-06-02 | Wed
184 | 213 | 2027-06-03 | Thu
185 | 214 | 2027-06-04 | Fri
186 | 215 | 2027-06-05 | Sat
187 | 217 | 2027-06-07 | Mon
188 | 218 | 2027-06-08 | Tue
189 | 219 | 2027-06-09 | Wed
190 | 220 | 2027-06-10 | Thu
191 | 221 | 2027-06-11 | Fri
192 | 222 | 2027-06-12 | Sat
193 | 224 | 2027-06-14 | Mon
194 | 225 | 2027-06-15 | Tue
195 | 226 | 2027-06-16 | Wed
196 | 227 | 2027-06-17 | Thu
197 | 228 | 2027-06-18 | Fri
198 | 229 | 2027-06-19 | Sat
199 | 231 | 2027-06-21 | Mon
200 | 232 | 2027-06-22 | Tue
201 | 233 | 2027-06-23 | Wed
202 | 234 | 2027-06-24 | Thu
203 | 235 | 2027-06-25 | Fri
204 | 236 | 2027-06-26 | Sat
205 | 238 | 2027-06-28 | Mon
206 | 239 | 2027-06-29 | Tue
207 | 240 | 2027-06-30 | Wed
208 | 241 | 2027-07-01 | Thu
209 | 242 | 2027-07-02 | Fri
210 | 243 | 2027-07-03 | Sat
211 | 245 | 2027-07-05 | Mon
212 | 246 | 2027-07-06 | Tue
213 | 247 | 2027-07-07 | Wed
214 | 248 | 2027-07-08 | Thu
215 | 249 | 2027-07-09 | Fri
216 | 250 | 2027-07-10 | Sat
217 | 252 | 2027-07-12 | Mon
218 | 253 | 2027-07-13 | Tue
219 | 254 | 2027-07-14 | Wed
220 | 255 | 2027-07-15 | Thu
221 | 256 | 2027-07-16 | Fri
222 | 257 | 2027-07-17 | Sat
223 | 259 | 2027-07-19 | Mon
224 | 260 | 2027-07-20 | Tue
225 | 261 | 2027-07-21 | Wed
226 | 262 | 2027-07-22 | Thu
227 | 263 | 2027-07-23 | Fri
228 | 264 | 2027-07-24 | Sat
229 | 266 | 2027-07-26 | Mon
230 | 267 | 2027-07-27 | Tue
231 | 268 | 2027-07-28 | Wed
232 | 269 | 2027-07-29 | Thu
233 | 270 | 2027-07-30 | Fri
234 | 271 | 2027-07-31 | Sat
235 | 273 | 2027-08-02 | Mon
236 | 274 | 2027-08-03 | Tue
237 | 275 | 2027-08-04 | Wed
238 | 276 | 2027-08-05 | Thu
239 | 277 | 2027-08-06 | Fri
240 | 278 | 2027-08-07 | Sat
241 | 280 | 2027-08-09 | Mon
242 | 281 | 2027-08-10 | Tue
243 | 282 | 2027-08-11 | Wed
244 | 283 | 2027-08-12 | Thu
245 | 284 | 2027-08-13 | Fri
246 | 285 | 2027-08-14 | Sat
247 | 287 | 2027-08-16 | Mon
248 | 288 | 2027-08-17 | Tue
249 | 289 | 2027-08-18 | Wed
250 | 290 | 2027-08-19 | Thu
251 | 291 | 2027-08-20 | Fri
252 | 292 | 2027-08-21 | Sat
253 | 294 | 2027-08-23 | Mon
254 | 295 | 2027-08-24 | Tue
255 | 296 | 2027-08-25 | Wed
256 | 297 | 2027-08-26 | Thu
257 | 298 | 2027-08-27 | Fri
258 | 299 | 2027-08-28 | Sat
259 | 301 | 2027-08-30 | Mon
260 | 302 | 2027-08-31 | Tue
261 | 303 | 2027-09-01 | Wed
262 | 304 | 2027-09-02 | Thu
263 | 305 | 2027-09-03 | Fri
264 | 306 | 2027-09-04 | Sat
265 | 308 | 2027-09-06 | Mon
266 | 309 | 2027-09-07 | Tue
267 | 310 | 2027-09-08 | Wed
268 | 311 | 2027-09-09 | Thu
269 | 312 | 2027-09-10 | Fri
270 | 313 | 2027-09-11 | Sat
271 | 315 | 2027-09-13 | Mon
272 | 316 | 2027-09-14 | Tue
273 | 317 | 2027-09-15 | Wed
274 | 318 | 2027-09-16 | Thu
275 | 319 | 2027-09-17 | Fri
276 | 320 | 2027-09-18 | Sat
277 | 322 | 2027-09-20 | Mon
278 | 323 | 2027-09-21 | Tue
279 | 324 | 2027-09-22 | Wed
280 | 325 | 2027-09-23 | Thu
281 | 326 | 2027-09-24 | Fri
282 | 327 | 2027-09-25 | Sat
283 | 329 | 2027-09-27 | Mon
284 | 330 | 2027-09-28 | Tue
285 | 331 | 2027-09-29 | Wed
286 | 332 | 2027-09-30 | Thu
287 | 333 | 2027-10-01 | Fri
288 | 334 | 2027-10-02 | Sat
289 | 336 | 2027-10-04 | Mon
290 | 337 | 2027-10-05 | Tue
291 | 338 | 2027-10-06 | Wed
292 | 339 | 2027-10-07 | Thu
293 | 340 | 2027-10-08 | Fri
294 | 341 | 2027-10-09 | Sat
295 | 343 | 2027-10-11 | Mon
296 | 344 | 2027-10-12 | Tue
297 | 345 | 2027-10-13 | Wed
298 | 346 | 2027-10-14 | Thu
299 | 347 | 2027-10-15 | Fri
300 | 348 | 2027-10-16 | Sat
301 | 350 | 2027-10-18 | Mon
302 | 351 | 2027-10-19 | Tue
303 | 352 | 2027-10-20 | Wed
304 | 353 | 2027-10-21 | Thu
305 | 354 | 2027-10-22 | Fri
306 | 355 | 2027-10-23 | Sat
307 | 357 | 2027-10-25 | Mon
308 | 358 | 2027-10-26 | Tue
309 | 359 | 2027-10-27 | Wed
310 | 360 | 2027-10-28 | Thu
311 | 361 | 2027-10-29 | Fri
312 | 362 | 2027-10-30 | Sat
313 | 364 | 2027-11-01 | Mon
314 | 365 | 2027-11-02 | Tue
315 | 366 | 2027-11-03 | Wed
316 | 367 | 2027-11-04 | Thu
317 | 368 | 2027-11-05 | Fri
318 | 369 | 2027-11-06 | Sat
319 | 371 | 2027-11-08 | Mon
320 | 372 | 2027-11-09 | Tue
321 | 373 | 2027-11-10 | Wed
322 | 374 | 2027-11-11 | Thu
323 | 375 | 2027-11-12 | Fri
324 | 376 | 2027-11-13 | Sat
325 | 378 | 2027-11-15 | Mon
326 | 379 | 2027-11-16 | Tue
327 | 380 | 2027-11-17 | Wed
328 | 381 | 2027-11-18 | Thu
329 | 382 | 2027-11-19 | Fri
330 | 383 | 2027-11-20 | Sat
331 | 385 | 2027-11-22 | Mon
332 | 386 | 2027-11-23 | Tue
333 | 387 | 2027-11-24 | Wed
334 | 388 | 2027-11-25 | Thu
335 | 389 | 2027-11-26 | Fri
336 | 390 | 2027-11-27 | Sat
337 | 392 | 2027-11-29 | Mon
338 | 393 | 2027-11-30 | Tue
339 | 394 | 2027-12-01 | Wed
340 | 395 | 2027-12-02 | Thu
341 | 396 | 2027-12-03 | Fri
342 | 397 | 2027-12-04 | Sat
343 | 399 | 2027-12-06 | Mon
344 | 400 | 2027-12-07 | Tue
345 | 401 | 2027-12-08 | Wed
346 | 402 | 2027-12-09 | Thu
347 | 403 | 2027-12-10 | Fri
348 | 404 | 2027-12-11 | Sat
349 | 406 | 2027-12-13 | Mon
350 | 407 | 2027-12-14 | Tue
351 | 408 | 2027-12-15 | Wed
352 | 409 | 2027-12-16 | Thu
353 | 410 | 2027-12-17 | Fri
354 | 411 | 2027-12-18 | Sat
355 | 413 | 2027-12-20 | Mon
356 | 414 | 2027-12-21 | Tue
357 | 415 | 2027-12-22 | Wed
358 | 416 | 2027-12-23 | Thu
359 | 417 | 2027-12-24 | Fri
360 | 418 | 2027-12-25 | Sat
361 | 420 | 2027-12-27 | Mon
362 | 421 | 2027-12-28 | Tue
363 | 422 | 2027-12-29 | Wed
364 | 423 | 2027-12-30 | Thu
365 | 424 | 2027-12-31 | Fri
366 | 425 | 2028-01-01 | Sat
367 | 427 | 2028-01-03 | Mon
368 | 428 | 2028-01-04 | Tue
369 | 429 | 2028-01-05 | Wed
370 | 430 | 2028-01-06 | Thu
371 | 431 | 2028-01-07 | Fri
372 | 432 | 2028-01-08 | Sat
373 | 434 | 2028-01-10 | Mon
374 | 435 | 2028-01-11 | Tue
375 | 436 | 2028-01-12 | Wed
376 | 437 | 2028-01-13 | Thu
377 | 438 | 2028-01-14 | Fri
378 | 439 | 2028-01-15 | Sat
379 | 441 | 2028-01-17 | Mon
380 | 442 | 2028-01-18 | Tue
381 | 443 | 2028-01-19 | Wed
382 | 444 | 2028-01-20 | Thu
383 | 445 | 2028-01-21 | Fri
384 | 446 | 2028-01-22 | Sat
385 | 448 | 2028-01-24 | Mon
386 | 449 | 2028-01-25 | Tue
387 | 450 | 2028-01-26 | Wed
388 | 451 | 2028-01-27 | Thu
389 | 452 | 2028-01-28 | Fri
390 | 453 | 2028-01-29 | Sat
391 | 455 | 2028-01-31 | Mon
392 | 456 | 2028-02-01 | Tue
393 | 457 | 2028-02-02 | Wed
394 | 458 | 2028-02-03 | Thu
395 | 459 | 2028-02-04 | Fri
396 | 460 | 2028-02-05 | Sat
397 | 462 | 2028-02-07 | Mon
398 | 463 | 2028-02-08 | Tue
399 | 464 | 2028-02-09 | Wed
400 | 465 | 2028-02-10 | Thu
401 | 466 | 2028-02-11 | Fri
402 | 467 | 2028-02-12 | Sat
403 | 469 | 2028-02-14 | Mon
404 | 470 | 2028-02-15 | Tue
405 | 471 | 2028-02-16 | Wed
406 | 472 | 2028-02-17 | Thu
407 | 473 | 2028-02-18 | Fri
408 | 474 | 2028-02-19 | Sat
409 | 476 | 2028-02-21 | Mon
410 | 477 | 2028-02-22 | Tue
411 | 478 | 2028-02-23 | Wed
412 | 479 | 2028-02-24 | Thu
413 | 480 | 2028-02-25 | Fri
414 | 481 | 2028-02-26 | Sat
415 | 483 | 2028-02-28 | Mon
416 | 484 | 2028-02-29 | Tue
417 | 485 | 2028-03-01 | Wed
418 | 486 | 2028-03-02 | Thu
419 | 487 | 2028-03-03 | Fri
420 | 488 | 2028-03-04 | Sat
421 | 490 | 2028-03-06 | Mon
422 | 491 | 2028-03-07 | Tue
423 | 492 | 2028-03-08 | Wed
424 | 493 | 2028-03-09 | Thu
425 | 494 | 2028-03-10 | Fri
426 | 495 | 2028-03-11 | Sat
427 | 497 | 2028-03-13 | Mon
428 | 498 | 2028-03-14 | Tue
429 | 499 | 2028-03-15 | Wed
430 | 500 | 2028-03-16 | Thu
431 | 501 | 2028-03-17 | Fri
432 | 502 | 2028-03-18 | Sat
433 | 504 | 2028-03-20 | Mon
434 | 505 | 2028-03-21 | Tue
435 | 506 | 2028-03-22 | Wed
436 | 507 | 2028-03-23 | Thu
437 | 508 | 2028-03-24 | Fri
438 | 509 | 2028-03-25 | Sat
439 | 511 | 2028-03-27 | Mon
440 | 512 | 2028-03-28 | Tue
441 | 513 | 2028-03-29 | Wed
442 | 514 | 2028-03-30 | Thu
443 | 515 | 2028-03-31 | Fri
444 | 516 | 2028-04-01 | Sat
445 | 518 | 2028-04-03 | Mon
446 | 519 | 2028-04-04 | Tue
447 | 520 | 2028-04-05 | Wed
448 | 521 | 2028-04-06 | Thu
449 | 522 | 2028-04-07 | Fri
450 | 523 | 2028-04-08 | Sat
451 | 525 | 2028-04-10 | Mon
452 | 526 | 2028-04-11 | Tue
453 | 527 | 2028-04-12 | Wed
454 | 528 | 2028-04-13 | Thu
455 | 529 | 2028-04-14 | Fri
456 | 530 | 2028-04-15 | Sat
457 | 532 | 2028-04-17 | Mon
458 | 533 | 2028-04-18 | Tue
459 | 534 | 2028-04-19 | Wed
460 | 535 | 2028-04-20 | Thu
461 | 536 | 2028-04-21 | Fri
462 | 537 | 2028-04-22 | Sat
463 | 539 | 2028-04-24 | Mon
464 | 540 | 2028-04-25 | Tue
465 | 541 | 2028-04-26 | Wed
466 | 542 | 2028-04-27 | Thu
467 | 543 | 2028-04-28 | Fri
468 | 544 | 2028-04-29 | Sat
469 | 546 | 2028-05-01 | Mon
470 | 547 | 2028-05-02 | Tue
471 | 548 | 2028-05-03 | Wed
472 | 549 | 2028-05-04 | Thu
473 | 550 | 2028-05-05 | Fri
474 | 551 | 2028-05-06 | Sat
475 | 553 | 2028-05-08 | Mon
476 | 554 | 2028-05-09 | Tue
477 | 555 | 2028-05-10 | Wed
478 | 556 | 2028-05-11 | Thu
479 | 557 | 2028-05-12 | Fri
480 | 558 | 2028-05-13 | Sat
481 | 560 | 2028-05-15 | Mon
482 | 561 | 2028-05-16 | Tue
483 | 562 | 2028-05-17 | Wed
484 | 563 | 2028-05-18 | Thu
485 | 564 | 2028-05-19 | Fri
486 | 565 | 2028-05-20 | Sat
487 | 567 | 2028-05-22 | Mon
488 | 568 | 2028-05-23 | Tue
489 | 569 | 2028-05-24 | Wed
490 | 570 | 2028-05-25 | Thu
491 | 571 | 2028-05-26 | Fri
492 | 572 | 2028-05-27 | Sat
493 | 574 | 2028-05-29 | Mon
494 | 575 | 2028-05-30 | Tue
495 | 576 | 2028-05-31 | Wed
496 | 577 | 2028-06-01 | Thu
497 | 578 | 2028-06-02 | Fri
498 | 579 | 2028-06-03 | Sat
499 | 581 | 2028-06-05 | Mon
500 | 582 | 2028-06-06 | Tue
501 | 583 | 2028-06-07 | Wed
502 | 584 | 2028-06-08 | Thu
503 | 585 | 2028-06-09 | Fri
504 | 586 | 2028-06-10 | Sat
505 | 588 | 2028-06-12 | Mon
506 | 589 | 2028-06-13 | Tue
507 | 590 | 2028-06-14 | Wed
508 | 591 | 2028-06-15 | Thu
509 | 592 | 2028-06-16 | Fri
510 | 593 | 2028-06-17 | Sat
511 | 595 | 2028-06-19 | Mon
512 | 596 | 2028-06-20 | Tue
513 | 597 | 2028-06-21 | Wed
514 | 598 | 2028-06-22 | Thu
515 | 599 | 2028-06-23 | Fri
516 | 600 | 2028-06-24 | Sat
517 | 602 | 2028-06-26 | Mon
518 | 603 | 2028-06-27 | Tue
519 | 604 | 2028-06-28 | Wed
520 | 605 | 2028-06-29 | Thu
521 | 606 | 2028-06-30 | Fri
522 | 607 | 2028-07-01 | Sat
523 | 609 | 2028-07-03 | Mon
524 | 610 | 2028-07-04 | Tue
525 | 611 | 2028-07-05 | Wed
526 | 612 | 2028-07-06 | Thu
527 | 613 | 2028-07-07 | Fri
528 | 614 | 2028-07-08 | Sat
529 | 616 | 2028-07-10 | Mon
530 | 617 | 2028-07-11 | Tue
531 | 618 | 2028-07-12 | Wed
532 | 619 | 2028-07-13 | Thu
533 | 620 | 2028-07-14 | Fri
534 | 621 | 2028-07-15 | Sat
535 | 623 | 2028-07-17 | Mon
536 | 624 | 2028-07-18 | Tue
537 | 625 | 2028-07-19 | Wed
538 | 626 | 2028-07-20 | Thu
539 | 627 | 2028-07-21 | Fri
540 | 628 | 2028-07-22 | Sat
541 | 630 | 2028-07-24 | Mon
542 | 631 | 2028-07-25 | Tue
543 | 632 | 2028-07-26 | Wed
544 | 633 | 2028-07-27 | Thu
545 | 634 | 2028-07-28 | Fri
546 | 635 | 2028-07-29 | Sat
547 | 637 | 2028-07-31 | Mon
548 | 638 | 2028-08-01 | Tue
549 | 639 | 2028-08-02 | Wed
550 | 640 | 2028-08-03 | Thu
551 | 641 | 2028-08-04 | Fri
552 | 642 | 2028-08-05 | Sat
553 | 644 | 2028-08-07 | Mon
554 | 645 | 2028-08-08 | Tue
555 | 646 | 2028-08-09 | Wed
556 | 647 | 2028-08-10 | Thu
557 | 648 | 2028-08-11 | Fri
558 | 649 | 2028-08-12 | Sat
559 | 651 | 2028-08-14 | Mon
560 | 652 | 2028-08-15 | Tue
561 | 653 | 2028-08-16 | Wed
562 | 654 | 2028-08-17 | Thu
563 | 655 | 2028-08-18 | Fri
564 | 656 | 2028-08-19 | Sat
565 | 658 | 2028-08-21 | Mon
566 | 659 | 2028-08-22 | Tue
567 | 660 | 2028-08-23 | Wed
568 | 661 | 2028-08-24 | Thu
569 | 662 | 2028-08-25 | Fri
570 | 663 | 2028-08-26 | Sat
571 | 665 | 2028-08-28 | Mon
572 | 666 | 2028-08-29 | Tue
573 | 667 | 2028-08-30 | Wed
574 | 668 | 2028-08-31 | Thu
575 | 669 | 2028-09-01 | Fri
576 | 670 | 2028-09-02 | Sat
577 | 672 | 2028-09-04 | Mon
578 | 673 | 2028-09-05 | Tue
579 | 674 | 2028-09-06 | Wed
580 | 675 | 2028-09-07 | Thu
581 | 676 | 2028-09-08 | Fri
582 | 677 | 2028-09-09 | Sat
583 | 679 | 2028-09-11 | Mon
584 | 680 | 2028-09-12 | Tue
585 | 681 | 2028-09-13 | Wed
586 | 682 | 2028-09-14 | Thu
587 | 683 | 2028-09-15 | Fri
588 | 684 | 2028-09-16 | Sat
589 | 686 | 2028-09-18 | Mon
590 | 687 | 2028-09-19 | Tue
591 | 688 | 2028-09-20 | Wed
592 | 689 | 2028-09-21 | Thu
593 | 690 | 2028-09-22 | Fri
594 | 691 | 2028-09-23 | Sat
595 | 693 | 2028-09-25 | Mon
596 | 694 | 2028-09-26 | Tue
597 | 695 | 2028-09-27 | Wed
598 | 696 | 2028-09-28 | Thu
599 | 697 | 2028-09-29 | Fri
600 | 698 | 2028-09-30 | Sat
601 | 700 | 2028-10-02 | Mon
602 | 701 | 2028-10-03 | Tue
603 | 702 | 2028-10-04 | Wed
604 | 703 | 2028-10-05 | Thu
605 | 704 | 2028-10-06 | Fri
606 | 705 | 2028-10-07 | Sat
607 | 707 | 2028-10-09 | Mon
608 | 708 | 2028-10-10 | Tue
609 | 709 | 2028-10-11 | Wed
610 | 710 | 2028-10-12 | Thu
611 | 711 | 2028-10-13 | Fri
612 | 712 | 2028-10-14 | Sat
613 | 714 | 2028-10-16 | Mon
614 | 715 | 2028-10-17 | Tue
615 | 716 | 2028-10-18 | Wed
616 | 717 | 2028-10-19 | Thu
617 | 718 | 2028-10-20 | Fri
618 | 719 | 2028-10-21 | Sat
619 | 721 | 2028-10-23 | Mon
620 | 722 | 2028-10-24 | Tue
621 | 723 | 2028-10-25 | Wed
622 | 724 | 2028-10-26 | Thu
623 | 725 | 2028-10-27 | Fri
624 | 726 | 2028-10-28 | Sat
625 | 728 | 2028-10-30 | Mon
626 | 729 | 2028-10-31 | Tue
627 | 730 | 2028-11-01 | Wed
628 | 731 | 2028-11-02 | Thu
629 | 732 | 2028-11-03 | Fri
630 | 733 | 2028-11-04 | Sat
631 | 735 | 2028-11-06 | Mon
632 | 736 | 2028-11-07 | Tue
633 | 737 | 2028-11-08 | Wed
634 | 738 | 2028-11-09 | Thu
635 | 739 | 2028-11-10 | Fri
636 | 740 | 2028-11-11 | Sat
637 | 742 | 2028-11-13 | Mon
638 | 743 | 2028-11-14 | Tue
639 | 744 | 2028-11-15 | Wed
640 | 745 | 2028-11-16 | Thu
641 | 746 | 2028-11-17 | Fri
642 | 747 | 2028-11-18 | Sat
643 | 749 | 2028-11-20 | Mon
644 | 750 | 2028-11-21 | Tue
645 | 751 | 2028-11-22 | Wed
646 | 752 | 2028-11-23 | Thu
647 | 753 | 2028-11-24 | Fri
648 | 754 | 2028-11-25 | Sat
649 | 756 | 2028-11-27 | Mon
650 | 757 | 2028-11-28 | Tue
651 | 758 | 2028-11-29 | Wed
652 | 759 | 2028-11-30 | Thu
653 | 760 | 2028-12-01 | Fri
654 | 761 | 2028-12-02 | Sat
655 | 763 | 2028-12-04 | Mon
656 | 764 | 2028-12-05 | Tue
657 | 765 | 2028-12-06 | Wed
658 | 766 | 2028-12-07 | Thu
659 | 767 | 2028-12-08 | Fri
660 | 768 | 2028-12-09 | Sat
661 | 770 | 2028-12-11 | Mon
662 | 771 | 2028-12-12 | Tue
663 | 772 | 2028-12-13 | Wed
664 | 773 | 2028-12-14 | Thu
665 | 774 | 2028-12-15 | Fri
666 | 775 | 2028-12-16 | Sat
667 | 777 | 2028-12-18 | Mon
668 | 778 | 2028-12-19 | Tue
669 | 779 | 2028-12-20 | Wed
670 | 780 | 2028-12-21 | Thu
671 | 781 | 2028-12-22 | Fri
672 | 782 | 2028-12-23 | Sat
673 | 784 | 2028-12-25 | Mon
674 | 785 | 2028-12-26 | Tue
675 | 786 | 2028-12-27 | Wed
676 | 787 | 2028-12-28 | Thu
677 | 788 | 2028-12-29 | Fri
678 | 789 | 2028-12-30 | Sat
679 | 791 | 2029-01-01 | Mon
680 | 792 | 2029-01-02 | Tue
681 | 793 | 2029-01-03 | Wed
682 | 794 | 2029-01-04 | Thu
683 | 795 | 2029-01-05 | Fri
684 | 796 | 2029-01-06 | Sat
685 | 798 | 2029-01-08 | Mon
686 | 799 | 2029-01-09 | Tue
687 | 800 | 2029-01-10 | Wed
688 | 801 | 2029-01-11 | Thu
689 | 802 | 2029-01-12 | Fri
690 | 803 | 2029-01-13 | Sat
691 | 805 | 2029-01-15 | Mon
692 | 806 | 2029-01-16 | Tue
693 | 807 | 2029-01-17 | Wed
694 | 808 | 2029-01-18 | Thu
695 | 809 | 2029-01-19 | Fri
696 | 810 | 2029-01-20 | Sat
697 | 812 | 2029-01-22 | Mon
698 | 813 | 2029-01-23 | Tue
699 | 814 | 2029-01-24 | Wed
700 | 815 | 2029-01-25 | Thu
701 | 816 | 2029-01-26 | Fri
702 | 817 | 2029-01-27 | Sat
703 | 819 | 2029-01-29 | Mon
704 | 820 | 2029-01-30 | Tue
705 | 821 | 2029-01-31 | Wed
706 | 822 | 2029-02-01 | Thu
707 | 823 | 2029-02-02 | Fri
708 | 824 | 2029-02-03 | Sat
709 | 826 | 2029-02-05 | Mon
710 | 827 | 2029-02-06 | Tue
711 | 828 | 2029-02-07 | Wed
712 | 829 | 2029-02-08 | Thu
713 | 830 | 2029-02-09 | Fri
714 | 831 | 2029-02-10 | Sat
715 | 833 | 2029-02-12 | Mon
716 | 834 | 2029-02-13 | Tue
717 | 835 | 2029-02-14 | Wed
718 | 836 | 2029-02-15 | Thu
719 | 837 | 2029-02-16 | Fri
720 | 838 | 2029-02-17 | Sat
721 | 840 | 2029-02-19 | Mon
722 | 841 | 2029-02-20 | Tue
723 | 842 | 2029-02-21 | Wed
724 | 843 | 2029-02-22 | Thu
725 | 844 | 2029-02-23 | Fri
726 | 845 | 2029-02-24 | Sat
727 | 847 | 2029-02-26 | Mon
728 | 848 | 2029-02-27 | Tue
729 | 849 | 2029-02-28 | Wed
730 | 850 | 2029-03-01 | Thu
731 | 851 | 2029-03-02 | Fri
732 | 852 | 2029-03-03 | Sat
733 | 854 | 2029-03-05 | Mon
734 | 855 | 2029-03-06 | Tue
735 | 856 | 2029-03-07 | Wed
736 | 857 | 2029-03-08 | Thu
737 | 858 | 2029-03-09 | Fri
738 | 859 | 2029-03-10 | Sat
739 | 861 | 2029-03-12 | Mon
740 | 862 | 2029-03-13 | Tue
741 | 863 | 2029-03-14 | Wed
742 | 864 | 2029-03-15 | Thu
743 | 865 | 2029-03-16 | Fri
744 | 866 | 2029-03-17 | Sat
745 | 868 | 2029-03-19 | Mon
746 | 869 | 2029-03-20 | Tue
747 | 870 | 2029-03-21 | Wed
748 | 871 | 2029-03-22 | Thu
749 | 872 | 2029-03-23 | Fri
750 | 873 | 2029-03-24 | Sat
751 | 875 | 2029-03-26 | Mon
752 | 876 | 2029-03-27 | Tue
753 | 877 | 2029-03-28 | Wed
754 | 878 | 2029-03-29 | Thu
755 | 879 | 2029-03-30 | Fri
756 | 880 | 2029-03-31 | Sat
757 | 882 | 2029-04-02 | Mon
758 | 883 | 2029-04-03 | Tue
759 | 884 | 2029-04-04 | Wed
760 | 885 | 2029-04-05 | Thu
761 | 886 | 2029-04-06 | Fri
762 | 887 | 2029-04-07 | Sat
763 | 889 | 2029-04-09 | Mon
764 | 890 | 2029-04-10 | Tue
765 | 891 | 2029-04-11 | Wed
766 | 892 | 2029-04-12 | Thu
767 | 893 | 2029-04-13 | Fri
768 | 894 | 2029-04-14 | Sat
769 | 896 | 2029-04-16 | Mon
770 | 897 | 2029-04-17 | Tue
771 | 898 | 2029-04-18 | Wed
772 | 899 | 2029-04-19 | Thu
773 | 900 | 2029-04-20 | Fri
774 | 901 | 2029-04-21 | Sat
775 | 903 | 2029-04-23 | Mon
776 | 904 | 2029-04-24 | Tue
777 | 905 | 2029-04-25 | Wed
778 | 906 | 2029-04-26 | Thu
779 | 907 | 2029-04-27 | Fri
780 | 908 | 2029-04-28 | Sat
781 | 910 | 2029-04-30 | Mon
782 | 911 | 2029-05-01 | Tue
783 | 912 | 2029-05-02 | Wed
784 | 913 | 2029-05-03 | Thu
785 | 914 | 2029-05-04 | Fri
786 | 915 | 2029-05-05 | Sat
787 | 917 | 2029-05-07 | Mon
788 | 918 | 2029-05-08 | Tue
789 | 919 | 2029-05-09 | Wed
790 | 920 | 2029-05-10 | Thu
791 | 921 | 2029-05-11 | Fri
792 | 922 | 2029-05-12 | Sat
793 | 924 | 2029-05-14 | Mon
794 | 925 | 2029-05-15 | Tue
795 | 926 | 2029-05-16 | Wed
796 | 927 | 2029-05-17 | Thu
797 | 928 | 2029-05-18 | Fri
798 | 929 | 2029-05-19 | Sat
799 | 931 | 2029-05-21 | Mon
800 | 932 | 2029-05-22 | Tue
801 | 933 | 2029-05-23 | Wed
802 | 934 | 2029-05-24 | Thu
803 | 935 | 2029-05-25 | Fri
804 | 936 | 2029-05-26 | Sat
805 | 938 | 2029-05-28 | Mon
806 | 939 | 2029-05-29 | Tue
807 | 940 | 2029-05-30 | Wed
808 | 941 | 2029-05-31 | Thu
809 | 942 | 2029-06-01 | Fri
810 | 943 | 2029-06-02 | Sat
811 | 945 | 2029-06-04 | Mon
812 | 946 | 2029-06-05 | Tue
813 | 947 | 2029-06-06 | Wed
814 | 948 | 2029-06-07 | Thu
815 | 949 | 2029-06-08 | Fri
816 | 950 | 2029-06-09 | Sat
817 | 952 | 2029-06-11 | Mon
818 | 953 | 2029-06-12 | Tue
819 | 954 | 2029-06-13 | Wed
820 | 955 | 2029-06-14 | Thu
821 | 956 | 2029-06-15 | Fri
822 | 957 | 2029-06-16 | Sat
823 | 959 | 2029-06-18 | Mon
824 | 960 | 2029-06-19 | Tue
825 | 961 | 2029-06-20 | Wed
826 | 962 | 2029-06-21 | Thu
827 | 963 | 2029-06-22 | Fri
828 | 964 | 2029-06-23 | Sat
829 | 966 | 2029-06-25 | Mon
830 | 967 | 2029-06-26 | Tue
831 | 968 | 2029-06-27 | Wed
832 | 969 | 2029-06-28 | Thu
833 | 970 | 2029-06-29 | Fri
834 | 971 | 2029-06-30 | Sat
835 | 973 | 2029-07-02 | Mon
836 | 974 | 2029-07-03 | Tue
837 | 975 | 2029-07-04 | Wed
838 | 976 | 2029-07-05 | Thu
839 | 977 | 2029-07-06 | Fri
840 | 978 | 2029-07-07 | Sat
841 | 980 | 2029-07-09 | Mon
842 | 981 | 2029-07-10 | Tue
843 | 982 | 2029-07-11 | Wed
844 | 983 | 2029-07-12 | Thu
845 | 984 | 2029-07-13 | Fri
846 | 985 | 2029-07-14 | Sat
847 | 987 | 2029-07-16 | Mon
848 | 988 | 2029-07-17 | Tue
849 | 989 | 2029-07-18 | Wed
850 | 990 | 2029-07-19 | Thu
851 | 991 | 2029-07-20 | Fri
852 | 992 | 2029-07-21 | Sat
853 | 994 | 2029-07-23 | Mon
854 | 995 | 2029-07-24 | Tue
855 | 996 | 2029-07-25 | Wed
856 | 997 | 2029-07-26 | Thu
857 | 998 | 2029-07-27 | Fri
858 | 999 | 2029-07-28 | Sat
859 | 1001 | 2029-07-30 | Mon
860 | 1002 | 2029-07-31 | Tue
861 | 1003 | 2029-08-01 | Wed
862 | 1004 | 2029-08-02 | Thu
863 | 1005 | 2029-08-03 | Fri
864 | 1006 | 2029-08-04 | Sat
865 | 1008 | 2029-08-06 | Mon
866 | 1009 | 2029-08-07 | Tue
867 | 1010 | 2029-08-08 | Wed
868 | 1011 | 2029-08-09 | Thu
869 | 1012 | 2029-08-10 | Fri
870 | 1013 | 2029-08-11 | Sat
871 | 1015 | 2029-08-13 | Mon
872 | 1016 | 2029-08-14 | Tue
873 | 1017 | 2029-08-15 | Wed
874 | 1018 | 2029-08-16 | Thu
875 | 1019 | 2029-08-17 | Fri
876 | 1020 | 2029-08-18 | Sat
877 | 1022 | 2029-08-20 | Mon
878 | 1023 | 2029-08-21 | Tue
879 | 1024 | 2029-08-22 | Wed
880 | 1025 | 2029-08-23 | Thu
881 | 1026 | 2029-08-24 | Fri
882 | 1027 | 2029-08-25 | Sat
883 | 1029 | 2029-08-27 | Mon
884 | 1030 | 2029-08-28 | Tue
885 | 1031 | 2029-08-29 | Wed
886 | 1032 | 2029-08-30 | Thu
887 | 1033 | 2029-08-31 | Fri
888 | 1034 | 2029-09-01 | Sat
889 | 1036 | 2029-09-03 | Mon
890 | 1037 | 2029-09-04 | Tue
891 | 1038 | 2029-09-05 | Wed
892 | 1039 | 2029-09-06 | Thu
893 | 1040 | 2029-09-07 | Fri
894 | 1041 | 2029-09-08 | Sat
895 | 1043 | 2029-09-10 | Mon
896 | 1044 | 2029-09-11 | Tue
897 | 1045 | 2029-09-12 | Wed
898 | 1046 | 2029-09-13 | Thu
899 | 1047 | 2029-09-14 | Fri
900 | 1048 | 2029-09-15 | Sat
Formulas:
Working date = 'Controls'!$B8+[Calendar offset]

## Basis
Programme methods and assumptions
CPM conventions, resource assumptions and scope boundaries.
Topic | Method and scope
Document | CE-R01-PC Rev 01. Independent portfolio planning study.
Scope | Priced civil, structural, envelope and architectural works from CE-R01 BOQ. No client completion record is represented.
Calendar | Monday to Saturday, eight hours/day. No public holidays or weather allowances. Day zero is the baseline origin.
Forward pass | ES is maximum predecessor EF plus lag. EF = ES + duration, using exclusive finish offsets.
Backward pass | LF is minimum successor LS minus lag. Terminal LF is project completion. LS = LF - duration. Float = LS - ES.
Dates | Start date uses calendar index ES+1. Non-zero finish date uses EF. Zero-duration interface milestones use the next workday at the event boundary.
Productivity | Durations = rounded-up quantity / daily output. Crews and production rates are explicit planning assumptions, not field observations.
Structural sequencing | Deck formwork, reinforcement, concrete and curing gate repeat by storey. This is a planning package sequence, not a temporary works method statement.
Reinforcement allocation | 50% of reinforcement BOQ budget/quantity assigned to raft, 50% across 78 tower floors. This scheduling split is provisional and differs from a fabrication breakdown.
Finish releases | Masonry follows the floor three storeys above where available. Floor finish requires screed waiting period and tower glazing.
Resource logic | Crews assigned per activity. Weekly average workforce is worker-days divided by six. No automatic resource levelling or intraday peak claim.
Costs | Direct BOQ costs allocated exactly once across activities. Preliminaries and margin excluded from this direct-value curve.
Cashflow interface | Detailed baseline differs from earlier aggregate cash model phasing. Use the programme cost curve to rebaseline cash forecast before operational use.
MEP interface | MEP is excluded from the source BOQ. First-fix, testing and authority releases must be integrated before execution.
Change controls | Activity durations and costs recalculate in the existing network. Adding/deleting activities requires updating logic and weekly loading ranges.
Horizon | Calendar is 900 workdays; weekly model covers baseline and target plus two weeks. Calendar/horizon checks expose overrun.